## Slide 1: Nodal Change Control Update

## Slide 2: Change Control Update Agenda
Refresh understanding of Nodal Change Control approval process from May 2007
  Slides 3-5 (copied from original Nodal PMO presentation)
Change Control Board Activity Summary – Post-Baseline 2
  As of 6/23/2008
Appendix
  Recent NPRRs with Impacts (6)
    Approved by PRS (ready for TAC on 6/26 – all are believed to be essential)
      NPRR097 – Changes to Section 8
      NPRR107 – Nodal Emergency Interruptible Load Service (EILS)
      NPRR130 – CRR Settlements Revenue Equalization
    Tabled at PRS (Impact Analyses not yet complete – all are believed to be essential)
      NPRR091 – Scarcity Pricing and Mitigated Offer Cap… for a Total of 45 Days
      NPRR102 – Implementation of PUC Subst. R. 25.505(f)
      NPRR113 – Load Resource Type Indicator for A/S Trades and Self-Arranged A/S

## Slide 3: Change control objectives: future NPRRs as well as the backlog
To maintain overall system integrity by ensuring each project is focused on an explicit, current, common baseline
To formally authorize additional scope into the program, and its budget and schedule implications
To verify that a request is approved by the appropriate authority
To ensure implementation of each accepted change
To support the maintenance of traceability across the system (from protocols to test cases) by synchronizing all projects to one version of the protocols
Current emphasis is the backlog and advancing the current baseline - but process must handle additional NPRRs and subsequent baseline advances
May 10 2007

## Slide 4: The proposed process is designed to handle NPRRs and Nodal change requests in tandem
TPTF
PRS 1
IC (1-4)
PRS 2
TAC
CCB
CR* Approval
Process
Y/N for
Go-Live
IA (group
changes)
Draft
NPRR
CR*
Projects
BOD
Approves
PRS to finalize
language and
recommend Go-Live
position
PRS to approve
time and dollars
ERCOT to provide an
initial impact categorization
and a Program position for Go-Live
Approval depends on
budget thresholds and
funding sources
The process is modified slightly to accommodate the change control objectives…
CR* - A Change Request is the Nodal
program’s mechanism for implementing
changes to scope, timescales, cost. A change
request normally incorporates multiple items
including NPRRs, white papers, etc.
Technical Change Control
Board to work with projects
to develop and submit
change requests to the CCB
CR Approval
Periodic updates will be provided to TPTF, PRS, TAC & BOD on the status of NPRRs
NPRR Approval
May 10 2007

## Slide 5: Proposed a resolution to TAC to limit additional scope change
The objective of the Nodal program is to design and implement the nodal market system and transition from the current zonal market to the nodal market by 12/1/2008.
The budget presented to the Board of Directors, TAC and TPTF was based on this timeline and the scope defined under the May 2006 version of the protocols (termed “Baseline 0”).
Multiple NPRRs have been approved since May 2006 and the program is currently working to incorporate them into a revised baseline (“Baseline 1”). The scope of the revised baseline includes the previous baseline plus NPRRs approved as of March 31st, 2007.
As the program continues through its delivery cycle, and the systems are built and tested, additional changes requiring additional work and rework will potentially have an exponential impact on cost and schedule.
Such changes are to be minimized. As a practical measure:
  An NPRR that is not essential for Go-Live should be deferred until after nodal goes live.
  An NPRR that addresses the correct working of the Nodal Market will be considered as essential for Go-Live.
  An NPRR that deals with adding or enhancing functionality to the existing systems will be considered not essential for Go-Live.
ERCOT will work with TPTF and PRS to determine whether a specific NPRR is not “essential for Go-Live”
May 10 2007

## Slide 6: Change Control Board Activity Summary – Post-Baseline 2
Group / Type |  | Counts |  | Cost Estimates
Changes Approved as Part of Latest Nodal Fee Filing |  |  | 52 | $ 8,419k
 | NPRRs (17), NOGRRs (15) | 32 |  | $ 615k
 | White Papers (8), Change Items (12) | 20 |  | $ 7,804k
Subsequent Post-Baseline 2 Items |  |  | 28 | $2,319k-$3,044k
 | No Impact NPRRs (18), NOGRRs (2), White Papers (1) | 21 |  | $ 0
 | NPRRs with Impacts (NPRR 091, 097, 102, 107, 113, 130) | 6 |  | $2,225k-$2,950k
 | Change Item with Impact (CI232 - Mimic User) | 1 |  | $ 94k
Pending Impact Assessment (25 NPRRs, 2 NOGRRs, 2 White Papers) |  |  | 29 | TBD
Nodal Deferred Items (placed on the 2009 PPL) |  |  | 17 | N/A
Totals |  |  | 126 | $10,738k-$11,463k
As of June 23, 2008

## Slide 7: APPENDIX

## Slide 8: NPRR097 Changes to Section 8, Performance Monitoring and Compliance (formerly titled “Changes to Section 8 to Incorporate Role of TRE, the IMM, and the Concept of Market Compliance”)
NPRR No. |  | 97
Characteristics |  | 
Total $ impact range |  | $125k-$150k
Essential for Go-Live (E/D/N) |  | E
Detail |  | 
Item description: | Cost Drivers / Risks / Dependencies: | 
Essential for Go-Live justification: Specifies the performance measures ERCOT will be monitoring for QSEs, TSPs and ERCOT. The NPRR ensures that ERCOT is collecting the necessary data and producing the appropriate reports for IMM and TRE. The changes improve the performance monitoring for various areas in EMS such as telemetry, resources, and other areas. It is anticipated that the changes will reduce implementation costs and market costs for compliance. Modifications will be made to EMS systems related to Regulation Service and Generation Resource Energy Deployment Criteria Performance (Sec. 8.1.4.1), and to EDW/MIS for posting reports. | Cost Drivers: EMS: ~$120k for making Section 8.1.4.1 changes. EDW / MIS: ~$17k for posting Section 8 reports. Cost do not include estimates for a TAC-approved monitoring program which is referenced in this NPRR and is under development via a NOGRR. Risks: Timely implementation of changes Impacts to downstream systems possible. Market review - finalization of the Protocol language through the stakeholder process. Pending Issues: Schedule for completion of these changes have not been finalized. It is anticipated that implementation will initiate in September and will take 12 weeks to complete. | 
Scope Change (Y/N): Yes | Schedule Delay (Y/N): No

## Slide 9: NPRR107 Nodal Emergency Interruptible Load Service (EILS)
NPRR No. |  | 107
Characteristics |  | 
Total $ impact range |  | < $50k
Essential for Go-Live (E/D/N) |  | E
Detail |  | 
Item description: | Cost Drivers / Risks / Dependencies: | 
Essential for Go-Live justification: Transitions the Emergency Interruptible Load Service (EILS) to the Nodal Market and complies with PUCT requirements. The changes are made to be consistent with the split deployment of Load Resources in Step 2 of EECP, by grouping the EILS Loads into two approximately equal groups if the total amount of available EILS equals or exceeds 500 MW. It also has the following posting requirements: (1) Post the number of MW procured per EILS Time Period, the number of EILS Loads selected and the projected total cost of EILS for that Contract Period; (2) Post the list of Load Resources on MIS Certified immediately following DRUC for each QSE with a Load Resource obligation which may be deployed to interrupt; (3) Post a summary of each QSEs EILS Load availability and performance | Cost Drivers: MIS – For posting reports. Risks: Market review - finalization of the Protocol language through the stakeholder process. Pending Issues: None | 
Scope Change (Y/N): Yes | Schedule Delay (Y/N): No

## Slide 10: NPRR130 CRR Settlements Revenue Equalization
NPRR No. |  | 130
Characteristics |  | 
Total $ impact range |  | $50k-$100k
Essential for Go-Live (E/D/N) |  | E
Detail |  | 
Item description: | Cost Drivers / Risks / Dependencies: | 
Essential for Go-Live justification: Corrects potential revenue equalization issues with current Nodal design. Adds an accounting provision to assure revenue neutrality in the Day-Ahead Market (DAM) financial activity while refunding the proper funds later through the Congestion Revenue Right (CRR) Balancing Account. Protocols require ERCOT to be revenue neutral in all markets. Without the proposed changes, ERCOT may have a shortfall or have excess revenue by the close of the DAM. | Cost Drivers: COMS - This change affects mostly settlement equations. CSI, Lodestar, Rome and Appworx systems will be modified. Risks: Market review - finalization of the Protocol language through the stakeholder process. Pending Issues: CWG believes that this NPRR would have unfair implications on the LSEs. Specifically, they have concerns about uplifting CRR shortfall to LSEs. | 
Scope Change (Y/N): Yes | Schedule Delay (Y/N): No

## Slide 11: NPRR091 Scarcity Pricing and Mitigated Offer Cap During the Period Commencing on the Nodal Market Implementation Date and Continuing for a Total of 45 Days
NPRR No. |  | 91
Characteristics |  | 
Total $ impact range |  | $50k-$100k
Essential for Go-Live (E/D/N) |  | E
Detail |  | 
Item description: | Cost Drivers / Risks / Dependencies: | 
Essential for Go-Live justification: Addresses concerns raised by the PUCT and Market Participants that actions be taken to lessen the impact of the new requirements necessitated by the start of the Texas Nodal Market until such time as Market Participants have acquired experience operating in the DAM and Real Time nodal market. It provides for a set of “guardrails” to reasonably protect against unforeseen issues associated with the operation of the Nodal Market in the period shortly after “go-live.” Modifications include: (1) Treat all transmission constraints as non-competitive constraints during the initial 30 Operating Day period, beginning with the Texas Nodal Market Implementation Date (TMID); (2) require the System-Wide Offer Cap be set to the higher of $180 or 18 mmBtu Heat Rate times the Fuel Index Price (FIP) during the initial 45 Operating Day period, beginning with the TMID and (3)establish an Energy Offer Curve floor adjusted to -$50 per MWh. | Cost Drivers: MMS and MER CDR The costs are primarily driven by MMS to implement and test the required interim process, procedure and configuration changes. Risks: Market review - finalization of the Protocol language through the stakeholder process. Timely implementation of changes Pending Issues: Schedule for completion of these changes not yet available from vendor. | 
Scope Change (Y/N): Yes | Schedule Delay (Y/N): No

## Slide 12: NPRR102 Implementation of PUC Subst. R. 25.505(f), Publication of Resource and Load Information
<number>
NPRR No. |  | 102
Characteristics |  | 
Total $ impact range |  | $1.3M-$1.9M
Essential for Go-Live (E/D/N) |  | E
Detail |  | 
Item description: | Cost Drivers / Risks / Dependencies: | 
Essential for Go-Live justification: Synchronizes Nodal Protocols with PUC Subst. R. 25.505(f). It incorporates the disclosure requirements pursuant to P.U.C. Subst. R. 25.505, Resource Adequacy in the Electric Reliability of Texas Power Region, paragraph (f), adopted under P.U.C. Project No. 33490, Rulemaking Proceeding to Address Pricing Safeguards in the Markets Operated by ERCOT. Disclosure of offers and bids and other information encourages Market Participants to take advantage of practices such as hedging, long-term contracting between Market Participants that supply power and Market Participants that serve Load, and price responsiveness by end-use customers. | Cost Drivers: MMS and EDW impacts only. Option 1: $1M to $1.5M (if extracts by disclosure area are removed) Option 2: $1.5M to $2M range Risks: Detail design is not yet available for downstream systems to assess the total impact of this NPRR. Potentially impacted systems include EMS, COMS, and MIS. Additional impacts to downstream systems can increase cost. Timely implementation of changes. Impact to Nodal go-live date unknown. Market review - finalization of the Protocol language through the stakeholder process. Pending Issues: Schedule for performing these changes by vendor. Detail design from vendor. | 
Scope Change (Y/N): Yes | Schedule Delay (Y/N): Yes

## Slide 13: NPRR113 Load Resource Type Indicator for Ancillary Service (AS) Trades and Self-Arranged AS
NPRR No. |  | 113
Characteristics |  | 
Total $ impact range |  | ~$650k
Essential for Go-Live (E/D/N) |  | E
Detail |  | 
Item description: | Cost Drivers / Risks / Dependencies: | 
Essential for Go-Live justification: There could be reliability implications to the overall grid operations as without this flag, the system could schedule RRS to be more than 50% from Load resources and there is no protocol mechanism to allow ERCOT to decommit the extra Load Resources It adds an indicator to Self-Arranged Ancillary Services and AS Trades to reflect if Responsive Reserve (RRS) service is being provided from a Generation Resource, Controllable Load Resource, or Load Resource controlled by high-set under-frequency relays. It increases the transparency of which RRS type is being self-arranged and traded. Option: ERCOT (from a reliability perspective) can initiate a Secondary AS Market to properly satisfy the 50% requirement from Generation Resources. This secondary market will potentially result in over-procurement and create uplifted costs to the market for the extra services procured to secure the 50% RRS levels from generation (as required by existing protocols). | Cost Drivers: MMS Risks: Detail design is not yet available for downstream systems to assess the total impact of this NPRR. Additional impacts to downstream systems can increase cost. Timely implementation of changes. Potential to extend the Nodal Go-Live date. Pending Issues: Schedule for completion of these changes by vendor. Detail design from vendor. | 
Scope Change (Y/N): Yes | Schedule Delay (Y/N): Yes