|  |  | System Planning Division |
| --- | --- | --- |
|  |  | Monthly Status Report to Reliability and Operations Subcommittee for June 2008 |
|  | Report Highlights |  |
| Item |  |  |
| 1. | ERCOT is currently tracking 246 active generation interconnection requests totaling almost 106,000 MW. This includes almost 54,000 MW of wind generation New Interconnect Agreements signed: Lufkin Biomass (08INR0033) in Angelina County for 45 MW |  |
| 2. | Regional Planning is currently reviewing proposed transmission improvements with a total cost of $575 Million Transmission Projects approved in 2008 to date total $169 Million All projects (in engineering, routing, licensing and construction) totals approximately $3.6 Billion Transmission Projects energized in Q2 of 2008 total about $160 Million |  |

Table of Contents

1.	Generation Interconnection	1

1.1.	New Generation Beginning Commercial Operations	1

1.2.	New Signed Interconnection Agreements (also found in 1.4 Table) 	1

1.3.	Summary of Active Generation Interconnection Requests	1

1.4.	Potential Future Generation Interconnections	2

2.	Regional Planning Group Project Reviews	4

3.	Other Notable Activities	4

# 1.	Generation Interconnection

Additional information regarding detailed generation interconnection and impact studies is contained in the “Generation Project Interconnection Information” folder in the “Operations and System Planning” area on the ERCOT website:  http://oldercot.ercot.com/tmaps.

## New Generation Beginning Commercial Operations

# None

# The installed wind capacity is 5,519 MW.

## New Signed Interconnection Agreements

# Lufkin Biomass Generation (08INR0033) in Angelina County for 45 MW

## Summary of Active Generation Interconnection Requests

| GENERATION INTERCONNECTION REQUESTS CURRENTLY BEING PROCESSED |
| --- |
| Currently tracking 242 active generation interconnection or change requests As of June 30, 2008 |
|  | North | South | West | Total |
| Security Screening Study |  | 2 | 14 | 10 | 26 |
| SSS Completed |  | 8 | 5 | 28 | 41 |
| Full Interconnect Study |  | 29 | 29 | 77 | 135 |
| FIS Completed |  | 0 | 6 | 0 | 6 |
| Interconnect Agreement Completed |  | 8 | 7 | 23 | 38 |
| Capacity for Grid, MW |  | 25,143 | 35,493 | 45,343 | 105,979 |
| Wind Capacity, MW |  | 2,415 | 9,366 | 42,023 | 53,804 |

| Fuel | Non-Public (MW) | Public (MW) | Total (MW) |
| --- | --- | --- | --- |
| Combined Cycle - Gas | 24,102 | 4,832 | 28,934 |
| Combustion Turbine - Gas | 400 | 505 | 905 |
| Nuclear | 3,200 | 9,186 | 12,386 |
| Coal | 4,144 | 4,131 | 8,275 |
| Wind | 43,714 | 10,090 | 53,804 |
| Other | 1,630 | 45 | 1,675 |
| Totals | 77,190 | 28,789 | 105,979 |

## Potential Future Generation Interconnections

The table below summarizes the publicly known potential future generation projects for the ERCOT region.  (IA=Interconnect Agreement, PL=Public Letter)

| Future Generation Interconnections (Public Projects) as of June 30, 2008 |
| --- |
| INR | SiteName | Status | County | Region | In-Service Date | Fuel | MW Into Grid | Change from Last Report |
| 07INR0022 | Panther Creek Wind Farm | IA | Howard | West | Jul-08 | Wind | 150 | Date Chg |
| 08INR0028 | McAdoo Energy Center | IA | Dickens | North | Jul-08 | Wind | 300 |  |
| 08INR0050 | Victoria Power Station | IA | Victoria | South | Jul-08 | GasCC | 332 |  |
| 07INR0027 | South Houston Green Pwr Exp Prj1 | IA | Galveston | South | Aug-08 | GasCC | 244 | Date Chg |
| 04INR0011b | Mesquite Wind Phase 4 | IA | Shackelford | West | Aug-08 | Wind | 136 |  |
| 04INR0011c | Cottonwood Wind | IA | Shackelford | West | Aug-08 | Wind | 100 |  |
| 04INR0017 | Ocotillo Wind Farm 1 | IA | Howard | West | Aug-08 | Wind | 59 |  |
| 03INR0030b | Wild Horse Wind Farm 2 | IA | Cottle | West | Aug-08 | Wind | 39 |  |
| 08INR0055 | Capricorn Ridge III | IA | Coke | West | Aug-08 | Wind | 249 |  |
| 06INR0012a | Sherbino Mesa Wind Farm 1 | IA | Pecos | West | Sep-08 | Wind | 150 |  |
| 08INR0038 | M Bar Wind | PL | Andrews | West | Sep-08 | Wind | 194 |  |
| 07INR0034 | Wolf Ridge Windfarm | IA | Cooke | North | Oct-08 | Wind | 113 |  |
| 07INR0025 | Lamesa Wind Plant | IA | Dawson | West | Oct-08 | Wind | 183 |  |
| 07INR0037 | Bull Creek Wind Plant | IA | Borden | West | Oct-08 | Wind | 180 |  |
| 07INR0045b | Airtricity Inadale | IA | Scurry | West | Nov-08 | Wind | 212 |  |
| 07INR0045a | Pyron Wind Farm | IA | Scurry | West | Nov-08 | Wind | 303 |  |
| 05INR0015a | Gulf Wind 1 | IA | Kenedy | South | Dec-08 | Wind | 283 |  |
| 06INR0022a | Penascal Wind Farm 1 | IA | Kenedy | South | Dec-08 | Wind | 202 |  |
| 09INR0026a | Sterling Energy Center | PL | Sterling | West | Dec-08 | Wind | 200 |  |
| 08INR0018 | Gunsight Mountain | IA | Howard | West | Dec-08 | Wind | 120 |  |
| 08INR0025 | Pistol Hill Energy Center | PL | Ector | West | Dec-08 | Wind | 300 |  |
| 07INR0029 | South Trent Wind Farm | IA | Taylor | West | Dec-08 | Wind | 101.2 |  |
| 07INR0005 | Notrees-1 | IA | Ector | West | Dec-08 | Wind | 150.75 |  |
| 07INR0011 | Turkey Track Energy Center | IA | Nolan | West | Dec-08 | Wind | 170 |  |
| 08INR0037 | Panther Creek 2 | IA | Howard | West | Dec-08 | Wind | 220 |  |
| 08INR0053 | Elbow Creek Wind Project | IA | Howard | West | Dec-08 | Wind | 117.3 |  |
| 08INR0059 | Gray Wind Project | PL | Borden | West | Dec-08 | Wind | 141 |  |
| 04INR0011e | Hackberry Wind Farm | IA | Shackelford | West | Dec-08 | Wind | 165 |  |
| 08INR0046 | Bosque Expansion | IA | Bosque | North | Mar-09 | GasCC | 255 |  |
| 08INR0065 | Buffalo Gap 4 and 5 | PL | Nolan | West | Mar-09 | Wind | 465 |  |
| 07INR0036 | Coyote Run Windfarm | IA | Borden | West | Mar-09 | Wind | 225 |  |
| 09INR0072 | Dansby3 | PL | Brazos | North | Apr-09 | GasCT | 48 |  |
| 09INR0028 | V H Braunig 6 | PL | Bexar | South | May-09 | GasCT | 185 |  |
| 08INR0040 | Lenorah Project | PL | Martin | West | May-09 | Wind | 350 |  |
| 09INR0060 | Wind Tex - Stephens Wind Farm | PL | Borden | West | May-09 | Wind | 141 |  |
| 08INR0035 | Cedar Bayou 4 | IA | Chambers | South | Jun-09 | GasCC | 539 |  |
| 09INR0036 | McAdoo Energy Center II | PL | Dickens | West | Jun-09 | Wind | 500 |  |
| 09INR0026 | Sterling Energy Center | PL | Sterling | West | Jun-09 | Wind | 300 |  |
| 08INR0003 | Sandow 5 | IA | Milam | North | Jul-09 | Coal | 581 |  |
| 09INR0006a | Oak Grove SES 1 | IA | Robertson | North | Jul-09 | Coal | 855 |  |
| 09INR0027 | Winchester Power Park | IA | Fayette | South | Jul-09 | GasCT | 178 |  |
| 08INR0033 | Lufkin | IA | Angelina | North | Sep-09 | Biomass | 45 | New IA |
| 05INR0015b | Gulf Wind 2 | PL | Kenedy | South | Sep-09 | Wind | 400 |  |
| 09INR0015 | Comanche Peak 1&2 Upgrade | PL | Somervell | North | Oct-09 | Nuclear | 86 |  |
| 09INR0045 | Sand Hill Peakers | PL | Travis | South | Nov-09 | GasCT | 94 |  |
| 03INR0030a | Wild Horse Wind Farm 1 | IA | Cottle | West | Nov-09 | Wind | 60 |  |
| 09INR0034 | Gatesville Wind Farm | PL | Coryell | North | Dec-09 | Wind | 200 |  |
| 09INR0006b | Oak Grove SES 2 | IA | Robertson | North | Jan-10 | Coal | 855 |  |
| 06INR0029 | Jackson Mountain | IA | Nolan | West | Jan-10 | Wind | 90 |  |
| 09INR0037 | Scurry County Wind III | PL | Scurry | West | Mar-10 | Wind | 350 |  |
| 06INR0006 | Cobisa-Greenville | PL | Hunt | North | May-10 | GasCC | 1750 |  |
| 09INR0002 | J K Spruce 2 | IA | Bexar | South | Jun-10 | Coal | 750 |  |
| 05INR0015c | Gulf Wind 3 | PL | Kenedy | South | Sep-10 | Wind | 400 |  |
| 06INR0012b | Sherbino Mesa Wind Farm 2 | IA | Pecos | West | Oct-10 | Wind | 150 |  |
| 06INR0026 | Wild Horse Mountain | IA | Howard | West | Dec-10 | Wind | 120 |  |
| 12INR0003 | Throckmorton Wind Farm | PL | Throckmorton | West | Dec-10 | Wind | 400 |  |
| 10INR0020 | Panda Temple Power | PL | Bell | North | May-11 | GasCC | 1092 |  |
| 10INR0010 | Jack County 2 | PL | Jack | North | Jun-11 | GasCC | 620 |  |
| 07INR0004 | Pampa Energy Center | PL | Gray | West | May-12 | Coal | 165 |  |
| 09INR0001 | Sandy Creek 1 | IA | McLennan | North | Jun-12 | Coal | 925 |  |
| 09INR0024 | B&B Panhandle Wind | PL | Carson | West | Jun-12 | Wind | 1001 |  |
| 12INR0004 | Fort Concho Wind Farm | PL | Tom Green | West | Jul-12 | Wind | 400 |  |
| 15INR0002 | Comanche Peak 3 and 4 | PL | Somervel | North | Jan-15 | Nuclear | 3200 |  |
| 11INR0011 | Victoria City Nuclear | PL | Victoria | South | Jan-15 | Nuclear | 3200 |  |
| 15INR0008 | STP 3 and 4 | PL | Matagorda | South | Jan-15 | Nuclear | 2700 |  |

# Regional Planning Group Project Reviews

# LCRA submitted a project to add a 3rd 345/138 kV autotransformer at the Zorn substation.  This project should be complete by summer peak 2013 and cost is estimated at $15 M.  The review of this project has been completed and the RPG Acceptance letter was distributed on June 10th, 2008.

# AEPSC submitted a project to increase the reliability of service in the Presidio area.  This project will install a second 138/69 kV autotransformer at Marfa in 2008, install 2-2.4 MW NaS battery units at Presidio in 2009, and replace the existing 69 kV line with a 138kV-capable but 69kV-operated line from Alamito Creek to Chinati to Presidio in 2012.  Total cost of the project is estimated to be $67 M.  This project was presented to TAC on June 26th, 2008 and will be presented to the ERCOT Board of Directors on July 15th, 2008.

# Oncor submitted a project to upgrade the Hillsboro to Alvarado 69 kV line.  This project will reconstruct the 27.2 mile line using conductor rated a minimum of 897 amperes on double circuit structures.  The estimated cost is $12.15 M.  The review of this project has been completed and the RPG Acceptance letter was distributed on June 10th, 2008.

# Oncor submitted a project to add a 300 Mvar dynamic reactive device at Renner station (tentative) by summer 2010.  This cost of this project will be $35 M.  This project is in ERCOT Independent Review.

# American Electric Power Service Corporation submitted a project to construct 2 new 138 kV substations, rebuild a 138 kV circuit, build  2 new 138 kV circuits, and install a new 138/69 kV autotransformer in the Abilene/San Angelo area.  The estimated cost of this project is $105.9 M.  This project is in ERCOT Independent Review.

# Oncor submitted a project to add a second 345/138 kV autotransformer at Forney.  This project was a result of the 2007 Five-Year Plan.  It has completed the comment period with no comments and an RPG Acceptance letter is being prepared.

# Luminant Energy submitted the Twin Butte – Kendall 345 kV double circuit line with series compensation.  It is a $327 million project comprised of 170 miles of 345 kV double circuit with both circuits in place, substation and breaker additions at Twin Butte and Kendall, and a 50% series compensation in each circuit.  This project is currently in the comment period.

- Oncor submitted a project to replace the Liggett #1 345/138 kV autotransformer with a 600 MVA autotransformer.  This project is estimated to cost $5.3 million and was a result of the 2007 Five-Year Plan.  This project is currently in the comment period.

- Transmission Projects energized in Q2 of 2008 include:

    - Temple Pecan Creek - Lake Creek 138 kV line

    - Fairdale Load 69 kv to 138 kV voltage conversion

    - Walnut - Fairdale 69 kV line

    - Manvel

    - Hidalgo - S. McAllen 69 kV upgrade including transformers & equipment

    - Nolanville - Harker Heights 138 kV line

    - Putnam, replace 69/138 kV transformer

    - Waterport - Loma Alta 138 kV Circuit

    - Key Substation equipment upgrade

    - Exxon-Bertron Reconfiguration and Baytown - Rohmas substation

    - Bunker – Hood rebuild

    - Olney Auto

    - Capote Substation conversion to 138 kV

    - Exxon Sharon Ridge Substation upgrade

    - Pancake – Gatesville rebuild

# Other Notable Activities

All postings referred to below can be found at http://oldercot.ercot.com/tmaps unless otherwise indicated.

- Individual TPIT Worksheets were sent out to TDSP June 19, 2008.

- Folder migrating from OLD SITE to NEW SITE is completed.  Security rolls and metadata have been set for NEW SITE files.

- Attend weekly PR60077 Registered Area Status meetings.

- Beginning July 7, 2008 this website will be replaced by a redesigned Planning and Operations website. Registration for the current site is now closed. Please visit the new Planning and Operations Information site at http://www.planning.ercot.com/login/register to pre-register for the new site. The new site will be available July 7, 2008.

- ERCOT Regional Planning has begun work on the 2013 case to be used for reliability analysis and RPG analysis.  The purpose of this effort is to extend the 2007 Five-Year plan from 2012 to 2013.  Work on the 2009 Five-Year plan will begin in October 2008 after completion of the Steady State Working Group Data Set B.

- ERCOT Regional Planning has started review of Reliability Standard Audit Worksheets (RSAWs) in preparation for the NERC compliance audit.