## Slide 1: June 2008 RO Projects Financial Overview Retail Market Subcommittee July 09, 2008 Hope Parrish Market Operations Division Projects Organization

## Slide 2: 2008 RO PPL
Planned and Unplanned 2007
Carry-over Projects
(Green Shaded Area)
Projects ABOVE the
current Capability Line
(Orange Shaded Area)
Projects BELOW the
current Capability Line
(Yellow Shaded Area)

## Slide 3: 2007 Carry-Over Projects
PR60008_01: Go-Live Update:
  06/22/2008: Performance Measures – Complete
  07/12/2008: Terms and Conditions – On Schedule
PR70007_01: Go-Live Update
  06/14/2008: Release 1 – Complete
  08/16/2008: Release 2 – On Schedule

## Slide 4: Projects ABOVE the Capability Line
No Changes
Notes: 50061_01 Moved to ON Hold: Freed up approx. $120k, however not recommended for release by CART

## Slide 5: Projects BELOW the Capability Line
No status change on these projects
Notes: ERCOT will continue to evaluate the projects under the line to determine if we can move anything up. Currently the items just below the line are funded with the 2008 PPL

## Slide 6: Financial Overview as of 05/01/2008 (cont’d)
RO PPL Budget Activity | Amount | Notes/comments
Approved RO Capability Line Budget Funding | $3.83M | Current approved RO funding allocation Designates where the capability line falls $2.27M Released due to deferred projects (Originally $6.1M Approved)
Current Forecast Spend of projects above the Capability Line | ~$2.5M | Based on current expectations and run rates for active and not started projects above the capability line
Budget Variance | ~$1.33M | Budget Variance is difference between RO Capability Line Budget Funding and Current Forecast Spend of projects above the Capability Line Variance attributed to projects deferred to future years Will be monitored throughout 2008 for reallocation to other RO projects or release to other CARTs as needed

## Slide 7: Questions / Contact
Hope Parrish
Project Manager, MO DPO
Market Operations Divisional Projects Organization
ERCOT
(512) 248-6522
hparrish@ercot.com