## Sheet1
Post-Baseline 2 Items as of June 2008
Type | Orig Sort | Item # | Source | NPRR # | Title - Short Description | Project | Market Status | Base-line | CCB Action | EMS | MMS | OS | MOTE SOTE OTS | NMMS | COMS | CRR | EDW | EIP | IDA | INF | EDS IRT | MER Training | MIS | INT | MER CDR (formerlyRTR) | MPIM
Y | 1 | 140 | NPRR | 76 | Synchronization of Emergency Electric Curtailment Plan (EECP) Event Realignment | NMMS, EMS, MMS, EIP | Approved | Post-Baseline2 | 11/14/2007 REMANDED | 3 | 2 | 4 | 4 |  | 4 | 4 |  | 4 | 4 | 4 | 3 | 3 | 4
Y | 2 | 107 | NPRR | 77 | Incorporating the ERCOT Internal Audit Department and Other Clarifications (PRR735 companion) | NA | Approved | Post-Baseline2 | NA NO IMPACT | 4 | 4 | 4 | 4 | 4 | 4 | 4 |  | 4 | 4 | 4 | 4 | 4 |  | 4
Y | 3 | 109 | NPRR | 78 | Simplifying the Dispute Process | COMS EDW MIS | Approved | Post-Baseline2 | 2007-11-14 | [9 empty] | 4 |  |  | 3
Y | 4 | 133 | NPRR | 80 | Revised Wording of Protocol Section 3.1.5.1 (Electrical buses as consequentially outaged transmission elements.) |  | Approved | Post-Baseline2 | NA NO IMPACT | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 4 | 4 | 4 | 4
Y | 5 | 136 | NPRR | 81 | Automatic Voltage Regulator (AVR) Status | NMMS | Approved | Post-Baseline2 | 12/12/2007 Info only | 3 | 4 | 4 | 4 | 1 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 4 | 4
Y | 6 | 141 | NPRR | 82 | Section 8, Performance Monitoring and Compliance, Revisions to Monitoring and Qualification Tests | EMS | Approved | Post-Baseline2 | 11/7/07 info only IMPACT in NPRR074 | 1 |  | 4 |  | 4 | 4 |  | 4 |  | 4 |  |  | 3 | 4 |  | 4
Y | 7 | 146 | NPRR | 83 | Remove Real-Time Energy Charge for a BLT from List of Real-Time Charge Types | COMS | Approved | Post-Baseline2 | NA NO IMPACT | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 |  | 3 | 4 | 4 | 4 | 4
Y | 8 | 148 | NPRR | 84 | Creating Amendment to Standard Form Market Participant Agreement |  | Approved | Post-Baseline2 | NA NO IMPACT | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 4 | 4 | 4 | 4
Y | 9 | 149 | NPRR | 85 | Revision of Digital Certificate Procedures | INT, MIS, INF | Approved | Post-Baseline2 | NA NO IMPACT | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 4 | 3 | 3 | 2 | 4 | 4
Y | 10 | 135 | NPRR | 86 | Settlement Clarifications to RUC Capacity Shortfall Ratio Share Formula | COMS, MMS, EIP, EMS, MOTE SOTE OTS | Approved | Post-Baseline2 | 2007-12-12 | 1 | 1 | 4 | 2 | 4 | 1 | 4 | 4 |  | 4 | 4 |  | 4 | 4
Y | 11 | 147 | NPRR | 87 | Market Monitor Terminology Change | NMMS MIS | Approved | Post-Baseline2 | NA NO IMPACT | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
Y | 12 | 150 | NPRR | 88 | Revision to 16.11.5, Monitoring of a Counter-Party’s Creditworthiness and Credit Exposure by ERCOT | INT, COMS, INF, EDS | Approved | Post-Baseline2 | NA NO IMPACT | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 4 | 3 | 4 | 2 | 4 | 4
Y | 13 | 167 | NPRR | 89 | Changing Posting Requirement of Certain Documents from MIS Secure to Public Area | EMS | Approved | Post-Baseline2 | 1/30/2008 NO IMPACT | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 3 | 3 | 4 | 4
Y | 14 | 151 | NPRR | 90 | Corrections of FIP-FOP in Energy Offers | MMS, INT, EDS | Approved Revised with ERCOT comments | Post-Baseline2 | 2008-01-16 | 3 | 1 | 4 |  |  | 4 | 4 | 4 |  | 4 | 4 | 2 | 3 | 4 | 1
A | 16 | 159 | NPRR | 92 | Remove Voltage Schedules Requirement | EMS | Approved | Post-Baseline2 | 3/12/08 NO IMPACT | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 3 | 4 | 3
Y | 17 | 165 | NPRR | 94 | Correct reference to credit limit determination | CRR | Approved | Post-Baseline2 | 1/30/2008 NO IMPACT | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 4 | 4 | 4 | 4
Y | 18 | 164 | NPRR | 95 | Clarify recipients of McFRIs | CRR | Approved | Post-Baseline2 | NA NO IMPACT | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 4 | 4 | 4 | 4
A | 19 | 168 | NPRR | 96 | Nodal Protocol Revisions to the RMR Startup Energy Payment | COMS | Approved | Post-Baseline2 | 1/30/2008 NO IMPACT | 4 | 4 | 4 | 4 | 4 | 1 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 4 | 4 | 4 | 4
A | 21 | 162 | NPRR | 98 | Protocols 4 and 6 Formula Clarifications | COMS | Approved | Post-Baseline2 | 1/30/2008 NO IMPACT | 4 | 4 | 4 | 4 | 4 | 1 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 4 | 4 | 4 | 4
B | 15 | 158 | NPRR | 91 | Scarcity Pricing and Mitigated Offer Cap During the Period Commencing on the Nodal Market Implementation Date and Continuing for a Total of 45 Days | MMS CDR | PRS 6/19/08 IA Review PRS 5/22 voted to table until June PRS meeting | Post-Baseline2 | CCB 6/4/08 voted to defer to Steering Committee SC 6/11/08 | 4 | 2 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 4 | 4 | 1
B | 25 | 103 | NPRR | 102 | PUCT 25.505 Publication of Resource and Load Information (Disclosure of market data (PRR697 / PUCT33490)) | EDW, MIS, MMS, COMS, EMS | PRS 6/19/08 IA Review PRS 5/22 voted to table until June PRS meeting | Post-Baseline2 | CCB 6/4/08 voted to defer to Steering Committee SC 6/11/08 | 1 | 1 | 4 | 4 | 4 | 2 | 4 | 1 |  | 4 | 4 |  | 3 | 2 |  | 4
B | 35 | 188 | NPRR | 113 | Load Resource Type Indicator for Ancillary Service (AS) Trades and Self-Arranged AS | MMS EMS | PRS 6/19/08 IA Review | Post-Baseline2 | CCB 6/4/08 voted to defer to Steering Committee SC 6/11/08 | 1 | 4 | 4 | 4 | 4 | 4 | 4 | 4 |  | 4 | 4 |  | 3 | 4 |  | 4
B | 20 | 163 | NPRR | 97 | Changes to Section 8 to Incorporate role of TRE, the IMM, and the concept of Market Compliance | SO EMS CDR | PRS 6/19/08 IA Review PRS 5/22 voted to table until June PRS meeting | Post-Baseline2 | TBD | 1 | 4 | 4 | 4 | 4 | 4 | 4 | 3 |  | 4 |  |  | 3 | 3 |  | 1
B | 29 | 184 | NPRR | 107 | Emergency Interruptible Load Service | MIS | PRS 6/19/08 IA Review | Post-Baseline2 | 2008-06-04 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 2 | 4 | 4 | 4
Z | 53 | 111 | NOGRR | 001NOGRR | NOGRRs Section 1, Overview | CRR | Approved | Post-Baseline2 | 2007-08-15 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 4 | 4 | 4 | 4 | 3 | 3 | 3 | 4
Z | 54 | 112 | NOGRR | 002NOGRR | NOGRRs Section 2, System Operations and Control Requirements | EMS, MMS, NMMS | Approved | Post-Baseline2 | 2007-08-15 | 2 | 1 | 4 | 4 | 1 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 3 | 3 | 4
Z | 72 | 96 | CI |  | EMMS Pipeline NODAL SIRs | EMS, NMMS | CCB Approved | Post-Baseline2 | 2007-09-12 | 1 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
K | 113 | 153 | WPIDA | TBD | Details on the Settlement of Combined Cycle Plants |  | TPTF Recommended 12/18/07 | Post-Baseline2 |  |  | 4 | [10 empty] | 3
I | 34 | 182 | NPRR | 112 | Emergency Base Point Price Revision | COMS | TPTF 6/9/08 Pending Language | Post-Baseline2 | 4/9/2008 NO IMPACT | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 4 | 4 | 4 | 4
I | 36 | 190 | NPRR | 114 | Section 11, Synchronization of Zonal Protocols |  | PRS 6/19/08 Pending Language | Post-Baseline2 | TBD |  | 4 | 4 | 4 |  | 4 | 4 | 4 | 4 | 4 |  |  | 3 | 4 |  | 4
I | 43 | 219 | NPRR | 124 | Resource Node Updated Definitions |  | PRS 6/19/08 Pending Language | Post-Baseline2 | TBD |  |  | 4 | 4 | 4 |  | 4 | 4 |  | 4 |  |  | 3 | 4 |  | 4
I | 44 | 221 | NPRR | 126 | Section 19, Synchronization of Zonal Protocols |  | TPTF Pending Language | Post-Baseline2 | TBD |  |  | 4 | 4 | 4 |  | 4 | 4 |  | 4 |  |  | 3 | 4 |  | 4
I | 45 | 222 | NPRR | 127 | Section 22 Attachments A, I, J & M, Synchronization of Zonal Protocols |  | TPTF 6/9/08 Pending Language | Post-Baseline2 | TBD |  | 4 | 4 | 4 |  | 4 | 4 | 4 | 4 | 4 |  |  | 3 | 4 |  | 4
I | 46 | 223 | NPRR | 128 | Combined Cycle Power Blocks with Multiple Voltage Interconnections |  | PRS 6/19/08 Pending Language | Post-Baseline2 | TBD |  | 1 | 4 | 4 |  | 4 | 4 | 4 | 4 | 4 |  |  | 3 | 4 |  | 4
I | 47 | 224 | NPRR | 129 | Section 15, Synchronization of Zonal Protocols |  | TPTF 5/22/08 Pending Language PRS 5/22/08 voted to refer to TPTF | Post-Baseline2 | TBD | [9 empty] | 4 |  |  | 3
I | 49 | 228 | NPRR | 131 | Ancillary Service Trades with ERCOT |  | PRS 6/19/08 Pending Language | Post-Baseline2 | TBD |  |  | 4 | 4 | 4 |  | 4 | 4 |  | 4 |  |  | 3 | 4 |  | 4
I | 50 | 230 | NPRR | 132 | Outage Clarification |  | PRS 6/19/08 Pending Language | Post-Baseline2 | TBD |  | 4 | 4 | 4 |  | 4 | 4 | 4 | 4 | 4 |  |  | 3 | 4 |  | 4
I | 51 | 231 | NPRR | 133 | Addtion of PSSE Format |  | PRS 6/19/08 Pending Language | Post-Baseline2 | TBD |  | 1 | 4 | 4 |  | 4 | 4 | 4 | 4 | 4 |  |  | 3 | 4 |  | 4
I | 52 | 229 | NPRR | 134 | Section 7 Cleanup |  | PRS 6/19/08 Pending Language | Post-Baseline2 | TBD | [9 empty] | 4 |  |  | 3
I | 105 | 110 | NPRR | TBD | Section 7 CRR Cleanup NPRR | CRR | TPTF Pending Language | Post-Baseline2 | TBD | [9 empty] | 4 |  |  | 3
I | 108 | 131 | NPRR | TBD | NPRR DC Tie | COMS | Draft Pending | Post-Baseline2 | TBD | [9 empty] | 4 |  |  | 3
I | 109 | 134 | NPRR | TBD | Simplifying OBLRACT and OPTRACT | COMS | TPTF Pending Language | Post-Baseline2 | TBD | [5 empty] | 1 |  |  |  | 4 |  |  | 3
I | 111 | 143 | NPRR | TBD | Failure to Update Verifiable Cost Data Results in Use of Resource Category Generic Costs | COMS | Drafted | Post-Baseline2 | TBD | [5 empty] | 2 |  |  |  | 4 |  |  | 3
I | 114 | 154 | PRR | TBD | EDS LFC Test Settlement | COMS | TPTF Pending Language | Post-Baseline2 | [13 empty] | 3
I | 115 | 156 | NPRR | TBD | Initiating the SWCAP at Real Time Market Opening |  | TPTF Pending Language | Post-Baseline2 | [10 empty] | 4 |  |  | 3
I | 116 | 157 | NPRR | TBD | Nodal Section 8 Protocol Revision Request (multiple NPRRs) | EMS EDW | TPTF Pending Language | Post-Baseline2 | [10 empty] | 4 |  |  | 3
I | 117 | 170 | NPRR | TBD | Nodal Protocols Section 3.2.3, System Adequacy Reports - Clarification Request |  | Drafted | Post-Baseline2 | TBD | [9 empty] | 4 |  |  | 3
I | 118 | 173 | NPRR | TBD | Scheduling and Operating Transmission Devices in the Nodal Environment |  | Draft Pending | Post-Baseline2 | TBD | [9 empty] | 4 |  |  | 3
I | 119 | 175 | NPRR | TBD | Nodal Protocol Step-Up Transformer Reporting Requirements |  | TPTF Pending Language | Post-Baseline2 | TBD | [9 empty] | 4 |  |  | 3
I | 120 | 178 | NPRR | TBD | Section 16: Remove Late Fee Language |  | TPTF Pending Language | Post-Baseline2 | CCB Pending 2/13/08 |  | 4 | 4 | 4 |  | 4 | 4 | 4 |  | 4 |  |  | 3
I | 121 | 179 | NPRR | TBD | Removal of partial assignment of CRR Shortfall to Real-Time |  | TPTF Pending Language | Post-Baseline2 | TBD | [9 empty] | 4 |  |  | 3
I | 122 | 201 | NPRR | TBD | Post to the MIS Resource Nodes Diagrams |  | TPTF Pending Language | Post-Baseline2 | TBD | [9 empty] | 4 |  |  | 3
I | 123 | 225 | NPRR | TBD | Verifiable Cost Draft NPRR for Nodal Protocols Sections 2, 4 and 5 |  | TPTF Pending Language | Post-Baseline2 | TBD | [9 empty] | 4 |  |  | 3
Z | 55 | 113 | NOGRR | 003NOGRR | NOGRRs Section 3, Resource Testing and Qualification Procedures | EMS | Approved | Post-Baseline2 | 2007-08-15 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 3 | 3 | 4
Z | 56 | 114 | NOGRR | 004NOGRR | NOGRRs Section 4, Emergency Operation | EMS | Approved | Post-Baseline2 | 2007-08-15 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 3 | 3 | 4
Z | 98 | WPIDA014 | WPIDA |  | Reactive Power and Voltage Support | EMS, COMS, OPs | Resolved / Closed | Post-Baseline2 | 2007-09-12 | 4 | 4 | 4 | 4 | 4 | 2 | 4 | 4 | 4 | 3 | 4 | 4 | 3 | 4
Z | 99 | WPIDA020 | WPIDA |  | Generation Schedules | EMS, MMS, NMMS, COMS, EDW, EIP, Ops, INT | Resolved / Closed | Post-Baseline2 | 2007-09-19 | 2 | 2 | 4 | 4 | 2 | 2 | 4 | 3 | 1 | 3 | 4 | 3 | 3 | 4
M | 80 | 202 | Deferred Item |  | Multiple EDW reports arising from draft NPRRs |  |  | Post-Baseline2
M | 81 | 203 | Deferred Item |  | MOTE (Market Operations Test Environment) |  |  | Post-Baseline2
M | 82 | 204 | Deferred Item |  | MMS Multiple Network Models |  |  | Post-Baseline2
M | 83 | 205 | Deferred Item |  | S&B Information Only Calculations |  |  | Post-Baseline2
M | 84 | 206 | Deferred Item |  | Dynamically scheduled resource incremental and decremental energy offer curves. |  |  | Post-Baseline2
M | 85 | 207 | Deferred Item |  | OTS (Operator Training Simulator) |  |  | Post-Baseline2
M | 86 | 208 | Deferred Item |  | Verifiable Cost Automation |  |  | Post-Baseline2
M | 87 | 209 | Deferred Item |  | Add API to CRR |  |  | Post-Baseline2
M | 88 | 210 | Deferred Item |  | Web-enabled Registration |  |  | Post-Baseline2
M | 89 | 211 | Deferred Item |  | NMMS API Upgrade |  |  | Post-Baseline2
M | 90 | 212 | Deferred Item |  | MPIM integration with Siebel |  |  | Post-Baseline2
M | 91 | 213 | Deferred Item |  | Co-optimizing energy and AS for self-committed resources in DAM |  |  | Post-Baseline2
M | 92 | 214 | Deferred Item |  | Internal-facing Alarm Handling/Presentation – Control Room/EMS |  |  | Post-Baseline2
M | 93 | 215 | Deferred Item |  | Internal-facing UI’s – Control Room/EMS |  |  | Post-Baseline2
M | 94 | 216 | Deferred Item |  | Migration of non-Nodal TML functionality to MIS; retirement of TML website |  |  | Post-Baseline2
M | 95 | 217 | Deferred Item |  | Migration of content from nodal.ercot.com website to ERCOT.com website; retirement of nodal.ercot.com website |  |  | Post-Baseline2
M | 96 | 233 | Deferred Item |  | Enhancements for Disputes API |  |  | Post-Baseline2
A | 22 | 171 | NPRR | 99 | RMR Incentive Factor Payment | COMS | Approved | Post-Baseline2 | 3/12/08 NO IMPACT | 4 | 2 | 4 | 4 | 4 | 2 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 4 | 4 | 4 | 4
Y | 23 | 166 | NPRR | 100 | Removing PCRR release mechanism | CRR COMS | Approved | Post-Baseline2 | 3/12/08 NO IMPACT | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 4 | 4 | 4 | 4
A | 24 | 176 | NPRR | 101 | Modify Time Requirements for Entry of Equipment in the Outage Scheduler | EMS | Approved | Post-Baseline2 | 3/19 NO IMPACT | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 4 | 4 | 4 | 4
A | 26 | 152 | NPRR | 103 | Settlement of Power Imported via DC Ties (Back to Back Ties) and Block Load Transfer Under Emergency Conditions | COMS | Approved | Post-Baseline2 | 3/12/08 NO IMPACT - Impact absorbed | 4 | 4 | 4 | 4 | 4 | 1 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 4 | 4 | 4 | 4
A | 27 | 180 | NPRR | 105 | Section 23, Synchronization of Zonal Protocols | None | TAC 6/5/2008 IA Review | Post-Baseline2 | 5/14/08 NO IMPACT | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 4 | 4 | 4 | 4
A | 28 | 181 | NPRR | 106 | Section 24, Synchronization of Zonal Protocols | None | TAC 6/5/2008 IA Review | Post-Baseline2 | 5/14/08 NO IMPACT | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 4 | 4 | 4 | 4
A | 30 | 183 | NPRR | 108 | Fuel Oil Price (FOP) Clarification | COMS | Approved | Post-Baseline2 | 4/9/2008 NO IMPACT | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 4 | 4 | 4 | 4
A | 31 | 186 | NPRR | 109 | Section 18, Synchronization of Zonal Protocols | None | TAC 6/5/2008 IA Review | Post-Baseline2 | 5/14/08 NO IMPACT | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 4 | 4 | 4 | 4
A | 32 | 185 | NPRR | 110 | Section 20, Synchronization of Zonal Protocols | None | TAC 6/5/2008 IA Review | Post-Baseline2 | 5/14/08 NO IMPACT | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 4 | 4 | 4 | 4
A | 33 | 187 | NPRR | 111 | Timelines for Response by ERCOT to TSP Requests |  | PRS 6/19/08 IA Review | Post-Baseline2 | TBD | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 4 | 4 | 4 | 4
A | 37 | 196 | NPRR | 117 | Resource Registration Clarification |  | PRS 6/19/08 IA Review | Post-Baseline2 | 6/4/2008 NO IMPACT | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 4 | 4 | 4 | 4
A | 38 | 197 | NPRR | 118 | Section 14, Synchronization of Zonal Protocols |  | PRS 6/19/08 IA Review | Post-Baseline2 | TBD | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 3 | 4 | 4 | 4
A | 39 | 198 | NPRR | 119 | Resource Limit Calculator |  | PRS 6/19/08 IA Review | Post-Baseline2 | TBD | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 4 | 4 | 4 | 4
A | 40 | 199 | NPRR | 120 | Corrections and Clarifications for Real Time Settlements |  | PRS 6/19/08 IA Review | Post-Baseline2 | TBD | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 4 | 4 | 4 | 4
A | 41 | 189 | NPRR | 122 | Simplify Ancillary Services Settlement Formulas |  | PRS 6/19/08 IA Review | Post-Baseline2 | TBD | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 4 | 4 | 4 | 4
A | 42 | 218 | NPRR | 123 | Inadvertent Energy Account Revision |  | PRS 6/19/08 IA Review | Post-Baseline2 | 6/4/2008 NO IMPACT | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 4 | 4 | 4 | 4
B | 48 | 194 | NPRR | 130 | CRR Settlements Revenue Equalization | COMS | PRS 6/19/08 IA Review | Post-Baseline2 | TBD | 4 | 4 | 4 | 4 | 4 | 1 | 4 | 4 |  | 4 | 4 |  | 3 | 4 |  | 4 | 4
Z | 57 | 115 | NOGRR | 005NOGRR | NOGRRs Section 5, Planning | CRR | Approved | Post-Baseline2 | 2007-08-15 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 4 | 4 | 4 | 4 | 3 | 3 | 3 | 4
Z | 58 | 116 | NOGRR | 006NOGRR | NOGRRs Section 6, Disturbance Monitoring and System Protection | EMS | Approved | Post-Baseline2 | 2007-08-15 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 3 | 3 | 4
Z | 59 | 117 | NOGRR | 007NOGRR | NOGRRs Section 7, Telemetry and Communication | MIS, INF | Approved | Post-Baseline2 | 2007-08-15 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 2 | 3
Z | 60 | 118 | NOGRR | 008NOGRR | NOGRRs Section 8, Attachment A, Detailed Black Start Information | EMS | Approved | Post-Baseline2 | 2007-08-15 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 3 | 4 | 4
Z | 61 | 119 | NOGRR | 009NOGRR | NOGRRs Section 8, Attachment B, Relay Misoperation Report | EMS | Approved | Post-Baseline2 | 2007-08-15 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 3 | 4 | 4
Z | 62 | 120 | NOGRR | 010NOGRR | NOGRRs Section 8, Attachment C, Turbine Governor Speed Tests | EMS | Approved | Post-Baseline2 | 2007-08-15 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 3 | 4 | 4
Z | 63 | 121 | NOGRR | 011NOGRR | NOGRRs Section 8, Attachment D, Seasonal Unit Net Real Power Capability Verification | EMS | Approved | Post-Baseline2 | 2007-08-15 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 3 | 4 | 4
Z | 64 | 122 | NOGRR | 012NOGRR | NOGRRs Section 8, Attachment E, Biennial Unit Reactive Limits (Lead and Lag) Verification | EMS | Approved | Post-Baseline2 | 2007-08-15 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 3 | 4 | 4
Z | 65 | 123 | NOGRR | 013NOGRR | NOGRRs Section 8, Attachment F, Seasonal Hydro Responsive Reserve Net Capability Verification | EMS | Approved | Post-Baseline2 | 2007-08-15 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 3 | 4 | 4
Z | 66 | 124 | NOGRR | 014NOGRR | NOGRRs Section 8, Attachment G, Load Resource Tests | EMS | Approved | Post-Baseline2 | 2007-08-15 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 3 | 4 | 4
Z | 67 | 125 | NOGRR | 015NOGRR | NOGRRs Section 8, Attachment H, Unit Alternative Fuel Capability | EMS | Approved | Post-Baseline2 | 2007-08-15 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 3 | 4 | 4
J | 68 | 192 | NOGRR | 018NOGRR | Synchronization of OGRR204, Hotline Technology Update |  | ROS 6/12/08 IA Review | Post-Baseline2 | 5/14 NO IMPACT | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 4 | 4 | 4 | 4
J | 69 | 193 | NOGRR | 019NOGRR | Synchronization of OGRR206, Black Start Satellite Phones |  | ROS 6/12/08 IA Review | Post-Baseline2 | 5/14 NO IMPACT | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 4 | 4 | 4 | 4
E | 70 | 226 | NOGRR | 020NOGRR | Synchronization of OGRR198, Firm Load Shed Implementation Time Periods |  | TPTF 6/9/08 Pending Language | Post-Baseline2 | 6/4/2008 NO IMPACT | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 4 | 4 | 4 | 4
E | 71 | 227 | NOGRR | 021NOGRR | Synchronization of OGRR205, Modify Responsive Reserve Service Obligation |  | TPTF 6/9/08 Pending Language | Post-Baseline2 | 6/4/2008 NO IMPACT | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 4 | 4 | 4 | 4
Z | 73 | 101 | CI |  | LMP Contour Map Requirement | MIS, MMS, NMMS, EIP, EDW, INT | CCB Approved | Post-Baseline2 | 2007-09-12 | 4 | 1 | 4 | 4 | 1 | 4 | 4 | 1 | 2 | 4 | 4 |  | 3 | 1 | 1
Z | 74 | 108 | CI |  | MMS Security Interface | MMS | TCCB Approved | Post-Baseline2 | NA DIR APPROVAL | 4 | 1 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
Z | 106 | 128 | CI |  | World Map Dynamic Display of ERCOT Transmission System | EMS, NMMS | CCB Approved | Post-Baseline2 | 2007-10-03 | [12 empty] | 3
Z | 107 | 129 | CI |  | SPS Monitor | EMS | CCB Approved | Post-Baseline2 | 2007-09-12 | [12 empty] | 3
Z | 75 | 130 | CI |  | Market Participant Submission Items | MMS | CCB Approved | Post-Baseline2 | 2008-01-09 | 4 | 1 | 4 |  | 4 | 4 | 4 | 4 |  | 4 | 4 | 4 | 3 | 3
Z | 76 | 137 | CI |  | EMS Hardware Increase for Areva | EMS | CCB Approved | Post-Baseline2 | 2007-09-12 | 1 | [8 empty] | 4 |  |  | 3
Z | 77 | 138 | CI |  | MMS Hardware Increase for ABB | MMS | CCB Approved | Post-Baseline2 | 2007-09-12 |  | 1 | [7 empty] | 4 |  |  | 3
Z | 78 | 139 | CI |  | Release Management | PMO | CCB Approved | Post-Baseline2 | 2007-09-12 | [9 empty] | 4 |  |  | 3
K | 104 | WPIDA031 | WPIDA | NPRR067 | Private Use Network | MMS | Drafted | Post-Baseline2 | TBD | 1 | 1 | 4 | 4 | 1 | 3 | 4 | 4 | 4 | 3 | 4 | 4 | 3 | 4 | 3
Z | 124 | WPIDA037 | WPIDA |  | DC tie processes | MMS, COMS, EIP, EMS (NI), NMMS | Resolved / Closed | Post-Baseline2 | 2007-09-12 | 2 | 2 | 4 | 3 | 2 | 1 | 4 | 4 | 3 | 3 | 4 | 4 | 3 | 4
Z | 103 | WPIDA046 | WPIDA | NPRR035 | Net Metering | NMMS, MMS, EMS, COMS, INT, EIP | Resolved / Closed | Post-Baseline2 | 2007-09-12 | 4 | 4 | 4 | 4 | 1 | 1 | 4 | 4 | 1 | 3 | 4 | 4 | 3 | 4
Z | 100 | WPIDA057 | WPIDA |  | Outage Scheduler interface to NMMS | OS, EIP, NMMS, INT, CRR | CCB Approved | Post-Baseline2 | 2007-12-19 | 4 | 4 | 2 | 3 | 2 | 4 | 2 | 4 | 1 | 3 | 4 | 4 | 3 | 4
Z | 125 | WPIDA059 | WPIDA |  | Settlement During Emergency Condition | No Impact | Resolved / Closed | Post-Baseline2 | 2007-09-12 | 4 | 4 | 4 | 4 | 4 | 2 | 4 | 4 | 4 | 3 | 4 | 4 | 3 | 4
Z | 101 | WPIDA064 | WPIDA |  | Data Requirements for Controllable Load Resources | NMMS, COMS, EMS, MMS | CCB Approved | Post-Baseline2 | 2008-01-09 | 4 | 4 | 4 | 4 | 4 | 1 | 4 | 4 | 4 | 3 | 4 | 4 | 3 | 4
Z | 110 | 142 | CI |  | Automated inclusion of PMCRs in augmented file (NMMS-CRR) | NMMS, COMS, CRR | CCB Approved | Post-Baseline2 | 2007-10-24 | [12 empty] | 3
Z | 79 | 144 | CI |  | CRR compliance with current Program design standards for UI, INT and EA. | CRR | CCB Approved | Post-Baseline2 | 2007-11-07 | [9 empty] | 4 |  |  | 3
Z | 112 | 145 | CI |  | Outage Scheduler Essential Changes | OS | 12/12/2007 Cost Incr 11/14/2007 Info Only | Post-Baseline2 | 11/14/2007 Info only | [12 empty] | 3
F | 97 | 232 | CI |  | Mimic User Requirement | MPIM, MIS, EIP, MMS | CCB Approved | Post-Baseline2 | 2008-06-04 | 4 | 1 | 4 | 4 | 4 |  | 4 | 4 | 1 |  |  |  | 3 | 2 |  | 4 | 1
Z | 102 | WPIDA065 | WPIDA |  | CRR and DAM Solution Similarity | EIP, NMMS, COMS, INT, EDS | Resolved / Closed | Post-Baseline2 | 2007-09-12 | 4 | 4 | 4 | 4 | 1 | 2 | 4 | 4 | 1 | 4 | 4 | 2 | 3 | 4
H | 126 | WPIDA301 | WPIDA |  | Creation and Deletion of Settlement Points | COMS, MMS, NMMS, CRR, EIP, INT | Resolved / Closed | Post-Baseline2 | [13 empty] | 3
A |  | 18 |  | No Impact approved NPRRs |  |  |  | 126
B |  | 6 |  | NPRRs with impact in progress
E |  | 2 |  | No impact NOGRRs
F |  | 1 |  | 1 impact Change Item
G |  | 0 |  | No Impact Change Items
H |  | 1 |  | No Impact White Papers
I |  | 25 |  | Pending NPRRs
J |  | 2 |  | Pending NOGRRs
K |  | 2 |  | Pending White Papers
L |  | 0 |  | Pending Change Items
M |  | 17 |  | Deferred Items
Y |  | 17 |  | NPRRs approved PB2 in revised budget
Z |  | 35 |  | Other items approved PB2 in revised budget
Total |  | 126
Note on C9: shensley: Item # assigned out of order as cleanup effort
Note on C15: shensley: Item # assigned out of order as part of cleanup