## SIG Tracking
Item # | Paper # | Problem Title | Version and date on paper | Comments
1 | 0005 | Load Resource Topology Modeling (Controllable Loads) | V2 6/11/08 | Implementation schedule removed 6/11
2 | 0006 | Flowgate Modeling (MCFRI - MMS Needs Flowgate Definitions from NMMS (Thermal and Non-Thermal) - Settlements expects shadow prices produced for FGRs and that FGRs be capable of deration.) | V2 6/11/08 | On 5-30-08, "TPTFreview" requested comments from Market Participants on version "0 11". Comments due 6-6-08. No comments received. Implementation schedule removed 6/11
3 | 0008 | Non-Modeled Generation | V2 6/11/08 | Implementation schedule removed 6/11
4 | 0009 | Resource Node Location | V2 6/11/08 | Design Solution updated 6/6 Implementation schedule removed 6/11
5 | 0002 | Private Use Networks | V24 7/21/08 | On 5-30-08, "TPTFreview" requested comments from Market Participants on version "0 21". Comments due 6-6-08. Comments recieved from Luminant. Some changes made. Implementation schedule removed 6/11 On 7-9-08 "TPTFreview" requested comments from Market Participants on version "0 23". Comments due 7-15-08. Comments recieved from Luminant, Reliant and Centerpoint. Version "0 24" sent back out for review on 7-21-08. Version "0 24" document scheduled to be presented to TPTF on 7-22-09
6 | 0003 | Combined Cycle | V4 6/11/08 | On 5-30-08, "TPTFreview" requested comments from Market Participants on version "0 31". Comments due 6-6-08. Implementation schedule removed 6/11
7 | 0004 | Digital Certificates for Counter Parties | V3 6/11/08 | Implementation schedule removed 6/11
8 | 0007 | Block Load Transfer | V4 6/11/08 | Implementation schedule removed 6/11
9 | 0011 | Net Generation (Use of Net MW) | V3 6/11/08 | Tied to PUN and Self Committed. Implementation schedule removed 6/11
10 | 0020 | Rounding of MW Values | V3 6/11/08 | Implementation schedule removed 6/11
11 | 0022 | Transmission Constraint Model for RT CCP Dispatch | V2 6/11/08 | Implementation activities updated 6/6 Implementation schedule removed 6/11