PMO

Working Readiness Metric Inventory

v0.09

July 10, 2008

TABLE OF CONTENTS

Revision History	3

Market Participant Metrics	6

Market Participant Metrics	6

MP1 - MP Engagement	6

MP2 – QSE with Resources Connectivity to EDS Environment	7

MP3 – QSE with Resources Upload of SCED Offers to EDS	8

MP5 – ICCP Point to Point Telemetry Test	9

MP6 - QSE and TSP Telemetry/ICCP System Availability	10

MP8 - QSE Ability to Submit Transactions Via MIS	11

MP9 – QSE Ability to Submit Web Service Transactions	12

MP10 - Mapping of Resources to Resource Nodes and Resources to EPS Meters is Complete	13

MP11 - MP Registration Activities	15

MP12 - MP Completes Nodal Market Related Training	17

MP13 - MP Completes  Nodal Operations Related Training	19

MP14 – A - MP EDS-2, Release 3 Trials Participation	21

MP14 – B - MP EDS-2, Release 4 Trials Participation	23

MP14 – C - MP EDS-2, TSP Model Synchronization Participation	24

MP15 – A - MP EDS-3, Releases 5 and 6 Participation	26

MP15 – B - MP EDS-3, Release 7 Trials Participation	27

MP16 - MP EDS-4 Trials Participation  – TO BE REVISED AT A LATER DATE	28

MP17 - MP Qualification Activities	29

MP18 - Mapping of Resources and Loads in Private Area Networks is Complete	30

MP19 – Load Serving Entitles Engagement and Readiness	30

MP20 - MP Ability to Submit Outage – Connectivity Test	31

MP21 – Wind Generating Resources ICCP Telemetry	32

MP22 – New Entrant Readiness	34

MP23 – Outage Trials Participation	35

# Revision History

| Date | Author | Version Number | Description of Revision |
| --- | --- | --- | --- |
| 11/30/07 | Chris Wilkinson | 0.01 | Initial version. MP11 and MP19 for TPTF review on 12/4/07 |
| 12/05/07 | Chris Wilkinson | 0.02 | Results of 12/3/07 TPTF meeting. Moved MP11 redlined to Active inventory pending TAC approval |
| 12/05/07 | Chris Wilkinson | .03 | Copied remaining metrics from Future inventory and updated with Reliant and Luminant comments in preparation for 12/19/07 meeting |
| 12/20/07 | Chris Wilkinson | .04 | Moved metrics approved by TPTF to Active inventory for TAC approval: MP19 - Load Serving Entities Engagement and Readiness MP16 - MP EDS-4 Trials Participation MP18 - Mapping of Resources and Loads in Private Area Networks is Complete CO1 - Settle Market for 7 Days and Provide Appropriate Extracts CO2 - Verify Dispute Process of 168 Hour Test CO3 - Verify DAM Settlement Statements CO4 - Zonal/Nodal Coordinated Settlement Operations CO5 - Verify RTM Settlement Statements CO6 - Verify RTM Settlement Invoices CO7 - Verify DAM Invoices CO8 - Verify CRR Auction Invoices CO9 - Verify Financial Transfer and Processing CO10 - Verify Credit Calculations EMO12 - Network Operations Model and SE Performance EMO13 - ERCOT Operating Personnel and Facilities Readiness MO7 - ERCOT Operating Personnel and Facilities Readiness |
| 1/11/2008 | Chris Wilkinson | .05 | Moved the following metrics to the Active document. These were endorsed by TPTF on 1/8/08. ERCOT Internal Metrics E2 - Verify ERCOT Performance Monitoring Test Plan E4 - Transition Pricing Mechanisms E7 - Validate EDW Access and Accuracy of Postings Required by the IMM and PUCT Rules E10 - Validate EDW Commercial Systems Access Accuracy E11 - Validate EDW Compliance Data Access E14 - Verify QSE Performance Monitoring Test Plan E15 - Verify TSP Performance Monitoring Test Plan Energy Management Operations Metrics EMO3 - Verify Outage Evaluation System Functionality EMO8 - Conduct EECP Test Market Operations Metrics MO3 - Verify Supplemental Ancillary Services Market (SASM) Contingency Metrics C1 - Contingency Plan Procedures for Weekly, Daily and Hourly RUC Failure C2 - Contingency Plan Procedures for DAM Failure C3 - Contingency Plan Procedures for ICCP Data Failure C4 - Contingency Plan Procedures for SCED Failure C5 - Contingency Plan Procedures for Key Settlement and Financial Transfer Processes C6 - Develop Plan for SE Failure C7 - Contingency Plan Procedures for a Backup Facility C8 - Contingency Plan Procedures for Portal/API Failure C9 - Contingency Plan Procedures for Site Unavailability C10 - Verify Single Point of Failure Recovery EMS/MMS/NMMS/CRR/COMS IMM Metrics IMM1 - Market Monitor Systems Capability Overall Readiness Metrics R0 - Market Participants Operations Readiness R1 - Nodal Readiness Declaration R2 - Develop Texas Nodal Market Launch Plan |
| 2/20/08 | Chris Wilkinson | .06 | Updates to MP10 with comments received form ERCOT. |
| 2/28/08 | Chris Wilkinson | .07 | Updated MP10 and C02 in the active metric inventory based on TPTF feedback received 2/21/08. These were moved out of the working document. Updated CO1 to remove references to the 168 hour test. |
| 4/4/08 | Chris wilkinson | .08 | CO1 and E5 moved to the Active Metric Inventory V5.1 for TAC approval Redlined E8 to reflect clarified RAG Rules Redlined EMO5 to reflect change in criteria Added new Outage Scheduler metric (MP20) |
| 7/10/2008 | Jerry Sullivan SallyRose Anderson | 0.09 | Propose revising Market Participant Metrics as follows: - MP1 - propose removing majority of specifics that are no longer relevant (targets from the first rounds of surveys), propse adding MP and Segment RAG rules - MP2 - propose closing this metric, adding MP22 - MP3 - propose closing this metric, adding MP22 - MP5 - propose closing this metric, adding MP22 - MP6 - propose removing the multiple target completions and tying the metric more directly to both the Nodal Protocols (3.10.9) and the TAC approved completion criteria - MP8 - propose closing this metric, adding MP22 - MP9 - propose closing this metric, adding MP22 - MP10 - propose removing the multiple target completion goals and implementing a MP Segment RAG rule - MP11 - propose removing the multiple target completion goals, specifying what is entailed in the “required resource registration activities”, and making the RAG rule for MPs more objective - MP12 and MP13 -propose changing reporting source and realigning focus of the metrics - MP14 (A and B) - propose splitting the metric to cover SE trials participation and NOMCR trials participation separately (A and B) - MP14 (C) - new EDS 2 trials metric to address TSP Model Synchronization - MP15 (A and B) - propose splitting the metric to cover SCED/LFC trials and CRR trials separately (A and B) - MP16 - propose freezing this metric, modifying later - MP17 - propose clarifying the MP RAG rule to make it more objective and adding a Segment RAG rule - MP18 - propose freezing this metric, modifying later MP19 - propose modifying/adding MP RAG rules and modifying Segment RAG rule - MP20 - propose closing this metric, adding MP23 - MP21 - new metric propsed at TPTF on Monday (7/7/08) - MP22 - new metric that will measure the activity of new entrants to the market and existing entities with new resources, need to add MP5 links - MP23 - new metric that will follow MP20 and address Outage Trials Participation |

# Market Participant Metrics

MP1—ERCOT proposes removing majority of specifics in MP1 that are no longer relevant (targets from the first rounds of surveys) and adding MP and Segment RAG rules Reliant suggests we make no changes to this metric and just call it completed and move it to the Completed stack.  Readiness is somewhat measurable by showing that all metrics are completed and this metric should be coded green and done.

### MP1 - MP Engagement

| Reported By: QSER, QSE, TDSP |  |  |  |
| --- | --- | --- | --- |
| Target Completion: Periodic: June 1, TBD, TBD |  |  |  |
| Category: Engagement |  |  |  |
| Metric Description: MP are actively participating in Nodal preparation and have indicated an intent to participate in the Nodal Market. |  |  |  |
| Background: The intent of this metric is to ensure that Market Participants are engaged in Nodal preparations. |  |  |  |
| Criteria: The Readiness Team will review self reporting from each Market Participant indicating their level of engagement in Nodal preparation, mobilization and delivery. For Market Participants Completed Survey with All Positive Responses = Green Completed Survey with One or More Negative Response = Amber Did Not Complete Survey = Red For Market Segment Over 95% of Market Share Responded Positively to the Survey = Green Over 5% of Market Share Did Not Respond to the Survey = Red Any Alternative Scenario = Amber |  |  |  |
| Reporting Data Sources: MP Self Reported from Survey |  |  |  |
| References | TP: N/A | TNP: N/A |  |

MP2—ERCOT proposes closing MP2 and adding MP22. Formal testing is no longer happening on a large scale. Rather than having several metrics active that will change with the addition of a new resource, thus posing difficulties in reporting status objectively, we propose closing this (and metrics that impact only new entries to the market). We propose the creation of a new metric that will measure the compliance of new entities and existing entities with new resources to the required entry tests (MP2, MP3, MP5, MP8, MP9). Reliant suggests we make no changes to this metric and just call it completed and move it to the Completed stack.  Readiness is somewhat measurable by showing that all metrics are completed and this metric should be coded green and done.

### MP2 – QSE with Resources Connectivity to EDS Environment

| Reported By: QSER |  |  | EDS: 3 |
| --- | --- | --- | --- |
| Target Completion: Completed and Closed – now covered under MPx (New Entrant Metric) |  |  |  |
| Category: Connectivity |  |  |  |
| Metric Description: QSEs with resources have confirmed their ability to connect to the MIS and/or an External Web Service in the early Early Delivery System (EDS) environments. |  |  |  |
| Background: The intent of this metric is to ensure that QSEs with Resources can successfully connect to the eEDS allowing ERCOT to provide better support to the MPs facilitating trials completion. |  |  |  |
| Criteria: The Readiness Team will review documentation providing connectivity statistics for the EDS3 environment by Market Participant. Readiness will be met when the MP successfully submits a three part offer, incremental/decremental offer, current operating plan or a output schedule via either web services or the MIS that is logged in the Enterprise Integration Framework (EIF) transaction database as successfully passing the proxy server. EIF entry per QSE with resources >=1 RAG Rules Red – Failure to meet 10/2/07 execution deadline Amber – Failure to sign-up by 8/15/07 Green – Meeting Plan |  |  |  |
| Reporting Data Sources: EIF log table entry in EDS / ERCOT EDS 3 PM EDS 3 team will track registration and execution by QSE with Resources |  |  |  |
| References | TP: N/A | TNP: N/A |  |

MP3—ERCOT proposes closing MP3 and adding MP22. Formal testing is no longer happening on a large scale. Rather than having several metrics active that will change with the addition of a new resource, thus posing difficulties in reporting status objectively, we propose closing this (and metrics that impact only new entries to the market). We propose the creation of a new metric that will measure the compliance of new entities and existing entities with new resources to the required entry tests (MP2, MP3, MP5, MP8, MP9). Reliant suggests we make no changes to this metric and just call it completed and move it to the Completed stack.  Readiness is somewhat measurable by showing that all metrics are completed and this metric should be coded green and done.

### MP3 – QSE with Resources Upload of SCED Offers to EDS

| Reported By: QSER |  |  | EDS: 3 |
| --- | --- | --- | --- |
| Target Completion: Completed and Closed – now covered under MPx (New Entrant Metric) |  |  |  |
| Category: Connectivity |  |  |  |
| Metric Description: QSEs with Resources shall demonstrate their ability to successfully submit a 3 part offer and if applicable a dynamic output schedule to the MIS and/or an External Web Service in the Early Delivery System (EDS) environment and successfully pass validation with the MMS system. |  |  |  |
| Background: The intent of this metric is to ensure that QSEs with Resources can successfully submit a 3 part offer and if applicable a dynamic output schedule to the EDS. |  |  |  |
| Criteria: The Readiness Team will review documentation providing transaction statistics by Market Participant. Readiness will be met when the MP successfully submits a request that is logged in the Enterprise Integration Framework (EIF) transaction database. EIF entry with transaction status of Passed per QSE with resources >=1 RAG Rules Red – Failure to meet 10/2/07 execution deadline Amber – Failure to sign-up by 8/15/07 Green – Meeting Plan |  |  |  |
| Reporting Data Sources: EIF log table entry in EDS as verified by the ERCOT EDS Test Team / ERCOT EDS 3 PM EDS 3 team will track SCED offers by QSE with Resources. |  |  |  |
| References | TP: N/A | TNP: N/A |  |

MP5—ERCOT proposes closing MP5 and adding MP22. Formal testing is no longer happening on a large scale. Rather than having several metrics active that will change with the addition of a new resource, thus posing difficulties in reporting status objectively, we propose closing this (and metrics that impact only new entries to the market). We propose the creation of a new metric that will measure the compliance of new entities and existing entities with new resources to the required entry tests (MP2, MP3, MP5, MP8, MP9). At the last TPTF meeting, there seems like several entities who are still not providing ERCOT with correct data.  Has this really been completed? Should we not keep this until we are satisfied that SE is working correctly with the point to points we have.  Otherwise let just call this metric complete.

### MP5 – ICCP Point to Point Telemetry Test

| Reported By: QSER, TDSP |  |  | EDS: 2 |
| --- | --- | --- | --- |
| Target Completion: Completed and Closed – now covered under MPx (New Entrant Metric) |  |  |  |
| Category: Telemetry |  |  |  |
| Metric Description: ERCOT shall coordinate a test with TSPs and QSEs with resources to verify that the equipment point mapping, value, and status are correctly transmitted within an acceptable scan rate. |  |  |  |
| Background: The intent of this metric is to ensure that TSP, QSE and ERCOT telemetry ICCP representations are in synch with one another. |  |  |  |
| Criteria: The Readiness Team will review documentation that verifies the accuracy of telemetry points mapping, station topology diagrams, values and status within an acceptable scan rate. Readiness will be achieved when MPs have added all required points to meet Nodal Protocols, Point to Point Verification has occurred, Telemetry issues documented and communicated to MPs, ERCOT has ICCP database under change control and MPs have submitted service requests to resolve ICCP issues. Number of points missing from Nodal Protocol Requirement <= 5% Number of Point to Point Verification = 95% of Points within a 10 second scan rate Number of Telemetry issues identified = Number of Telemetry issues documented and communicated to MPs. Number of MP service request submitted >= 90% of Number of Telemetry issues documented and communicated to MPs RAG Rules Red – Failure to meet above criteria Amber – Behind point to point schedule Green – Meeting above criteria |  |  |  |
| Reporting Data Sources: ICCP Database / Network Operations Model & the EDS 1 status report located on the Nodal Readiness Center: EDS 1 Status MMDDYYYY.xls / ERCOT EDS 2 PM |  |  |  |
| References | TP: 5.4.1 (2)(a) | TNP: 3.10.7, 6.5.7.6.1(8) & 8.1.2.2(6)(b) |  |

MP6—ERCOT proposes removing the multiple target completions in MP6 and tying the metric more directly to both the Nodal Protocols (3.10.9) and the TAC approved completion criteria So far this has been more of a problem on the ERCOT side yet we are removing ERCOT from the metric.  How are we addressing this?

### MP6 - QSE and TSP Telemetry/ICCP System Availability

| Reported By: QSER, TDSP |  |  |  |
| --- | --- | --- | --- |
| Target Completion: 168-Hour Test Minus 180 Days [we continue to face many problems getting the SE to work propperly. Waiting this long to ;complete is too much slack.] |  |  |  |
| Metric Description: Verify that MP telemetry systems are compliant with Nodal Protocols section 3.10.9. |  |  |  |
| Category: Telemetry |  |  |  |
| Background: The intent of this metric is to ensure that MP telemetry systems are stable in a redundant state and meet TAC approved telemetry data standards. |  |  |  |
| Criteria: Meeting TAC approved criteria. For Market Participants Red – Failure to meet above criteria Amber – is not applicable Green – Meeting above criteria For Market Segment Red – Over 5% of Market Share Failing to Meet Criteria Amber – is not applicable Green – Over 95% of Market Share Meeting Criteria |  |  |  |
| Reporting Data Sources: EDW Reports/Extracts Which report/extract would house the telemetry and ICCP system availability? |  |  |  |
| References | TP: 5.4.1 (2)(k), 5.4.1 (2)(a) | TNP: 3.10.9 |  |

MP8—ERCOT proposes closing MP8 and adding MP22. Formal testing is not longer happening on a large scale.  Rather than having several metrics active that will change with the addition of a new resource, thus posing difficulties in reporting status objectively, we propose closing this (and metrics that impact only new entries to the market).  We propose the creation of a new metric that will measure the compliance of new entities and existing entities with new resources to the required entry tests (MP2, MP3, MP5, MP8, MP9). Reliant suggests we make no changes to this metric and just call it completed and move it to the Completed stack.  Readiness is somewhat measurable by showing that all metrics are completed and this metric should be coded green and done.

### MP8 - QSE Ability to Submit Transactions Via MIS

| Reported By: QSER, QSE |  |  | EDS: 3,4 |
| --- | --- | --- | --- |
| Target Completion: EDS-4 Release 3 |  |  |  |
| Metric Description: Completed and Closed – now covered under MPx (New Entrant Metric) |  |  |  |
| Background: The intent of this metric is to ensure that QSEs have the ability to participate in the real time market DA Operations and Adjustment Period Operations. |  |  |  |
| Criteria: The Readiness Team will review documentation that verifies that market participants can and have successfully sent test real time transactions. Readiness will be met when ERCOT has observed Market Participants successfully sending test real time transactions during the EDS Market Particpant test window. QSEs will be asked to submit transactions via the MIS or External Web Services according to the MMS Explanation of Market Participant Submission Items. MP Transactions Sent = MP Transactions Received at ERCOT during the Market Participant test window MP RAG Rules Green = Complete Amber = Not complete, less than 1 month past due date Red = Not complete, over a month past due |  |  |  |
| Reporting Data Sources: MMS Data Extract / ERCOT EDS 3 & 4 PM |  |  |  |
| References | TP: 5.4.4 & 5.4.7 | TNP: 3.9, 4.3(1), 5.4, 6.4.6 |  |

MP9—ERCOT proposes closing MP9 and adding MP22. Formal testing is not longer happening on a large scale.  Rather than having several metrics active that will change with the addition of a new resource, thus posing difficulties in reporting status objectively, we propose closing this (and metrics that impact only new entries to the market).  We propose the creation of a new metric that will measure the compliance of new entities and existing entities with new resources to the required entry tests (MP2, MP3, MP5, MP8, MP9). Reliant suggests we make no changes to this metric and just call it completed and move it to the Completed stack.  Readiness is somewhat measurable by showing that all metrics are completed and this metric should be coded green and done.

### MP9 – QSE Ability to Submit Web Service Transactions

| Reported By: QSER |  |  | EDS: 4 |
| --- | --- | --- | --- |
| Target Completion: Completed and Closed – now covered under MPx (New Entrant Metric) |  |  |  |
| Metric Description: ERCOT shall verify the ability of QSEs to submit transactions via the Web Services. |  |  |  |
| Background: The intent of this metric is to ensure that QSEs have the ability to participate in the Market. |  |  |  |
| Criteria: The Readiness Team will review documentation that verifies that the market participants can and have successfully sent test Transactions. Readiness will be met when ERCOT has observed Market Participants successfully sending test transactions during the EDS Market Participant test window. MP Transactions Sent = MP Transactions Received at ERCOT during the Market Participant test Window MP RAG Rules Green – Complete Amber – Not Complete, less than 1 month past due date Red – Not complete, over month past due |  |  |  |
| Reporting Data Sources: MMS Data Extract / ERCOT EDS 4 PM |  |  |  |
| References | TP: 5.4.6 (1) | TNP: 4.3, 4.4, 4.5 |  |

MP10—ERCOT proposes removing the multiple target completion goals in MP10 and implementing a MP Segment RAG rule

### MP10 - Mapping of Resources to Resource Nodes and Resources to EPS Meters is Complete

| Reported By: QSER |  |  |  |
| --- | --- | --- | --- |
| Target Completion: Network Model One-Line (NMO) + 30 Days, Following Single Entry Model Go-Live |  |  |  |
| Metric Description: ERCOT shall ensure that all participating Generation Resources in the TN Market have completed their mapping of Resources to Resource Nodes and Resources to EPS Meters at the Generation Facility and validate the accuracy of breaker and switch configurations on the Nodal Model. What is the TN Market referenced above? |  |  |  |
| Background: It is the intent of this metric to ensure that the settlement of resources involved in a net metering configuration can be executed as specified by the Nodal Protocols. |  |  |  |
| Criteria: The Readiness Team will review documentation that verifies that all participating resources in the TN Market have completed their mapping of Resources to Resource Nodes and Resources to EPS Meters. Readiness will be achieved when each resource has either mapped their Resources or have accepted the existing default configuration. MP RAG Rules Green = Complete Amber = Not complete, but working on network model issues, past target completion date Red = Not complete, not working on network model issues, past target completion date this measurement is to vague and impossible to measure. What is not working on it? Needs objectivity. Criteria: The Readiness Team will review documentation that verifies that all participating resources in the TN Market have completed their mapping of Resources to Resource Nodes and Resources to EPS Meters. Readiness will be achieved when each resource has either mapped their Resources or have accepted the existing default configuration. MP RAG Rules Green = Complete Amber = Not complete, but working on network model issues, past target completion date Red = Not complete, not working on network model issues, past target completion date this measurement is to vague and impossible to measure. What is not working on it? Needs objectivity. Criteria: The Readiness Team will review documentation that verifies that all participating resources in the TN Market have completed their mapping of Resources to Resource Nodes and Resources to EPS Meters. Readiness will be achieved when each resource has either mapped their Resources or have accepted the existing default configuration. What is the TN Market referenced above? Criteria: The Readiness Team will review documentation that verifies that all participating resources in the TN Market have completed their mapping of Resources to Resource Nodes and Resources to EPS Meters. Readiness will be achieved when each resource has either mapped their Resources or have accepted the existing default configuration. MP RAG Rules Green = Complete Amber = Not complete, but working on network model issues, past target completion date Red = Not complete, not working on network model issues, past target completion date For Market Segment Over 95% of Market Share Meeting Criteria = Green Over 5% of Market Share Failing to Meet Criteria, Post Completion Date = Red Any Alternative Scenario = Amber |  |  |  |
| Reporting Data Sources: Wholesale Client Services |  |  |  |
| References | TP: N/A | TNP: 16.2.3.2(2) |  |

MP11—ERCOT proposes removing the multiple target completion goals in MP11, as well as specifying what is entailed in the "required resource registration activities" and making the RAG rule for MPs more objective

### MP11 - MP Registration Activities

| Reported By: QSER |  |  |  |
| --- | --- | --- | --- |
| Target Completion: 168-Hour Test Minus 120 Days |  |  |  |
| Category: Registration and Qualification |  |  |  |
| Metric Description: This metric shall measure whether Market Participants have completed the resource registration activities required for the Nodal program. |  |  |  |
| Background: The intent of this metric is that ERCOT has all registration related data for all market participants intending to participate in the Nodal Market on record. |  |  |  |
| Criteria: MP Readiness will be achieved when the MP has completed the required resource registration activities including: Acceptance of RARF Acceptance of Station Network Topology Registration Non-Modeled Generation Declaration Resource Decision Making Authority Attestation RAG Rules – MPs QSERs will be scored based on status of resource registration for all resources represented Red – Failure to meet criteria, not responding after the target completion date Amber – working on document revisions, after target completion date Green – All forms received and accepted RAG Rules – Market Segment Red – over 5% of market share not meeting criteria Amber – any alternative scenario Green – over 95% of market share meeting criteria |  |  |  |
| Reporting Data Sources: Wholesale Client Services |  |  |  |
| References | TP: N/A | TNP: 16.2 thru 16.8 & 3.7.1 |  |

MP12—ERCOT proposes changing the reporting source for MP12 and realigning the focus of the metric.

ERCOT is proposing two primary changes for metrics MP12 and MP13.

The first change addresses the reporting source for the metrics. For the past months MP12 and MP13 have been evaluated based on the results of self-reported surveys. The metrics were never modified to reflect this.  We propose changing the metric to state that status is determined based on self-reported survey data.  Following this thought process, we propose adding MP and Segment RAG rules that are consistent with MP1 (the other self-reported metric).  

The second change addresses the focus of the metrics. Currently MP12 focuses on EDS 3 Training and MP13 focuses on EDS 4 Training. We propose differentiating the MP training efforts from the EDS schedule slightly, and re-focusing the metrics. We suggest having MP12 focus on Nodal Market Related Training and MP13 focus on Nodal Operations Related Training.  To accomplish this we combined the two metrics and reallocated the recommended courses. We did not remove any courses from the recommended list, just transferred some from MP12 to MP13, and visa versa.

### MP12 - MP Completes Nodal Market Related Training

| Reported By: QSER, QSE, TDSP |  |  |  |
| --- | --- | --- | --- |
| Target Completion: Cyclical through 168-Hour Test |  |  |  |
| Category: Training |  |  |  |
| Metric Description: Market Participants complete the applicable training modules associated with nodal market related readiness |  |  |  |
| Background: The intent of this metric is to ensure that Market Participants participating in Nodal have adequate knowledge of the Nodal Market to participate . |  |  |  |
| Criteria: The Readiness Team will review self-reporting from each Market Participant indicating their level of training necessary to assure the Market Participant’s ability to successfully particpate in the Nodal Market meets the scope of activities described in the ERCOT developed Training Materials included in the following courses: self-reporting from each Market Participant indicating their level of training for the Nodal Market. Ideally, training will focus on the following courses: - ERCOT Nodal 101 (The Basics) - Load Serving Entity 201 - Generation 101, 201, 301 - Market Settlements - CRRs, PCRRs, and Supply Hedging - Market Information Systems For Market Participants Completed Survey with All Positive Responses = Green Completed Survey with One or More Negative Response = Amber Did Not Complete Survey = Red For Market Segment Over 95% of Market Share Responded Positively to the Survey = Green Over 5% of Market Share Did Not Respond to the Survey = Red Any Alternative Scenario = Amber \ |  |  |  |
| Reporting Data Sources: Self-Reported Survey |  |  |  |
| References | TP: | TNP: N/A |  |

MP13—ERCOT proposes changing the reporting source for MP13 and realigning the focus of the metric.

ERCOT is proposing two primary changes for metrics MP12 and MP13.

The first change addresses the reporting source for the metrics. For the past months MP12 and MP13 have been evaluated based on the results of self-reported surveys. The metrics were never modified to reflect this.  We propose changing the metric to state that status is determined based on self-reported survey data.  Following this thought process, we propose adding MP and Segment RAG rules that are consistent with MP1 (the other self-reported metric).  

The second change addresses the focus of the metrics. Currently MP12 focuses on EDS 3 Training and MP13 focuses on EDS 4 Training. We propose differentiating the MP training efforts from the EDS schedule slightly, and re-focusing the metrics. We suggest having MP12 focus on Nodal Market Related Training and MP13 focus on Nodal Operations Related Training.  To accomplish this we combined the two metrics and reallocated the recommended courses. We did not remove any courses from the recommended list, just transferred some from MP12 to MP13, and visa versa.

### MP13 - MP Completes  Nodal Operations Related Training

| Reported By: QSER, QSE, TDSP |  |  |  |
| --- | --- | --- | --- |
| Target Completion: Cyclical through 168-Hour Test |  |  |  |
| Metric Description: Market Participants complete the applicable training modules associated with nodal operations related readiness |  |  |  |
| Background: The intent of this metric is to ensure that Market Participants participating in Nodal have adequate knowledge of the Nodal Operations to participate |  |  |  |
| Criteria: The Readiness Team will review self-reporting from each Market Participant indicating their level of training necessary to assure the Market Participant’s ability to successfully operate in the Nodal Market meets the scope of activities described in the ERCOT developed Training Materials included in the following courses: Criteria: The Readiness Team will review self-reporting from each Market Participant indicating their level of training for Nodal Operations. Ideally, training will focus on the following courses: Basic Training Program Non-Opt In Entity NOIE (QSE) Operations Is the Gen 201 and Gen 301 course material covered within the Basic Training Program course? If not, suggestion to add these two courses within MP13. self-reporting from each Market Participant indicating their level of training for Nodal Operations. Ideally, training will focus on Basic Training Program Non-Opt In Entity NOIE (QSE) Operations Transmission 101; Network Model Management; ERCOT 101 for Wind Generation. For Market Participants Completed Survey with All Positive Responses = Green Completed Survey with One or More Negative Response = Amber Did Not Complete Survey = Red For Market Segment Over 95% of Market Share Responded Positively to the Survey = Green Over 5% of Market Share Did Not Respond to the Survey = Red Any Alternative Scenario = Amber |  |  |  |
| Reporting Data Sources: Self-Reported Survey |  |  |  |
| References | TP: | TNP: N/A |  |

MP14 – A—ERCOT proposes splitting metric MP14 into MP14 – A and MP14 – B to cover SE trials participation and NOMCR trials participation separately and adding MP14 – C to address TSP Model Synchronization.

Within MP14 – A we propose tying the metric more closely to the TAC telemetry criteria and modifying the MP RAG rules to reflect the removal of NOMCR related activities from this metric.

While ERCOT recognizes the importance of MP14, we found it difficult to report it in a transparent manner. MP14 covers both State Estimator (EDS 2, Release 3) and NOMCR (EDS 2, Release 4). Reporting an entity “red” for MP14 would not indicate whether the entity was “red” for SE Participation and “green” for NOMCR, or visa versa. To accurately and transparently report on both of these trials, we needed to split the metric. MP14 – A now addresses SE Trials Participation while MP14 – B now addresses NOMCR Trials Participation.

### MP14 – A - MP EDS-2, Release 3 Trials Participation

| Reported By: QSER, TDSP |  |  |  |
| --- | --- | --- | --- |
| Target Completion: Go-Live?????????? Need to be done sooner in order to measure readiness? |  |  |  |
| Category: Trials Participation |  |  |  |
| Metric Description: This metric evaluates the level of TSP and QSE market participant participation in the EDS 2, Release 3 Trials. General comment: Consistency between TDSP and TSP within the document. |  |  |  |
| Background: The intent of this metric is to ensure that Market Participants have the ability to access telemetry and State Estimator performance reports. |  |  |  |
| Criteria: The Readiness Team will review documentation that an adequate number of MPs by market segment representing an adequate percent of overall generation have reviewed performance reports on MIS and confirmed ability to access those reports , as based on TAC telemetry criteria. % of Generation Participation AND % Resource Entities Participation # of TSP and QSER MPs Participating in Trial accessing Telemetry SE Performance Report >= 75% RAG Rules - MPs Red - Not participating in trials Amber – not applicable Green – Meeting criteria RAG Rules – Market Segment Red – Not meeting criteria Amber – within 10 percent of criteria Green – meeting criteria |  |  |  |
| Reporting Data Sources: EDS 2 PM |  |  |  |
| References | TP: 5.4.1 | TNP: 3.10.8, 3.3.2.1, 3.10.7 |  |

MP14 – B— ERCOT proposes splitting metric MP14 into MP14 – A and MP14 – B to cover SE trials participation and NOMCR trials participation separately and adding MP14 – C to address TSP Model Synchronization.

Within MP14 – B we propose tying the metric more closely to the TAC criteria and modifying the MP RAG rules to reflect the focus on NOMCR related activities for this metric.

While ERCOT recognizes the importance of MP14, we found it difficult to report it in a transparent manner. MP14 covers both State Estimator (EDS 2, Release 3) and NOMCR (EDS 2, Release 4). Reporting an entity “red” for MP14 would not indicate whether the entity was “red” for SE Participation and “green” for NOMCR, or visa versa. To accurately and transparently report on both of these trials, we needed to split the metric. MP14 – A now addresses SE Trials Participation while MP14 – B now addresses NOMCR Trials Participation.

MP14 – B - MP EDS-2, Release 4 Trials Participation

| Reported By: TDSP |  |  |  |
| --- | --- | --- | --- |
| Target Completion: Point In Time??????????? |  |  |  |
| Category: Trials Participation |  |  |  |
| Metric Description: This metric evaluates the level of TDSP market participant participation in the EDS 2, Release 4 Trials. |  |  |  |
| Background: The intent of this metric is to ensure that Market Participants are actively participating in the NOMCR process. |  |  |  |
| Criteria: The Readiness Team will review documentation that an adequate number of MPs by market segment representing an adequate percent of overall generation have submitted modifications through the NOMCR process. % of Generation Participation AND % Resource Entities Participation # of TDSP MPs Participating in Trial participating in the NOMCR process >= 95% RAG Rules - MPs Red - Not participating in trials Amber – Not Applicable Green – Meeting criteria RAG Rules – Market Segment Red – Not meeting criteria Amber – within 10 percent of criteria Green – meeting criteria |  |  |  |
| Reporting Data Sources: EDS 2 PM |  |  |  |
| References | TP: 5.4.1 | TNP: 3.10.8, 3.3.2.1, 3.10.7 |  |

MP14 – C— ERCOT proposes splitting metric MP14 into MP14 – A and MP14 – B to cover SE trials participation and NOMCR trials participation separately and adding MP14 – C to address TSP Model Synchronization.

When splitting MP14 into MP14 – A and MP14 – B, we realized that there was not a metric that directly addressed TSP Model Synchronization.  TSP Model Synchronization is an important aspect of EDS 2, and should be reflected in the EDS 2 Trials Participation metric (MP14).  To continue allowing us the ability to report transparently, we propose adding TSP Model Synchronization as a separate portion of MP14 (MP14 – C) and measuring it, directly related to the protocols, as detailed below.

### MP14 – C - MP EDS-2, TSP Model Synchronization Participation

| Reported By: TDSP |  |  |  |
| --- | --- | --- | --- |
| Target Completion: TBD |  |  |  |
| Category: Trials Participation |  |  |  |
| Metric Description: - Gauge compliance with the following protocol sections: - Nodal Protocol § 3.10 (1) - Nodal Protocol § 3.10 (3) - Nodal Protocol § 3.10.7.1 (1) - Nodal Protocol § 3.10.7.1.1 - Nodal Protocol § 3.10.7.1.2 - Nodal Protocol § 3.10.7.1.3 - Nodal Protocol § 3.10.7.1.4 - Nodal Protocol § 3.10.7.1.5 - Nodal Protocol § 3.10.7.2 (4) - Nodal Protocol § 3.10.7.2 (7) - Nodal Protocol § 3.10.4 (7) - Nodal Protocol § 3.10.5 |  |  |  |
| Background: TBD ???????????????? TBD |  |  |  |
| Criteria: Ensure that Market Participants are compliant with the above listed protocol sections. RAG Rules - MPs Red - Not compliant Amber –Not applicable Green – Compliant RAG Rules – Market Segment Red – 5%+ Not meeting criteria Amber – any other scenario Green – 95+ meeting criteria |  |  |  |
| Reporting Data Sources: EDS 2 PM |  |  |  |
| References | TP: 5.4.1 | TNP: see above |  |

MP15 – A—ERCOT propose splitting metric MP15 into MP15 – A and MP15 – B to cover SCED/LFC trials and CRR trials separately.

Within MP15 – A, we propose specifying more closely how we will measure participation in SCED and LFC testing.  We also propose modifying the MP RAG rules to be more specific and objective and adding Segment RAG rules.

The situation for metric MP15 is very similar to the situation with MP14.  We recognize the importance of MP15, but find it difficult to report in a transparently manner.  MP15 covers both SCED and LFC testing (EDS 3, Release 5 and 6) and CRR testing (EDS 3, Release 7).  To accurately and transparently report on both of these areas, we needed to split the metric.  MP15 – A now addresses SCED and LFC Trials Participation while MP15 – B now addresses CRR Trials Participation.

### MP15 – A - MP EDS-3, Releases 5 and 6 Participation

| Reported By: QSER |  |  |  |
| --- | --- | --- | --- |
| Target Completion: 168-Hour Test |  |  |  |
| Metric Description: This metric evaluates the level of QSE market participant participation in EDS 3.5 and 3.6. |  |  |  |
| Background: The intent of this metric is to ensure active participation in SCED and LFC testing. |  |  |  |
| Criteria: Ensure active participation in SCED and LFC testing through monitoring COP and TPO submissions. Criteria: Weekly average of COP and TPO submissions >= 95% For Market Participants Meeting criteria = Green Within 10% of meeting criteria = Amber Not meeting criteria = Red For Market Segment Over 95% of Market Share Meeting Criteria = Green Over 5% of Market Share Failing to Meet Criteria = Red Any Alternative Scenario = Amber |  |  |  |
| Reporting Data Sources: EDS 3 PM |  |  |  |
| References | TP: 5.4.8 | TNP: 6.4.4, 6.5.7.1.12, 6.5.7.1.13 |  |

MP15 – B— ERCOT propose splitting metric MP15 into MP15 – A and MP15 – B to cover SCED/LFC trials and CRR trials separately.

Within MP15 – B, we propose modifying the MP RAG rules to be more specific and objective and adding Segment RAG rules.

The situation for metric MP15 is very similar to the situation with MP14.  We recognize the importance of MP15, but find it difficult to report in a transparently manner.  MP15 covers both SCED and LFC testing (EDS 3, Release 5 and 6) and CRR testing (EDS 3, Release 7).  To accurately and transparently report on both of these areas, we needed to split the metric.  MP15 – A now addresses SCED and LFC Trials Participation while MP15 – B now addresses CRR Trials Participation.

### MP15 – B - MP EDS-3, Release 7 Trials Participation

| Reported By: QSER Should this be reported by a CRR Account Holder and not a QSER? |  |  |  |
| --- | --- | --- | --- |
| Target Completion: 168-Hour Test |  |  |  |
| Metric Description: This metric evaluates the level of CRR market participant participation in EDS 3.7. |  |  |  |
| Background: The intent of this metric is to ensure that CRR is functional at the market level. |  |  |  |
| Criteria: The Readiness Team will review documentation that all interested MPs have participated in the CRR auction testing. # of CRR Account Holders Participating participating in CRR Auction Testing >= 90% For Market Participants Participating in CRR testing = Green Not participating in CRR testing, but intending to participate in the CRR auctions = Red Amber is not applicable If QSER is not intending in participating in the CRR auctions, they will be white For Market Segment Over 95% of CRR participating Market Share meeting criteria = Green Over 5% of CRR participating Market Share failing to meet criteria = Red Any Alternative Scenario = Amber |  |  |  |
| Reporting Data Sources: EDS 3 PM |  |  |  |
| References | TP: 5.4.8 | TNP: 6.4.4, 6.5.7.1.12, 6.5.7.1.13 |  |

MP16—ERCOT proposes freezing metric MP16 and modifying it at a later date. Due to the schedule slippages and the limited EDS 4 activities, we feel that tabling this metric at this time will not have any negative repercussions.

### MP16 - MP EDS-4 Trials Participation 
– TO BE REVISED AT A LATER DATE FOLLOWING THE ADOPTION OF THE REVISED/UPDATED NODAL IMPLEMETATION TIMELINE -

| Reported By: QSER, QSE |  |  | EDS: 4 |
| --- | --- | --- | --- |
| Target Completion: TBD |  |  |  |
| Metric Description: This metric evaluates the level of market participant participation in the EDS 4 Trial. |  |  |  |
| Background: The intent of this metric is to ensure adequate participation in the testing of Full Nodal Market Functionality. |  |  |  |
| Criteria: Market Participants are participating in each of the activities outlined in the EDS 4 Trails Handbook. The Readiness Team will review documentation that an adequate number of MPs by market segment representing an adequate percent of overall load have participated. QSEs Participating in EDS 4 represent > 99% of the LSE load intending to participate in Nodal Market QSEs Participating in EDS 4 represent > 99% of the Resource Entities intending to participate in Nodal Market RAG Rules – Market Segment Red – Not meeting criteria Amber – within 1 percent of criteria Green – meeting criteria |  |  |  |
| Reporting Data Sources: EDS 4 Trials Log / ERCOT EDS 4 PM |  |  |  |
| References | TP: 5.4.1 | TNP: 3.9, 3.16-18, 9.2.7-8 |  |

MP17—ERCOT proposes clarifying the RAG rule in MP17 to make it more objective and adding a Segment RAG rule

### MP17 - MP Qualification Activities

| Reported By: QSER, QSE |  |  |  |
| --- | --- | --- | --- |
| Target Completion: 168-Hour Test minus 90, 30, 14 days |  |  |  |
| Metric Description: This metric will measure the completion of specified qualification requirements to support 168-Hour Test Activities and particpate in NODAL market. |  |  |  |
| Background: The intent of this metric is to measure Market Participant ability to perform specific market and operational functions required for qualification approval of all required market-participation. This metric is not intended to be used for final qualification of Market Participants to participate in the market which is provided under a separate ERCOT process. |  |  |  |
| Criteria: The Readiness Team will review documentation that verifies that market participants are qualified to engage in the market. Target 1; Target 2; Target 3. 90% (90 days); 95% (30 Days); 100% (14 days). MP Qualification = Target % of number of MPs Intending to Participate in the market based on the following timeline: 90 percent 90 days prior to the 168 Hour Test 95 percent 30 days prior to the 168 Hour Test 100 percent 14 days prior to the 168 Hour Test MP RAG Rules Green = Qualified Amber = Qualifying, issues exist, working on issues Red = Not qualified, not working on issues For Market Segment Meeting criteria = Green Within 10% of meeting criteria = Amber Not meeting criteria = Red |
| Reporting Data Sources: Wholesale Client Services |  |  |  |
| References | TP: N/A | TNP: 16.1, 16.2 |  |

MP18—ERCOT proposes freezing MP18 and modifying it at a later date. Due to the schedule slippages and the limited EDS 4 activities, we feel that tabling this metric at this time will not have any negative repercussions.  Why..  This is very important to the progress of the nodal project.  Freezing this removes the incentives to progress.  ERCOT is bound to continue reporting metrics that are active.

### MP18 - Mapping of Resources and Loads in Private Area Networks is Complete

– TO BE MODIFIED AT A LATER DATE FOLLOWING THE ADOPTION OF THE REVISED/UPDATED NODAL IMPLEMETATION TIMELINE -

| Reported By: TSPs & ERCOT |  |  | EDS: 4 |
| --- | --- | --- | --- |
| Target Completion: Start Go Live Activities less 120 days |  |  |  |
| Metric Description: ERCOT shall ensure that all Private Use Networks in the TN Market have completed their mapping of any generation and loads necessary for go live operation. |  |  |  |
| Background: It is the intent of this metric to ensure that Private Use Networks are modeled as specified by the Nodal Protocols. |  |  |  |
| Criteria: The Readiness Team will review documentation that verifies that all Private Use Networks in the TN Market have accuractly modeled in the Network Operations Model. Readiness will be achieved when each Private Use Network has either mapped their generation and load or have accepted the existing default configuration. Generation and Load Mapping = 100% RAG Rules – Market Segment Red – Not meeting criteria Amber – within 10 percent of criteria Green – meeting criteria |  |  |  |
| Reporting Data Sources: Extract from Registration / ERCOT Manager of Wholesale Client Services |  |  |  |
| References | TP: N/A | TNP: 16.2.3.2(2) |  |

MP19—ERCOT proposes modifying/adding MP RAG rules and modifying Segment RAG rule in MP19 to be consistent with MP1 (Engagement for the other entity types).

### MP19 – Load Serving Entitles Engagement and Readiness

| Reported By: LSEs |  |  |  |
| --- | --- | --- | --- |
| Target Completion: Cyclical through 168-Hour Test |  |  |  |
| Metric Description: ERCOT shall ensure that all Load Serving Entities are fully engaged in preparation for the Nodal Market. |  |  |  |
| Background: It is the intent of this metric to ensure that Load Serving Entites are actively engaged in preparing for nodal market activities. |  |  |  |
| Criteria: The Readiness Team will review self-reported documentation that verifies that Load Serving Entities have acknowledged the planned start of nodal operations and have access to nodal training. For Market Participants Completed Survey with All Positive Responses = Green Completed Survey with One or More Negative Response = Amber Did Not Complete Survey = Red RAG Rules – Market Segment Over 95% of Market Share Responded Positively to the Survey = Green Over 5% of Market Share Did Not Respond to the Survey = Red Any Alternative Scenario = Amber |  |  |  |
| Reporting Data Sources: Self-Reported Survey |  |  |  |
| References | TP: N/A | TNP: N/A |  |

MP20—ERCOT proposes closing metric MP20 as MPs have already demonstrated their ability to submit an outage. We propose opening a new metric, MP23, that will serve as measure of outage scheduler ability. Reliant can not recall where all MPs have been tested in their ablity to submit Outages.  What removing TSPs from

{Closing this? metric may be premature given the discussions regarding the entry of data into the Outage Scheduler by TSP versus QSE personnel.  It may be better to freeze this metric pending the outcome of the discussions regarding changes to the Outage Scheduler.}

### MP20 - MP Ability to Submit Outage – Connectivity Test

| Reported By: QSER |  |  | EDS: 4 |
| --- | --- | --- | --- |
| Target Completion: Completed and Closed – now covered under MPx (New Entrant Metric) |  |  |  |
| Metric Description: This metric evaluates the ability of a Market Participant to submit an Outage to the NODAL Outage Scheduler and evaluates the level of TSP and QSE with Resources participation in the EDS 4.9.2 Outage Scheduler Data Submission. |  |  |  |
| Background: The purpose of this metric is to confirm that ERCOT, TSPs, and QSEs with Resources have synchronized use of the Outage Scheduler for Transmission Element Outages and use such to schedule Outages. This assures that the NODAL systems are properly updated. In addition, this metric will confirm that QSEs with Resources and TSPs are able to interact with the Nodal Outage Scheduler through the User Interface and Web Services (as applicable) and are able to submit Outages conforming to the Nodal Protocols. QSEs with Resources and TSPs are required to participate in the Validation of Performance phase of Outage Scheduler testing. |  |  |  |
| Criteria: - QSEs with Resources and TSPs have successfully interacted with the NODAL OS and submitted required outage types using the RUI and, as applicable, Web Services - QSEs with Resources and TSPs participate in the Validation of Performance phase of EDS testing MP RAG Rules Green = Complete Amber = Not complete, less than 1 month past target completion date Red = Not complete, over a month past target completion date RAG Rules – Market Segment Red – Not meeting criteria Amber – within 10 percent of criteria Green – meeting criteria |  |  |  |
| Reporting Data Sources: EDS 4.9 Testing Logs / ERCOT EDS 4 PM |  |  |  |
| References | TP: 5.4.1. 5.4.10 | TNP: 3.1 |  |

MP21—ERCOT proposes adding MP21 as a new metric as proposed at TPTF on 7/7/08.

### MP21 – Wind Generating Resources ICCP Telemetry

| Reported By: QSE with WInd Resources & ERCOT |  |  | EDS: 4 |
| --- | --- | --- | --- |
| Target Completion: December 31, 2008 |  |  |  |
| Category: Telemetry |  |  |  |
| Metric Description: Wind Generation Resources confirmed their provision of Wind generation Mw, and required meterlogical ICCP telemetry to ERCOT meeting protocol requirements, including Sections 3.13 Renewable Production Potential Forecasts and Section 4.2.2 Wind-Powered Generation Resource Production Potential and ERCOT Procedures providing details of the required telemetry, for the Early Delivery System (EDS) environments and zonal environments as required. |  |  |  |
| Background: The intent of this metric is to ensure that Wind Resources are providing to their selected QSE the required telemetry to meet nodal protocols and that QSE is successfully connected its ICCP to the EDS allowing ERCOT to provide better wind production potential forecasting as required by protocols. |  |  |  |
| Criteria: The Readiness Team will review documentation providing ICCP statistics for the EDS4 environment by Wind Resouce and by QSEs with Wind Resources. Readiness will be measured when Wind Resources provide required data to ERCOT on a continous basis according to protocol requirements. Results will be reported by individual Wind Resources RAG Rules Red – If Resource fails to meet Target Completion deadline Amber – If Resource fails to provide all required data for each Wind Resouce by October 31, 2008 Green – Meeting Plan |  |  |  |
| Reporting Data Sources: PI database in EDS / ERCOT EDS 4 PM EDS 4 team will track Wind Generation registration and ICCP telemetry standard for Wind Resources and QSEs with Wind Resouces |  |  |  |
| References | TP: N/A | TNP: 3.13 & 4.2.2 |  |

MP22—ERCOT proposes adding MP22 as a new metric to measure the activity of new entrants to the market and existing Entities with new Resources; need to add MP5 links before the next review.

### MP22 – New Entrant Readiness ??????????? this language does not seem ready to be voted on as written.  What is the specific language?  Why are TSPs in the list when they are not in the “Reported By” list??

| Reported By: QSER, QSE |  |  |  |
| --- | --- | --- | --- |
| Target Completion: 168-Hour Test Minus 45 Days What is the criteria for new entrance after the 168 Hour Test is completed? |  |  |  |
| Category: Registration and Qualification |  |  |  |
| Metric Description: QSER: 1) Confirmation of the ability to connection to the MIS and/or an External Web Service in Early Delivery Systems (EDS). Previously MP2 2) Confirmation of the ability to submit a Three Part Offer (TPO) and, if applicable, a dynamic output schedule to the MIS and/or External Web Service in EDS. Previously MP3 3) Verification that QSE has the ability to submit transactions via the Web Services. Previously MP9 4) To include MP5 link QSE: 1) Verification that QSE has the ability to submit transactions via MIS. Previously MP8 2) To include MP5 link TDSP: 1) To include MP5 link |  |  |  |
| Background: QSER: This metric will evaluate the MPs ability to send transactional submissions via External Web Services to ERCOT and receive notifications from ERCOT, a crucial ability for Market Participants in the Day Ahead and Real Time Markets….. To include MP5 link QSE: This metric will evaluate the MPs ability to send transactional submissions via the MIS to ERCOT crucial ability for Market Participants in the Day Ahead Market…. To include MP5 link TDSP: ###### To include MP5 link |  |  |  |
| Criteria: Criteria: MP Completion Checklist by Production PM and MP and On File with EDS PM ##### For New Entrant Market Participants Meeting Criteria = Green Failing to Meet Criteria, Prior to 30 Calendar Days from Entrance to Market = Amber Failing to Meet Criteria, Prior to 60 Calendar Days from Entrance to Market = Red For Market Segment Over 95% of Market Share Meeting Criteria = Green Over 5% of Market Share Failing to Meet Criteria, Post Completion Date = Red Any Alternative Scenario = Amber |  |  |  |
| Reporting Data Sources: Production PMs |  |  |  |
| References | TP: N/A | TNP: N/A |  |

MP23—ERCOT proposes adding MP23 as a new metric to follow MP20. This metric will address Outage Trials Participation. Details for this metric will be discussed in a future Readiness Metrics Update. This metric is not compete.  Need to final language in order to support.

### MP23 – Outage Scheduler Trials Participation

| Reported By: QSER, TDSP |  |  |  |
| --- | --- | --- | --- |
| Target Completion: |  |  |  |
| Category: Trials Participation |  |  |  |
| Metric Description: |  |  |  |
| Background: |  |  |  |
| Criteria: |  |  |  |
| Reporting Data Sources: |  |  |  |
| References | TP: | TNP: |  |