## Slide 1: EMMS Infrastructure Cost/Risk Analysis
TAC
August 7th, 2008
Aaron Smallwood
Manager, IT Business & Customer Services

## Slide 2: Scope
Perform an analysis and comparison of the costs and risks associated with the three most plausible courses of action for the Zonal production EMMS infrastructure
Drivers for this analysis:
  Aging Zonal hardware infrastructure and increasing failure rates
  April 2008 infrastructure failure that impacted the market and ERCOT production operations
  Delay in Nodal program delivery
ERCOT Public

## Slide 3: Methodology
Failure Rate & Implementation Summary:
Forecasted failure rates of the EMMS infrastructure servers and storage equipment are based on historical data and forecasted at an increasing rate in subsequent years
ERCOT implementation costs include asset acquisition and ERCOT labor estimates for project completion
Year three (2010) cumulative costs are used for comparison
Cost Summary:
Capital expenditure = ERCOT implementation cost
Support costs = ERCOT maintenance expenses
Failure costs = 600 hours of ERCOT + 400 hours of market recovery labor costs @ $65/hour (per incident)
Cumulative costs = capital expenditure + support costs + failure costs
ERCOT Public

## Slide 4: Alternatives Considered
Alternative One:
  Retain the existing server and storage infrastructure and continue to maintain parts inventories and high priority vendor support contracts
Alternative Two:
  Retain the existing server infrastructure while migrating from directly attached storage to ERCOT SAN infrastructure
Alternative Three:
  Full replacement of both the server and storage infrastructure including application porting to a new operating system
ERCOT Public

## Slide 5: Alternative One – Retain existing infrastructure
Retain the existing server and storage infrastructure and continue to
maintain parts inventories and high priority vendor support contracts
Year Three Cost:
  Initial Capital Expenditure = $0
  Annual Support Cost = $625,000
  Annual Failure Cost = $325,000
  Cumulative Year Three Cost = $2,460,000
Key Risks:
  Aging infrastructure increases the risk of failure
ERCOT Public

## Slide 6: Alternative Two – Replace storage infrastructure
Retain existing server infrastructure while migrating from directly
attached storage to ERCOT SAN infrastructure
Year Three Cost:
  Initial Capital Expenditure = $1,090,400
  Annual Support Cost = $575,000
  Annual Failure Cost = $130,000
  Cumulative Year Three Cost = $3,035,400
Key Risks:
  Continued failure of server infrastructure even though storage infrastructure has been replaced
Key Constraints:
  Lack of floor space, cooling, and power in the ERCOT data centers for the new infrastructure required for this solution
ERCOT Public

## Slide 7: Alternative Three – Full replacement (servers & storage)
Full replacement of the server and storage infrastructure
Year Three Cost:
  Initial Capital Expenditure = $7,734,400
  Annual Support Cost = $300,000
  Annual Failure Cost = $0
  Cumulative Year Three Cost = $8,959,499
Key Risks:
  The market management software is not supported by the vendor on the new operating system and the feasibility of moving the application to the new operating system is unknown. Even if possible it would be unsupported by the software vendor.
Constraints:
  Lack of floor space, cooling, and power in the ERCOT data centers for the new infrastructure required for this solution
ERCOT Public

## Slide 8: Comparable Cost Summary
Assumptions:
Year one begin date is July 1st, 2008
Alternatives two and three will require approval cycle of two or three months before work can begin
Alternative two implementation duration is estimated at 4-6 months with an expected completion date of Jan 2009.
Alternative three implementation duration is 9-12 months with an expected completion date of July 2009
ERCOT Public
7 August 2008
2008
2009
2010
2011

## Slide 9: Risk vs. Cost Matrix
ERCOT Public
7 August 2008