## Slide 1: TPTF Update for TAC August 7, 2008 Joel Mickey
http://nodal.ercot.com <number>
Notes: <number>

## Slide 2: Agenda:
http://nodal.ercot.com <number>
Item | Description | Purpose
1. TPTF Action Items | Status of action items assigned to TPTF by TAC | For Review
2. Meeting Summary | Summary of recent TPTF activities | For Review
3. Vote Summary | Summary of recent TPTF Votes | For Review
4. Next Meetings | Upcoming activities | For Review
5. Approval of Milestones | Request TAC acknowledge TPTF completion of the following Milestones: Infrastructure (INF) Market Participant Identity Management (MPIM) Requirements Readiness Metric MP21, Wind Generating Resources Inter-Control Center Communication Protocol (ICCP) Telemetry | For Vote
Notes: <number>

## Slide 3: TPTF Action Items:
http://nodal.ercot.com <number>
TPTF Action Items:
  TPTF currently has two open Action Items with TAC:
    Item One: Wind Issue
      On October 16, 2007, the ERCOT Board discussed NPRR045, Wind Power Forecasting. Concerns were voiced that future switchable Wind-Powered Generation Resources (WGRs) may pose reliability or settlement issues not currently addressed by existing processes or system logic.
    Item Two: Timeline Issue
      On May 8, TAC requested that TPTF would reassess the 30-day timeline for system maintenance in Protocol Section 21.12.5, Reinstatement of Zonal Protocol Provisions.
Notes: <number>

## Slide 4: TPTF Action Items:
http://nodal.ercot.com <number>
TPTF Action Items (continued):
  Item One: Wind Issue
  On May 7, 2008, TPTF discussed reliability issues for switchable WGRs and determined that:
    ERCOT currently has no switchable WGRs, so no reliability or settlement issues need to be addressed at this time.
    When switchable WGRs begin to operate in the ERCOT region, they will be able to make adjustments to the status of units that are available to ERCOT in the Current Operating Plan (COP).
      The “status” selections available in the COP may need to be expanded for WGRs to indicate where capacity will be available for any given period.
    When switchable WGRs begin to operate in the ERCOT region, they may also prorate their capacity available to ERCOT by reflecting corresponding Outages in the Outage Scheduler.
    If the future number of switchable WGRs or frequent switching activity indicates the need for a more robust solution than what can be accommodated via the COP or the Outage Scheduler, then ERCOT may need to revisit the Reliability Unit Commitment (RUC) capacity credit in Settlements and other potential issues.
Notes: <number>

## Slide 5: TPTF Action Items:
http://nodal.ercot.com <number>
TPTF Action Items (continued):
  Item One: Wind Issue (continued):
    Nodal Protocol Section 16.5.4 (2) states that a Resource that has a switchable Generation Resource must report to ERCOT by April 1st its availability during the Peak period (July – August). There is a question as to whether this Nodal Protocol is sufficient
    On July 21, 2008, TPTF noted that ERCOT should stipulate that switchable WGRs need to be reflected in the information that WGRs are asked to submit on the Resource Asset Registration Form (RARF)
    TPTF does not believe that further action is required at this time.
Notes: <number>

## Slide 6: TPTF Action Items:
http://nodal.ercot.com <number>
TPTF Action Items (continued):
  Item Two: Timeline Issue
    ERCOT Protocol 21.12.5, Reinstatement of Zonal Protocol Provisions:
      Market Participants shall maintain their zonal generation control systems for a period of thirty (30) days after the Texas nodal market implementation date. In the event of a contingency in implementation of the nodal market design for generation control subsystems (Load Frequency Control and Security Constrained Economic Dispatch as defined in the Nodal Protocols) or settlement systems that causes the ERCOT CEO to deem it necessary to reinstate a Zonal Protocol section, ERCOT shall issue a Notice stating the date and time on which the Zonal Protocol section will be reinstated. The time lines set forth in Section 21.12.2, Notice to Market Participants of Activities Essential for Nodal Market Open, shall not apply to any such reinstatement. That Notice will also include a description of the reason why the reinstatement is necessary and a proposed timeline for resolution of the system failure.
Notes: <number>

## Slide 7: TPTF Action Items:
http://nodal.ercot.com <number>
TPTF Action Items (continued):
  Item Two: Timeline Issue (continued):
    Reviewed issue with TPTF and internally at ERCOT.
    Conclusion: Believe the 30 day time-line is sufficient.
Notes: <number>

## Slide 8
http://nodal.ercot.com <number>
Meeting Summary:
TPTF Met 3 times since last TAC Meeting:
  June 23-25
  July 7-8
  July 21-23
Notes: <number>

## Slide 9
http://nodal.ercot.com <number>
Meeting Summary:
Discussed need to revise Nodal Protocols to allow Generation Resources to submit block offers for off-line Non-Spinning Reserve Service (NSRS)
Program Announcement
  Discussed recent organizational changes for the nodal program
  Reviewed Nodal Org Chart
  Change control process:
    TPTF’s role: Initial determination for “Needed for go-live”
Readiness Metrics:
  MP21, Wind Generating Resources ICCP Telemetry
Outage Scheduler Issues
  Need for Resource Entities to enter their Outages
Notes: <number>

## Slide 10
http://nodal.ercot.com <number>
Meeting Summary:
Technical Communication Workshop:
  Discussed need for basic technical components involved in setting up and maintaining interfaces with ERCOT web services
    Scheduled for September 3.
Congestion Revenue Rights (CRR) Credit Policy Task-Force Update
  Draft NPRR for Day-Ahead Market (DAM) Short Pay changes
  NPRR 140 Revision to CRR Obligation Margin Adder
Special TPTF meeting Aug 4-5
  Discuss Whitepaper on Private Use Network’s (PUNS)
Notes: <number>

## Slide 11
MP21 – Wind Generating Resources ICCP Telemetry:

## Slide 12: MP21 – Wind Generating Resources ICCP Telemetry:
Voted on and approved for TAC consideration by the Independent Power Marketer Market Segment on July 22nd
  Carried by a roll-call vote with 100% in favor and one abstention
  All market segments were represented
Metric will allow ERCOT to provide better wind production potential forecasting
  Ensure Wind Resources are providing the Nodal protocols required telemetry data to their selected QSE
  Ensure the selected QSEs are successfully connecting their ICCPs to the EDS
Criteria/RAG Rules
  EDS 4 team will review ICCP statistics for Wind Resources, QSEs with Wind Resources
  Criteria is met when Wind Resources provide all protocol required data to ERCOT on a continuous basis
    Red – Resource fails to meet criteria by the target completion deadline
    Amber – Resource fails to meet criteria by October 31, 2008
    Green – Resource meets criteria
Details
  Telemetry metric for QSEs with Wind Resources
  Target completion date of December 31, 2008
  Reported by EDS 4 Project Team (PI Database, PM)
  Linked to Texas Nodal Protocols
    3.13 (Renewable Production Potential Forecasts)
    4.2.2 (Wind-Powered Generation Resource Production Potential)

## Slide 13
Vote Summary: June 23 - 25, 2008
Vote Item | Sector | For | Against | Abstention
On June 23, TPTF endorsed RMS comments to NPRR126, Section 19, Synchronization of Zonal Protocols | Cooperative | ■ |  | LCRA
 | Municipal | ■ |  | Austin Energy
 | Investor Owned Utility | ■ |  | 
 | Independent Generator | ■ |  | 
 | Consumer |  |  | 
 | Independent REP | ■ |  | 
 | Independent Power Marketer | ■ |  | Shell Energy North America
Note: the votes in the above summary are available for pick-up from the June 23-25 TPTF Meeting Page.
Vote Item | Sector | For | Against | Abstention
On June 23, TPTF approved the amended INF Market Participant Identity Management Requirements v3.5. | Cooperative | ■ |  | 
 | Municipal | ■ |  | 
 | Investor Owned Utility | ■ |  | Centerpoint Energy
 | Independent Generator | ■ |  | 
 | Consumer |  |  | 
 | Independent REP | ■ |  | 
 | Independent Power Marketer | ■ |  | 
http://nodal.ercot.com <number>

## Slide 14
Vote Summary: June 23 - 25, 2008
Note: the vote in the above summary is available for pick-up from the June 23-25 TPTF Meeting Page.
Vote Item | Sector | For | Against | Abstention
On June 24, TPTF approved the Texas Nodal Market 168-Hour Test Procedure v0.04 | Cooperative | ■ |  | LCRA
 | Municipal | ■ |  | 
 | Investor Owned Utility | ■ |  | 
 | Independent Generator | ■ |  | 
 | Consumer |  |  | 
 | Independent REP | ■ |  | 
 | Independent Power Marketer | ■ |  | 
http://nodal.ercot.com <number>

## Slide 15
Vote Summary: July 7 - 8, 2008
Note: the votes in the above summary are available for pick-up from the July 7-8 TPTF Meeting Page.
Vote Item | Sector | For | Against | Abstention
On July 7, TPTF recognized the following NPRRs as “essential for go-live”: NPRR097, NPRR107, NPRR111, NPRR112, NPRR117, NPRR118, NPRR119, NPRR120, NPRR122, NPRR123, NPRR130, NPRR091, NPRR102, NPRR113, NPRR114, NPRR127, NPRR128, NPRR132, NPRR133, NPRR134, NPRR126 | Cooperative | ■ |  | 
 | Municipal | ■ |  | 
 | Investor Owned Utility | ■ |  | 
 | Independent Generator | ■ |  | Centerpoint Energy American Electric Power
 | Consumer |  |  | City of Dallas City of Eastland City of Allen Town of Flower Mound
 | Independent REP | ■ |  | 
 | Independent Power Marketer | ■ |  | 
http://nodal.ercot.com <number>

## Slide 16
Vote Summary: July 7 - 8, 2008
Note: the vote in the above summary is available for pick-up from the July 7-8 TPTF Meeting Page.
Vote Item | Sector | For | Against | Abstention
On July 7, TPTF endorsed forwarding TPTF comments to PRS for NPRR124, Resource Node Updated Definitions, to replace the first sentence of the definition of Resource Node to “Either a logical construct required to model a Combined-Cycle Configuration or an Electrical Bus defined in the Network Operations Model, at which a Generation Resource’s Settlement Point Price is calculated and used in Settlement | Cooperative | ■ |  | 
 | Municipal | ■ |  | Austin Energy
 | Investor Owned Utility | ■ |  | American Electric Power
 | Independent Generator | ■ |  | 
 | Consumer |  |  | 
 | Independent REP | ■ |  | 
 | Independent Power Marketer | ■ |  | 
http://nodal.ercot.com <number>

## Slide 17
Vote Summary: July 7 - 8, 2008
Vote Item | Sector | For | Against | Abstention
On July 8, TPTF approved the EDS Daylight-Savings Time Test Plan v0.04 as submitted. | Cooperative | ■ |  | 
 | Municipal | ■ |  | 
 | Investor Owned Utility | ■ |  | 
 | Independent Generator | ■ |  | 
 | Consumer |  |  | 
 | Independent REP | ■ |  | 
 | Independent Power Marketer | ■ |  | 
Note: the vote in the above summary is available for pick-up from the July 7-8 TPTF Meeting Page.
http://nodal.ercot.com <number>

## Slide 18
Vote Summary: July 21 - 23, 2008
Vote Item | Sector | For | Against | Abstention
On July 22, TPTF endorsed forwarding Readiness Metric MP21 – Wind Generating Resources ICCP Telemetry to TAC for consideration and approval as modified by TPTF on July 22, 2008. | Cooperative | ■ |  | 
 | Municipal | ■ |  | 
 | Investor Owned Utility | ■ |  | 
 | Independent Generator | ■ |  | 
 | Consumer | ■ |  | 
 | Independent REP | ■ |  | 
 | Independent Power Marketer | ■ |  | Exelon
Note: the votes in the above summary are available for pick-up from the July 21-23 TPTF Meeting Page.
Vote Item | Sector | For | Against | Abstention
On July 22, TPTF approved extending the effective period for the current EDS Service Level Agreement for Nodal EDS Environments for an additional 30 days and to make changes to the dates identified in the document as appropriate. | Cooperative | ■ |  | 
 | Municipal | ■ |  | 
 | Investor Owned Utility | ■ |  | 
 | Independent Generator |  |  | 
 | Consumer |  |  | 
 | Independent REP | ■ |  | 
 | Independent Power Marketer | ■ |  | 
http://nodal.ercot.com <number>

## Slide 19
Vote Summary: July 21 - 23, 2008
Vote Item | Sector | For | Against | Abstention
On July 22, TPTF endorsed forwarding TPTF comments to PRS for NPRR138, Credit Monitoring and Management Reports, as modified July 22, 2008, including the comment that TPTF believes that all MIS postings shall be made in a format (such as xls, csv, xml, etc) amenable to download and insertion into market participant’s systems to use individual elements of a report. | Cooperative | ■ |  | 
 | Municipal | ■ |  | 
 | Investor Owned Utility | ■ |  | 
 | Independent Generator | ■ |  | 
 | Consumer | ■ |  | 
 | Independent REP | ■ |  | 
 | Independent Power Marketer | ■ |  | 
Note: the vote in the above summary is available for pick-up from the July 21-23 TPTF Meeting Page.
http://nodal.ercot.com <number>

## Slide 20
Vote Summary: July 21 - 23, 2008
Vote Item | Sector | For | Against | Abstention
On July 23, TPTF approved the Procedure for Identifying Resource Nodes White Paper as modified by TPTF on July 23, 2008. | Cooperative | ■ |  | 
 | Municipal | ■ |  | 
 | Investor Owned Utility | ■ |  | 
 | Independent Generator |  |  | 
 | Consumer |  |  | 
 | Independent REP | ■ |  | 
 | Independent Power Marketer | ■ |  | 
Note: the votes in the above summary are available for pick-up from the July 21-23 TPTF Meeting Page.
Vote Item | Sector | For | Against | Abstention
On July 22, TPTF endorsed NPRR129, Section 15, Synchronization of Zonal Protocols, including RMS comments, as "Needed for Go-Live." | Cooperative | ■ |  | LCRA
 | Municipal | ■ |  | 
 | Investor Owned Utility | ■ |  | 
 | Independent Generator | ■ |  | 
 | Consumer | ■ |  | 
 | Independent REP | ■ |  | 
 | Independent Power Marketer | ■ |  | 
http://nodal.ercot.com <number>

## Slide 21
http://nodal.ercot.com <number>
Next Meetings:
On August 11-12, likely topics include:
  Outage Schedules scope changes
  Revised readiness metrics
  Begin first process overview and procedures
    Day-Ahead market
  Verifiable cost issues
  Integrated Schedule
Notes: <number>

## Slide 22
http://nodal.ercot.com <number>
Next Meetings (continued):
Next Meetings:
  Monday, August 11 and Tuesday August, 12
  Monday, August 25 through Wednesday, August 27
  Monday, September 8-9
  Monday, September 22-24
Visit the 2008 TPTF Calendar
Notes: <number>

## Slide 23
http://nodal.ercot.com <number>
Approval of Milestones:
On June 23, 2008, TPTF moved to approve the INF Market Participant Identity Management Requirements v3.5 as amended by TPTF on June 23, 2008. The vote carried by roll-call vote with 100% in favor and one abstention (CenterPoint). The Consumer Market Segment was not represented for the vote.
On July 22, 2008, TPTF moved to endorse forwarding Readiness Metric MP21, Wind Generating Resources ICCP Telemetry, to TAC for consideration and approval as modified by TPTF on July 22, 2008. The motion carried by roll-call vote, with 100% in favor and one abstention (Exelon). All Market Segments were represented for the vote.
The Transition Plan says: “Any declaration of the accomplishment of a major milestone (business requirements, conceptual design, and successful completion of Market Participant testing) or a decision to proceed is contingent on the approval of both ERCOT and TAC.”
Request TAC acknowledge TPTF completion of the following Milestones:
  INF Market Participant Identity Management Requirements complete
  Metric MP21, Wind Generating Resources ICCP Telemetry, complete
Notes: <number>

## Slide 24
http://nodal.ercot.com <number>
Questions
?
Notes: <number>