## Slide 1: Texas Nodal Market Implementation: Program Update
Ron Hinsley

## Slide 2: Agenda
Program Status
Accomplishments
Program Assessment and Schedule Revision
AREVA CIM Status
ERCOT Staff / Market Participant Readiness
Cost
Quality Controls (Eileen Hall)

## Slide 3: Program Status
`
Nodal Delivery status is:
ERCOT Staff Readiness status is:
Market Participant Readiness status is:
Cost
Schedule
Scope / Quality
Nodal Delivery
Amber status driven by the limited response to the Cycle 4 Survey (out-reach efforts are on-going)
Red status driven by quality, schedule, and cost impacts
Red
Red
Amber
Amber status driven primarily by E8, the staffing metric
Red*
* Final cost unknown until new schedule confirmed
Red
Amber
Amber
 | Scope | Quality | Schedule | Cost
Green | Program is aligned with current protocols | All Nodal products currently achieve quality standards | Go-Live = 12/1/2008 | Estimate at Complete =< 319M
Amber | Program is aligned to previous protocol versions | Most Nodal products currently achieve quality standards | Go-Live =< 30 days | Estimate at Complete =< 319M +10%
Red | Program is not aligned to protocols | Product quality not sufficient for Nodal launch | Go-Live =>30 days+ | Estimate at Complete => 319M +10%
Notes: <number>

## Slide 4: Accomplishments
Program Successes and Upcoming Market Activities
  MMS has received 3 patches from ABB (since the April 22 delivery of MMS4) on time with at least 100 defects resolved in each patch
  EMO12 (Network Operations Model and SE Performance) is GREEN
    The goal for this metric is => 99% of load is modeled. Of the initial 5000, there are only 47 remaining unobservable buses with load (<1%)
  Technical Communications Workshop
    Scheduled for September 3, 2008
    The purpose is to cover basics of implementing and maintaining interfaces with ERCOT Web Services
Schedule Development – Accomplishments to Date
  Completed “Plan for a Plan” and executing against it
  All individual project schedules integrated; in process of refining and optimizing the draft integrated schedule
  Working to incorporate EDS and integration project schedules into overall integrated schedule
Notes: <number>
<footer>
<header>
<date/time>

## Slide 5: Nodal Implementation – Assessment and Adjustment
ERCOT has implemented a change in the delivery approach because the nodal program has entered the early stages of integration:
  ERCOT has shifted perspective to a model that better supports integration of multiple large projects at the program level to ensure successful integration and end-to-end delivery
  The nodal program is putting much more rigor around program and budget controls, resource management and release management
  ERCOT has learned from past experience and is better positioned to reassess program complexities, dependencies, linkages, and task durations
  Assessment and schedule integration activities are allowing ERCOT to reassess program health without losing momentum

## Slide 6: Nodal Implementation – Adjustment Benefits
Results of the program adjustments include:
  Fully integrated schedule driven by core delivery projects with supporting functional and infrastructure projects
    Enhanced critical path identification and impact analysis capabilities
    Improved risk/issue detection and remediation/elimination
    Higher confidence in delivery to scheduled milestones
    Increased internal / external visibility and transparency to schedule analysis activities
  More rigorous testing in all environments
    Improved overall quality
    Earlier detection of defects / Shorter defect resolution periods
    Lower defect realization in EDS environment
  Improved release management and identification of release bundles
    Fewer number of releases will be easier for market participants to manage
    Improved support to EDS activities
    Increased support to Market Participants for management of their own activities and resource needs

## Slide 7: Nodal Integrated Program Schedule Key Dates
Schedule Development Activities
  Complete core project schedules with dependencies
  Complete supporting project schedules
  Integrate core project schedules
  Integrate supporting project schedules into overall integrated schedule
  Refine integrated schedule
  Review with ERCOT executives and refine
  Develop accompanying budget
  Provide draft integrated schedule to TPTF
  Review with TPTF
  Review with TAC
  Complete schedule refinement and optimization
  Prepare communication for Board meeting
  Present integrated schedule to ERCOT Board
July 21 (Complete)
July 23 (Complete)
July 23 (Complete)
July 25 (Refining)
Aug. 4-8 (Ongoing)
Aug. 5-15
Aug. 8-15
Aug.11*
Aug. 25
Sep. 4
Sep. 5
Sep. 5
Sep. 16
The August 11th date is a target. ERCOT may need to work with TPTF to schedule a special meeting to review the draft schedule and, as such, this date may change.
Notes: <number>
<footer>
<header>
<date/time>

## Slide 8: Sample Schedule Milestones
Example milestones to be communicated to MPs:
Approximately 150 milestones
Schedules and milestones dynamically linked
  Change to a date in one schedule automatically updates dates for dependent activities and milestones

## Slide 9: AREVA (CIM) Status
EMS CIM Importer – still testing at AREVA
ERCOT SMEs are testing with AREVA to identify and resolve issues with the goal of being able to start/run individual applications
ERCOT staffing on-site until CIM Importer exits preFAT
ERCOT is monitoring AREVA’s performance trends to address continuing or potential issues
Notes: <number>

## Slide 10: ERCOT Readiness
Engagement (green)
  ERCOT remains fully engaged
Training (amber)
  Training efforts are on-going
Process (green)
  All departments are meeting target performance levels
Staffing (amber)
  ERCOT is currently ~95% staffed
  (98% required for green status)
  Recruitment is on-going
Testing (green)
  No recent developments
ERCOT Staff Readiness status is AMBER

## Slide 11: Market Participant Readiness
Market Participant Readiness status is AMBER
Engagement (amber)
  Limited survey response from QSEs and LSEs drives amber status
  Out-reach efforts are on-going
Connectivity (green)
  No change
Registration and Qualification (amber)
  MP10 (resource mapping) continues to improve
  MP11 (RARF data) – RARFs representing more than 99.5% of MWs have been submitted
Telemetry (green)
  No change
Training (amber)
  Limited survey response from QSEs drives amber status
Trials Participation (green)
  Consistently solid performance for MP15 (EDS 3 trials participation)

## Slide 12: Cost: Element Summary
ERCOT Public
When the integrated schedule has been finalized and the financial impact determined we will incorporate this into an updated forecast

## Slide 13
LTD Spend (June actuals) 268 (1)
July (projected) 12
Committed contracts 40
July contracts/July NPRRs 6
Total commitments (2) 46
Total spend and commitments 326
Approved budget 319
Potential EAC Variance (over) (7)
(2) Contract commitments generally have 30-day out clauses
(1) Values represent $1 million
Nodal Financials

## Slide 14: Quality Controls
Eileen Hall

## Slide 15: Nodal Quality is of Increasing Concern
Areas of concern we are addressing:
  Inadequate test cycle durations
  Limited testing in lower environments
    DEV, preFAT, FAT
  Late detection of defects resulting in lengthy defect resolution time
  Rate of increase in number of severity 3 defects
    205% since January
  Minimal testing in integrated test environment to date

## Slide 16: Estimating Test Durations for Revised Schedule
Strategy for estimating testing time durations
  Determine level of effort remaining
  Analyze historical data
    Total defects to date
    Average defects per release
    Defect turnaround time
  Estimate number of releases and defect fix builds for future deliverables
    Compare to previous releases of similar level of complexity
  Other considerations
    Adequate time for migration/installation/smoke
    Dependent systems availability
    Creating/updating testing artifacts
    Emergency EDS patch support

## Slide 17: Number of Weeks of Test vs. Number of Weeks of Defect Management
The longer the test duration, the shorter the defect management time
(when number of weeks in test increases, defect management time decreases)

## Slide 18: Defect Turnaround Time for EDS vs. FAT
Defect turnaround time is the average time it takes (in days) to resolve a defect. This time includes detection, analysis, fix, successful retest, and close
Late detection of defects increases defect turnaround time
FAT – 51 days
EDS – 73 days
43% increase

## Slide 19: Nodal Active Defects by Severity Trend
Severity 3 defect trend is remaining relatively constant
  Indicates that current defect close rate is equal to defect open rate
  36 severity 1, 166 severity 2, and 767 severity 3 defects are currently outstanding
Severity 2
Severity 3
Severity 1

## Slide 20: Nodal Active Defects by Severity by Project
Note – Includes New, Open, Reopen, Fixed and Test

## Slide 21: Approach Moving Forward
Provide for adequate test cycles in revised schedule by ensuring planning for adequate testing time in the appropriate environments
Increase amount of testing in DEV, preFAT, and FAT to detect defects earlier, decrease overall defect resolution time, and decrease number of ‘defect fix’ builds
Prioritize defects on a program level to identify must-fix defects
Adhere to test phase entry/exit criteria
Increase focus on integration testing
Complete test documentation resulting in more comprehensive test suites

## Slide 22
Questions?