## Slide 1: July 2008 RO Projects Financial Overview Retail Market Subcommittee August 13, 2008 Hope Parrish Market Operations Division Projects Organization

## Slide 2: 2008 RO PPL
Planned and Unplanned 2007
Carry-over Projects
(Green Shaded Area)
Projects ABOVE the
current Capability Line
(Orange Shaded Area)
Projects BELOW the
current Capability Line
(Yellow Shaded Area)

## Slide 3: 2007 Carry-Over Projects
PR60015_01: Registration Data Model Assessment – Moved to “Closing” 08/08/2008
PR60008_01: T&Cs / Performance Measures – “Closing” Start 08/15/2008
PR70007_01: MarkeTrak Ph2 – Release 2 Go-Live 08/16/2008

## Slide 4: Projects ABOVE the Capability Line
PR70006_02 Website Enhancements for ERCOT Outages (SCR748) Ph.II – Execution 07/25/2008
PR80028_01 Small Renewables/Distributed Generation - Execution 08/08/2008
PR80027_01 Advanced Metering (PRR766 Interim Solution) – Not Started
Notes: 50061_01 Moved to ON Hold: Freed up approx. $120k, however not recommended for release by CART

## Slide 5: Projects BELOW the Capability Line
No status change on these projects
Projects below this line are under the capability line for 2008 and recommended for 2009 |  |  |  |  |  |  |  |  |  | 
ERCOT/Market | RMS | RO/MO |  | Advance Metering Infrastructure (ERCOT Changes) | New | Not started | 1 - Critical | 2009 | $1M-3M | $1M-3M
ERCOT | RMS | RO |  | TML Transition to MIS | New | Not started | 2 - High | 2009 | $250k-$500k | $1M-3M
ERCOT | RO | RO |  | EDW EAI Transition (inc. PaperFree & NAESB) | 50061_02 | Not started | 2 - High | 2009 | $100k-$250k | $3M-$4M
ERCOT | RO | RO |  | MarkeTrak Phase 3 | 80030_01 | Not started | 2 - High | 2009 | $100k-$250k | $3M-$4M
ERCOT | RO | RO |  | Retail Application Upgrades | 80031_01 | Not started | 1 - Critical | 2009 | $1M | $3M-$4M
Notes: ERCOT will continue to evaluate the projects under the line to determine if we can move anything up. Currently the items just below the line are funded with the 2008 PPL

## Slide 6: Financial Overview as of 05/01/2008 (cont’d)
RO PPL Budget Activity | Amount | Notes/comments
Approved RO Capability Line Budget Funding | $3.83M | Current approved RO funding allocation Designates where the capability line falls $2.27M Released due to deferred projects (Originally $6.1M Approved)
Current Forecast Spend of projects above the Capability Line | ~$2.88M | Based on current expectations and run rates for active and not started projects above the capability line
Budget Variance | ~$950K | Budget Variance is difference between RO Capability Line Budget Funding and Current Forecast Spend of projects above the Capability Line Variance attributed to projects deferred to future years Will be monitored throughout 2008 for reallocation to other RO projects or release to other CARTs as needed

## Slide 7: RO PPL Impacts from Nodal Delay
Nodal COMS Registration and Disputes is still targeting a December 2008 Production Release.
RO Impact:
Environment & Test Resources
  Siebel iTEST Code Freeze expected from 09/02/2008 – 12/13/2008
  Average Project Lifecycle is 10-12 months.
Projects expected to start in 2008:
PR80027_01: Advanced Metering (PRR766)
  Initiate August after Board Approval
PR80031_01: Retail Application Upgrades
  Initiate in 2008 based on data model, performance, and integration recommendations from Oracle/Siebel.

## Slide 8: Questions / Contact
Hope Parrish
Manager, MO DPO
Market Operations Divisional Projects Organization
ERCOT
(512) 248-6522
hparrish@ercot.com