## Slide 1
Audit Preparation

## Slide 2
September 8 – 12, 2008 ERCOT will be audited as the
 Reliability Coordinator (RC)
 Transmission Operator ( TOP)
 Balancing Authority (BA) and
 Transmission Service Provider (TSP)

## Slide 3: Logistics
● 13 auditors (4 NERC, 5 TRE)
4 FERC observers
● Two interviewing groups running concurrently: Tue – Thur noon.
● Operations floor interviews scheduled for Thur afternoon
● Additional SME’s onsite from ONCOR and TMPA (at the request of NERC)

## Slide 4
Definitions and Acronyms
CMEP – Compliance Monitoring and Enforcement Program
RSAW – Reliability Standard Audit Worksheet
OSD – Operating Standards Department
SME – Subject Matter Expert

## Slide 5
OVERVIEW OF PREPARATIONS
Developed the matrix
Answer RSAWs and Questionnaires

## Slide 6: Developing the matrix
Map ERCOT to NERC
First meeting – June 30th of 2007
Last meeting – April 11th of 2008
~30 meetings with market participants
6 ROS presentations and
1 presentation to TAC by ROS Chair

## Slide 7: RSAW Action Plan
● 94 FERC approved NERC Reliability Standards
● 57 standards in 2008 CMEP with RSAWs
● Divided by Operations, Planning, and Security
● Broken into 9 weekly packages
began on May 15, 2008
final sent out July 15, 2008.

## Slide 8: RSAW Action Plan(cont)
● Assigned to SME
 Utilized the matrix with references
 2007 Audit Responses were reviewed
● OSD reviewed evidence and resolved with SMEs
● Management review

## Slide 9: Current Status 8/11/08
 97% (36 out of 37) RSAW’s have been completed by SME’s
 78%(about 29 out of 37)RSAW’s have been resolved with SME’s
 69%(99 out of 143)action items have been completed.
 100% response on 4 questionnaires received

## Slide 10: Remaining Schedule
● Work with Market Participants scheduled to provide support
● Review FERC approved NERC Reliability Standards not on CMEP
● Review Board approved NERC Standards
● Two training sessions will be provided to SME’s

## Slide 11
Questions
?
?