## Slide 1: PMO Update to PRS
Troy Anderson
ERCOT Program Management Office
August 21, 2008

## Slide 2: PMO Update - Agenda
  NPRR Impact Analysis Update
  YTD Project Spending Update
  Recent Project Implementations
    July

## Slide 3: PMO Update - NPRR Impact Analysis Update
The work on the revised Nodal project schedule has limited our ability to complete NPRR Impact Analyses on schedule
  Critical path schedule work is top priority
  Some projects are dependent on detailed designs being completed by other projects
  We are doing our best to keep impact assessment moving forward
  We hope to complete IAs for the following NPRRs by September 2008:
    NPRR102 Implementation of PUC R. 25.505(f) Publication of Resource & Load Info
    NPRR113 Load Resource Type Indicator for Ancillary Service (AS) Trades and Self-Arranged AS
    NPRR124 Resource Node Updated Definitions
    NPRR128 Combined Cycle Power Blocks with Multiple Voltage Instructions
    NPRR131 Ancillary Service Trades with ERCOT
    NPRR134 Section 7 Cleanup, PRR761, Inadvertent Energy Account Revision

## Slide 4: 2008 Project Spending Update – 8/11/2008
CART | Initial Budget | Current Budget | Spending Forecast
CO | $ 8,450,000 | $ 4,728,205 | $ 5,180,147
IO | $ 6,400,000 | $ 6,400,000 | $ 6,102,810
MO | $ 1,200,000 | $ 1,200,000 | $ 1,129,097
RO | $ 6,100,000 | $ 3,830,000 | $ 3,004,819
SO | $ 50,000 | $ 1,071,795 | $ 1,025,323
Nodal / Zonal Interdependent | $ 5,314,000 | $ 6,715,130 | $ 6,715,130
Released but Not Reallocated | $ 0 | $ 3,568,870 | $ 0
Total | $ 27,514,000 | $ 27,514,000 | $ 23,157,326
CO – Met Center * | $ 0 | $ 6,232,880 | $ 5,992,163
* Met Center project is not funded by initial project budget allocation
Arrows indicate trend since last report (June 2008)

## Slide 5: PMO Update - YTD 2008 Project Implementations
January 2008
  IO PR-70050_01 EIS ETL Tool Implementation
February 2008
  CO PR-70044_01 MET Center Facility Analysis
  RO PR-70005_01 MO SAS70 Procedures Optimization
  IO PR-70012_01 Cyber Security Project #14
  IO PR-70037_01 OC-3 Microwave Replacement
  SO PR-70035_01 2007 REC Program Modifications
March 2008
  IO PR-60055_01 Enterprise Service Management
  IO PR-60013_01 Enhanced Digital Certificate Program
  MO PR-70038_01 ERCOT.com Infrastructure Enhancement
        (Collage Infrastructure Redesign)
  CO PR-70013_01 Corporate Document Management
  CO PR-70041_01 Taylor Control Room Display System Replacement
April 2008
  None

## Slide 6: PMO Update - YTD 2008 Project Implementations (cont’d)
May 2008
  MO PR-70048_01 MV90xi System Upgrade
  CO PR-70053_01 Video Teleconferencing
  IO PR-70055_01 Additional Production SAN Capacity
June 2008
  MO PR-60077_01 ERCOT.com Registered Area
  IO PR-70030_01 Tellabs DCCS System Replacement
  IO PR-80022_01 Additional SAN Capacity for Projects
July 2008
  RO PR-60008_01 Terms and Conditions & Performance Measures
  CO PR-70023_01 CyberSecurity Project #2
  CO PR-70047_01 Corporate Application Environment True-Up
  CO PR-80010_01 Ruby Standardization
  CO PR-60073_01 eRecruiting