Texas Nodal Market

Single Entry Model Go-Live Procedure

v0.05

Revision History

| Date | Version | Description | Author |
| --- | --- | --- | --- |
| 05/25/2008 | 0.01 | Initial Draft | Network Modeling Group and EDS team |
| 05/30/2008 | 0.02 | Consideration of internal and NDSWG comments | Network Modeling Group and EDS team |
| 6/3/2008 | 0.03 | Consideration of 2nd round of internal comments | Network Modeling Group and EDS team |
| 6/29/2008 | 0.04 | Consideration of NDSWG comments for the review period ending June 11, 2008 | Network Modeling Group and EDS team |
| 7/17/2008 | 0.05 | Consideration of 3rd round of internal comments | NMMS and EDS team |

Table of Contents

1.0	Introduction	4

2.0	Timeline	4

3.0	Pre Single Entry Model Go-Live	5

3.1	ERCOT responsibilities	5

3.1.1	ERCOT Network Model Validation	5

3.1.2	Translation of outstanding Service Requests to NOMCRs	6

3.1.3	Training	7

3.1.4	SEM Go-Live sequence	7

3.1.5	Network modeling documents	7

3.2	TSP responsibilities	7

3.3	Resource Entity (RE) Responsibilities	8

4.0	Single Entry Model Go-Live	8

5.0	Network Model Synchronization	9

5.1	ERCOT Responsibilities	9

5.2	TSP Responsibilities	9

5.3	RE Responsibilities	10

6.0	Transition to Nodal Protocol § 3	10

6.1	ERCOT Responsibilities	10

6.2	TSP Responsibilities	11

6.3	RE Responsibilities	11

7.0	Issue Resolution	11

8.0	Communications	11

# 1.0	Introduction

As the NOMCR process Early Delivery Systems testing nears completion, ERCOT shall prepare for implementation of the Single Entry Model (SEM) for Market Participants.   Single Entry Model Go-Live is the deployment of the nodal NMMS application, along with an ERCOT validated Network Operations Model into ERCOT’s production environment for use by ERCOT and Market Participants.  Network Operations Model maintenance for both zonal and nodal, shall transition to NMMSafter SEM Go-Live. Upon completion of Network Model Synchronization activities described in Section 5.0 below, the appropriate subsections of Nodal Protocol § 3 identified in the Nodal Protocol Transition Plan (available at http://nodal.ercot.com/about/po/sch/index.html) shall become effective . This procedure describes a coordinated plan of actions between ERCOT and Market Participants leading up to SEM Go-Live and subsequently until the Texas Nodal Market Implementation Date (TNMID).

The purpose of the activities outlined in this procedure is to ensure the successful transition (non-disruption of both existing Zonal and Nodal EDS during transition?) of Network Model maintenance from zonal to nodal and to provide a means of updating zonal system with model changes between SEM Go-Live and the Go-Live Period.  ERCOT staff and Market Participants must work closely together to successfully transition to nodal while minimizing risk and maintaining accuracy in ERCOT’s models.

# 2.0	 (Sequence of Transition Tasks?)

The following  steps are necessary to implement the SEM Go-Live.    The actual dates for the different activities shall be published when the Nodal Program publishes the revised Nodal Go-Live and the SEM Go-Live dates.

Task Sequence

ERCOT completes EDS 2 Release 4 testing

ERCOT conducts performance test of NMMS

ERCOT completes Data Consistency Check

ERCOT completes Rules Validation Activities

ERCOT model baselined for SEM Go-Live

ERCOT publishes Validation Rules

ERCOT publishes Modeling Guidelines document

ERCOT opens NMMS integrated with MPIM for TSP testing

TPTF approves SEM Go-Live

TAC approves SEM Go-Live

BOD approves SEM Go-Live

NMMS application and ERCOT validated Network Operations Model deployed to Production environment

TSPs confirm model validation complete

First Notice to Market Participants for enabling sub-sections of Nodal Protocol § 3 outlined in Nodal Protocol Transition Plan

Second Notice to Market Participants for enabling Nodal Protocol § 3

ERCOT enables Nodal Protocol § 3

ERCOT seeks TPTF approval for model to be used for TNMID in accordance with ERCOT Nodal Transition Plan § 5.1 (3)

Which activity corresponds to SEM Go-Live? “NMMS App… deployed to Production..?”

What does “ERCOT Model Baselined ..” mean for a TDSP? Would TDSPs know cut-off dates for S/Rs, that are included, would the CIM Schema be finalized?

Prior to the start of the SEM Go-Live date, the Market Participant User Security Administrator (MP USA) shall enter/validate roles for Market Participant employees into the nodal Market Participant Identity Management system (MPIM) to ensure access to nodal NMMS system.  Market Participants shall be responsible for testing roles of their employees at the beginning of the SEM Go-Live Period.  (I am not sure where this paragraph falls into the sequence of activities.  Should this be identified in the sequence of Activities above as a line item?  Otherwise should this paragraph be relocated to sections 3.2 and 3.3 - MP Responsibilities?  )

# 3.0	Pre Single Entry Model Go-Live

The objective of activities prior to SEM Go-Live is to ensure that both ERCOT and Market Participants have a common understanding of the quality of the Network Operations Model that shall be loaded into the NMMS application upon SEM Go-Live and to ensure that Market Participants are capable of verifying the Network Operations Model immediately after SEM Go-Live.  Does ERCOT need to also establish temporary business processes for the following activities?

- Managing Zonal model update during the transition period.

# 3.1	ERCOT Responsibilities

Prior to SEM Go-Live, ERCOT shall focus on validating the nodal Network Operations Model in CIM format and on provide training to TSPs that addresses how to perform model validation activities after SEM Go-Live.  The following sections of the document detail key ERCOT activities leading up to SEM Go-Live.

## 3.1.1	ERCOT Network Model Validation

The purpose of the Network Model Validation effort is to ensure that the nodal Network Operations Model is consistent with or better than the zonal Network Operations Model.

The first step in the Network Model Validation process is the CIM audit, which shall ensure that the modeling requirements of all Nodal systems are incorporated in the CIM format of the Network Operations Model.  The CIM audit shall include review of the data, classes, associations and attributes of all downstream systems that require data from the Network Operations Model to identify gaps in the CIM format of the Network Operations Model.  The necessary change requests for the CIM schema are prepared and processed, resulting in a CIM schema that includes all necessary data, classes, associations, and attributes.  Upon completion of the CIM audit, the CIM schema shall be considered as the baseline for SEM Go-Live.

What is MP involvement in future (post SEM Go-Live) changes to CIM Schema?

Once the CIM audit is complete, ERCOT shall conduct a Data Consistency Check and implement a rules based validation on the Network Operations Model.  The objective of the Data Consistency Check is to jump-start the nodal model building process by leveraging as much of the zonal model as possible (You may need to reword or delete.  The objective is also restated in the next sentence.) to pre-populate (seed) NMMS.  By conducting the Data Consistency Check, ERCOT shall also ensure consistency of model data between zonal and nodal, and provide for comparison of application results between Zonal and Nodal EMS systems.  The Data Consistency Check shall begin after the Nodal EMS CIM Importer has completed FAT and any defects that may impact the Data Consistency Check have been resolved.  For the Data Consistency Check, ERCOT shall upload the zonal “seed” model into the NMMS tool and execute a three-way database comparison between zonal Savecases, nodal Savecases generated through conversion scripts on zonal Savecases and nodal Savecases generated through the EMS CIM importer.  The results of this comparison shall ensure that nodal and zonal network model data are similar.  Once the database comparison is complete, ERCOT shall execute an application comparison between zonal and nodal by comparing the results of zonal and nodal EMS systems.  Application comparison shall ensure that nodal EMS system can execute on the nodal Network Operations Model in CIM format and produce results that are similar to, or better than, the zonal EMS system.  Once the Data Consistency check is complete, ERCOT shall publish a summary report on Nodal Readiness Center, identifying the health of the CIM Network Operations Model structure and readiness.

ERCOT shall also design, implement and test manual and automated rules based validations in the NMMS system.  ERCOT shall publish the Validation Rules document for Market Participant review prior to implementing the rules in the NMMS application. (The process for creating validation rule is expected to be long.  This activity should be independent of the data consistency checks.)

Upon completion of the ERCOT model validation activities and with approval from the Director of System Operations and the Director of Market Operations, the Network Operations Model shall be deemed as the Baseline Model to be used in the NMMS production system upon SEM Go-Live.

Would ERCOT model validation activities include data input by TDSP?  This will provide and an independent source for input data to NMMS that need to be addressed prior to SEM Go-Live?

## 3.1.2	Translation of outstanding Service Requests to NOMCRs

Any outstanding Service Requests that have not been included in the seed nodal Network Operations Model for SEM Go-Live shall be converted to an XML file and sent to the responsible TSP for verification and submittal to the NMMS application.   After SEM Go-Live, any outstanding Approval to Energize activities (i.e. closure of the Service Request using the Approval to Energize process) shall require a new NOMCR to be submitted by the Market Participants with reference to the Approval to Energize Service Request number.

## Training

ERCOT shall provide the necessary application and NOMCR process training and documentation to enable the TSPs to conduct model verification upon SEM Go-Live.  Such activities shall follow the timelines as mutually agreed upon by ERCOT and Market Participants as part of Early Delivery Systems 2 (EDS 2 Release 4).

(To avoid the disclaimers, this should be deleted.)

    - SEM Go-Live sequence

Upon completion of the model validation activities listed in Section 3.1.1 of this procedure, ERCOT shall begin the SEM Go-Live sequence.  The SEM Go_Live sequence is the sequence of activitites starting from “ERCOT Baseline …” till “NMMS ..in Production System.”  In accordance with Zonal Protocol § 21.12.3 ERCOT shall seek certification from TPTF, TAC and ERCOT BOD for proceeding with SEM Go-Live.    Upon certification, ERCOT shall issue two Notices alerting Market Participants of the SEM Go-Live date.  The First Notice shall be issued at least thirty (30) days prior to the SEM Go-Live date and the Second Notice shall be issues ten (10) days prior to the SEM Go-Live date.  (Nodal protocol implementation??)

This description appears to contradict the table in 2.0.  SEM GO-Live is an event that will happen prior to MP Model synchronization. TPTF and BOD certification is required.  However, transition to Nodal protocol will happen post SEM and TSP validation (see the sequence of activities in 2.0,)  The market notices are to happen following MP Model synchronization; and will serve as a notice for change in market protocol.

## 3.1.5	Network Modeling documents

Prior to SEM Go-Live, ERCOT shall post the following documents on the Nodal Readiness Center (http://nodal.ercot.com/readiness/eds2/documents/index.html)

    - ERCOT Network Operations Model validation whitepaper

    - NMMS Modeling Guidelines document

    - NMMS Validation Rules document

    - CIM Data Dictionary and Schema

3.2	TSP responsibilities

Prior to SEM Go-Live, TSPs should ensure that relevant personnel are trained on the NMMS application and NOMCR business processes such that TSPs can begin Network Model verification immediately after SEM Go-Live.  TSPs should conduct the following activities before SEM Go-Live:

Training:  Prior to SEM Go-Live, TSPs should ensure that relevant personnel are trained on the NMMS tool and NOMCR business processes as part of EDS 2 Release 4 testing.  TSPs are strongly encouraged to continue using the NMMS sandbox environment for testing the NOMCR business process prior to SEM Go-Live.  SEM Go-Live shall not occur until all TSPs have met the exit criteria for EDS 2 Release 4 testing.  TSPs are encouraged to contact the EDS team if they require additional training on the NMMS application prior to SEM Go-Live

(Do you need to add the MP USA – Security Administration activity here?)

- .

Document review:

- TSPs should familiarize themselves with the CIM schema of the Network Operations Model and other Network Modeling documents posted on the Nodal Readiness Center -http://nodal.ercot.com/readiness/eds2/documents/index.html.

- Internal processes and tools:  Prior to SEM Go-Live, TSPs should consolidate their internal processes and tools to implement the Nodal Protocols and for Network Model verification and management.  This activity is critical to ensure that TSPs can begin the Network Model verification immediately after SEM Go-Live.

- Sample NOMCR submissions: TSPs are encouraged to submit sample NOMCRs in CIM format to the EDS team (NetworkModelCoordinators@ercot.com) as this will enable ERCOT in its model validation activities.

- Service Requests:

  - (Is ERCOT Suggesting TDSPs validate the Zonal model prior to Nodal transition?)

  - TSPs should be diligent in reviewing outstanding Approval to Energize changes and submit Service Requests as appropriate to ensure that the seed model is accurate.

  - Prior to the ERCOT Network Model Validation tasks, outlined above in section 3.1.1, TSPs should submit Service Requests in advance of the zonal required timeline, when possible (How much lead-time does ERCOT neeed). This will limit the number of post SEM Go-Live NOMCRs that need to be processed to get the Nodal Model re-synchronized with zonal.

  - Note that the ERCOT validation efforts will be done using ‘point-in-time’ data sets.  That is, the zonal network model is updated every two weeks and the seed model will be based on one of these point-in-time models.

# 3.3	Resource Entity (RE) Responsibilities

REs are requested to review all topology data and equipment parameters in conjunction with completion of Readiness Metric MP10.  RARF data submissions must be complete and accurate to be implemented in the model used for SEM Go-Live.  For entities not meeting the requirements the nodal model shall use the existing zonal information of their respective Transmission Facilities.

(Do you need to add the MP USA – Security Administration activity here?)

# 4.0	Single Entry Model Go-Live

Upon ERCOT declaring SEM Go-Live, Market Participants should start the process of synchronizing their in-house Network Model with the ERCOT Network Operations Model.

Upon SEM Go-Live, the NMMS tool shall be managed as if the system were fully in production, exercising the same procedures used for zonal production operations to implement software updates and accommodate possible new nodal procedures for software updates.  After SEM Go-Live, any changes being implemented to the NMMS tool that affect Market Participants shall be notified through a Market Notice at least ten (10) days prior to implementing the change in the production environment.

The following entry criteria shall be met for SEM Go-Live

- ERCOT completes EDS 2 Release 4 activities

- All TSPs complete EDS 2 Release 4 activities

- Nodal network model validated and approved as baseline for SEM Go-Live by ERCOT System Operations and Market Operations Directors

- ERCOT publishes CIM model to be used for SEM Go-Live

- ERCOT sufficiently staffed for maintenance of both nodal and zonal systems

- Nodal EMS is capable of consuming NMMS CIM files through the EMS CIM importer for use in the Nodal EMS application suite

- SEM Go-Live readiness approved by TPTF, TAC and ERCOT BOD

- ERCOT publishes the following documents for TSPs

  - ERCOT Network Operations Model validation whitepaper

  - ERCOT Network Operations Model validation results

  - NMMS Modeling Guidelines document

  - NMMS Validation Rules document

  - Latest CIM data dictionary and schema

# 5.0	Network Model Synchronization

After SEM Go-Live, ERCOT shall ensure that TSPs have sufficient time to synchronize the Nodal Network Operations Model  with the TSP’s native model databases, before transitioning to relevant sub-sections of the Nodal Protocol § 3.  The duration of the transition period will be mutually agreed upon by ERCOT and TSPs, and shall be approved by TPTF.  During the transition period, TSPs should submit NOMCRs to the NMMS tool to ensure that the ERCOT network model is synchronized with the TSPs’ production model.  During this period, ERCOT and TSPs shall follow the timelines and business processes as outlined in Nodal Protocol § 3.10 for model change requests.  (For new projects,timeline will be based on prevailing protocol at the time the project is submitted to NMMS.  For synchronization changes ERCOT and TDSP need to reach a mutually agreeable time line for processing changes.)

# 5.1	ERCOT Responsibilities

After SEM Go-Live, ERCOT shall be responsible for processing NOMCRs as outlined in the Nodal Protocol § 3.10.  ERCOT shall make efforts to process NOMCR in an expedited fashion during the transition period.  In addition, ERCOT shall be responsible for transposing the NOMCRs into zonal Service Requests and for updating the zonal model with topological and parameter changes submitted using the NMMS tool.  Name changes made in the NMMS shall be updated on a very limited basis at the discretion of ERCOT staff into the zonal model because of the nature of the zonal EMS system.  Changes that do not require cascading deletes of entire modeling structures may be accommodated.

ERCOT shall begin posting of all NOMCRs submitted to ERCOT within five (5) Business Days of receipt, as required by Nodal Protocol § 3.10 (8).   In addition, any accepted changes to NOMCRs shall be posted on the nodal MIS within three (3) Business Days of accepting the change. ERCOT shall also post Network Operation Models according the timelines listed in Nodal Protocol § 3.10.1.  All information will be posted on the nodal MIS Secure Area as required by the Nodal Protocols.

Additionally, the Network Modeling Group at ERCOT shall work with CRR and Planning personnel to meet further requirements necessary before Nodal Go-Live.

In addition, ERCOT shall continue to train Market Participants when requested on the NMMS tool and nodal business processes during this period.

# 5.2	TSP Responsibilities

The objective of TSP efforts during the transition period should be to meet the Nodal Protocol and ERCOT Nodal Transition Plan requirements for TSP data submittal of Transmission Elements, and to maintain high fidelity and consistency in ERCOT Nodal Network Operations Model by synchronizing the ERCOT model to internal TSP operations model.

During this time TSPs shall submit NOMCRs and perform activities as outlined in the Nodal Protocol § 3.10 and  ERCOT Nodal Transition Plan § 5.4.1 (2)

.  In addition, any topological or commercial aspects should be resolved by the TSPs.( What is this?)  .

Each TSP shall communicate to ERCOT once its model synchronization and verification activities are complete to enable ERCOT to plan the transition to the Network Modeling Protocols identified Nodal Protocol Transition Plan.

# 5.3	RE Responsibilities

Any changes to the RARF data or new construction projects shall follow the timelines as outlined in Nodal Protocol § 3.10.

6.0	Transition to Nodal Protocol § 3

# 6.1	ERCOT Responsibilities

Once all TSPs have communicated to ERCOT that they have completed the activities listed in Section 5.2 of this procedure, ERCOT shall begin the approval sequence for transition to Network Modeling Protocols identified in Nodal Protocol Transition Plan.  In accordance with Zonal Protocol § 21.12.3 ERCOT shall seek certification from TPTF, TAC and ERCOT BOD for transitioning to Nodal Protocols for Network Model Maintenance.  Upon certification, ERCOT shall issue two Notices alerting Market Participants of the transition date.  The first Notice shall be issued at least thirty (30) days prior to the transition date and the second Notice shall be issues ten (10) days prior to the transition date.

# ERCOT shall continue to transpose the NOMCRs into zonal Service Requests and update the zonal model with topological and parameter changes made into the nodal NMMS application.  Name changes made in the nodal NMMS shall be updated on a very limited basis into the zonal model because of the nature of the zonal EMS system.  The nodal model from NMMS shall be used in the nodal EMS system throughout the duration of the test.   In accordance with ERCOT Nodal Transition Plan § 5.1 (3), ERCOT shall seek approval for the Network Operations Model to be used upon TNMID.

In addition, ERCOT shall continue to train TSPs when requested on the NMMS tool and nodal business processes during this period.

# 6.2	TSP Responsibilities

Upon transition to Nodal Protocols, TSPs shall continue to support ERCOT in managing the Network Operations Model. TSPs shall use the NOMCR process to communicate model changes to ERCOT following the timelines outlined in Nodal Protocol § 3.10

6.3	RE Responsibilities

Upon transition to Nodal Protocols for Network Model maintenance, REs shall continue to support ERCOT in managing the Network Operations Model following the timelines outlined in Nodal Protocol § 3.10.  REs should ensure that all near term construction projects are submitted to ERCOT within adequate timelines to be entered at NOMCR requests into the NMMS tool throughout the duration of the 168-Hour test and the Go-Live Period.

# 7.0	Issue Resolution

The following table shall be used as a guideline by Market Participants to report any defects or issues encountered throughout this period.

|  | Questions, issues with NMMS | Questions, issues related to zonal | Change to Network Operations Model can be submitted by |
| --- | --- | --- | --- |
| Pre SEM Go-Live | NetworkModelCoordinators @ercot.com | NetworkModelCoordinators @ercot.com | Service Request |
| After SEM Go-Live, during transition to Nodal Protocols | NetworkModelCoordinators @ercot.com | NetworkModelCoordinators @ercot.com | NOMCR |
| After transition to Nodal Protocols for Network Model maintenance | NetworkModelCoordinators @ercot.com | NetworkModelCoordinators @ercot.com | NOMCR |

# 8.0	Communications

ERCOT shall conduct periodic Market calls to inform Market Participants of the progress towards key milestones such as SEM Go-Live and Transition to Nodal Protocol § 3, newly discovered problems and resolutions to previously announced issues.   ERCOT shall post to the Quality Center on Nodal Readiness center, within a reasonable time after receiving notice of an issue, a summary of all outstanding software and hardware issues related to SEM Go-Live.