## Instructions
Document Title: EDS SLA Metrics and Detailed Incident Log Reporting
Version: 1.2
Document Definition:
This document contains monthly and YTD availability metrics, planned outage summaries and incident details for ERCOT Nodal EDS environment
Spreadsheet Tab: | Contents:
Current Month Av | This tab contains Current Month availabilities for Nodal EDS infrastructure, applications and services as specified in the EDS environment Service Level Agreement.
YTD Av | This tab contains YTD availabilities for Nodal EDS infrastructure, applications and services as specified in the EDS environment Service Level Agreement.
Detailed Incident Data: | This tab contains the detailed information regarding each IT incident related to Nodal applications and services for which monitoring has begun. Incident data is entered in a "running list", seperated by each month.
Plnd Outages | This tab contains the detailed information regarding each planned outage related to Nodal applications and services for which monitoring has begun. Planned outages are entered in a "running list", seperated by each month.
Instructions for filling in the 'Detailed Incident Data' worksheet
Column Name | Instructions:
Month | Month during which the incident occurred
Market Notice Date | Date Market Notification regarding the incident was sent
Notification ID | Market Notification ID, if any
Issue Start Date & Time | Issue start date and time
Issue End Date & Time | Issue end date and time
Issue Duration (Minutes and Seconds) | Duration = Issue end date and time - Issue start date and time. Issue duration need not be the same as 'SLA Item Outage Duration' (see below), since not all issues may result in outages. Note: Precision by seconds is applicable only for very high-availability applications
Nodal Application Impacted | Name of the high-level Nodal applications that are impacted due to the issue (Example: EMS, MMS, MIS, NMMS etc)
SLA Item Impacted (Refer to EDS SLA) | Name of the impacted Application / Service / Infrastructure component as defined in the EDS SLA for monitoring and reporting purposes.
SLA Item Outage Duration (Minutes and Seconds) | Outage duration of the SLA item in minutes. This need not the same as Issue Duration, since not all issues may result in outages. The values in this column are used in calculating Availabilities for SLA Metrics reporting purposes. Note: Precision
Issue Description | Description of the issue as observed
Root Cause Details | Description of the root cause of the issue as diagnosed
Market Impact | Description of the impact to the Market Participants due to the issue.
Resolution | Description in brief of the technical resolution
Date (to be implemented) | The date of resolution. If pending, shows expected date of resolution
Notes | Additional notes, if any
Current Status | Provides status of Root Cause resolution as of the date of the completing / updating this worksheet. Note: Root Cause resolution need not be the same as issue resolution, since issue can resolved by temporary workarounds.
Glossary of Terms
Term | Definition:
Incident | Any event that causes the service level or performance of ERCOT IT systems to be impacted
SLA Item | Application / Service / Infrastructure component as defined in the EDS SLA for monitoring and reporting purposes.
Degradation | An event that causes the normal levels of ERCOT IT systems to be impacted while still allowing for minimal processing of or access to these systems
Planned Outage | A planned change in ERCOT IT systems that prevents users from being able to access the systems
Unplanned Outage | An unplanned change or incident related to ERCOT IT systems that prevents users from being able to access the systems
Gross minutes | Total minutes in a month
Net minutes | Gross minutes minus planned outage minutes
Planned outage minutes | Minutes used by ERCOT during the maintenance and release windows
Unplanned outage minutes | Duration of time during which a services was not available outside of the used planned maintenance and release windows. Duration can also include seconds for very high availability applications.
Exception outage minutes | Minutes outside of the maintenance and release outage windows that have been granted exception from the availability metric for SLA reporting purposes
Service availability percent | The percent of time that a services was available, after discounting for planned outage minutes
High-Level Root Causes
Software | An incident caused by software bugs
Database | An incident caused by a database outage or issue
Infrastructure | An incident caused by an IT infrastructure failure (server, switch, etc…)
Human Error | An incident caused by human error
Other | An incident that is not described by another defined incident type
High-Level Impacts
Availability | The ability of a component or IT service to perform its required function over a stated period of time
Timeliness | A service impact resulting in noncompliance of delivery time requirements of data output, as specified in Protocols or Market Guides
Completeness | A service impact resulting in noncompliance of content requirements of data output, as specified in Protocols or Market Guides
Accuracy | A service impact resulting in noncompliance of accuracy requirements of data output, as specified in Protocols or Market Guides
Slow System Performance | A service impact resulting in abnormally slow or delayed response to Market Participant queries

## Current Month Av
Current Month Availabilities of Nodal Infrastructure and Applications
Month: Example, 2008
Month | Gross Available Minutes | Planned Outage Minutes | Net Available Minutes | Unplanned Outage Minutes | Percent Availability | Availability Target | Notes
EDS H/W Infrastructure | [5 empty] | 98%
EMS
§ ICCP | [5 empty] | 100%
§ State Estimator Network Topology Builder Bus Load Forecast | [5 empty] | 98%
§ Alarm Processor | [5 empty] | 98%
§ Forced Outage Detection | [5 empty] | 98%
§ LFC | [5 empty] | 98%
§ Network Security Analysis | [5 empty] | 98%
§ Dynamic Ratings Processor | [5 empty] | 98%
§ Transmission Constraint Management | [5 empty] | 98%
§ Topology Consistency Analyzer | [5 empty] | 98%
§ AS Capacity Monitoring | [5 empty] | 98%
§ Resource Limit Calc | [5 empty] | 98%
§ Load Forecasting | [5 empty] | 98%
§ Archiving application | [5 empty] | 98%
§ SESTAT | [5 empty] | 98%
§ Market Operations Test Environment (MOTE) | [5 empty] | 98%
§ Voltage and Stability Analysis | [5 empty] | 98%
§ Outage Evaluation | [5 empty] | 98%
Wind Forecast | [5 empty] | 98%
MMS
§ DAM | [5 empty] | 98%
§ SASM | [5 empty] | 98%
§ RUC | [5 empty] | 98%
§ CCT | [5 empty] | 98%
§ SCED | [5 empty] | 98%
Web Services | [5 empty] | 98%
MIS
§ MIS Portal | [5 empty] | 98%
§ LMP Contour Map | [5 empty] | 98%
§ MMS UI | [5 empty] | 98%
§ Reports Explorer | [5 empty] | 98%
§ Extracts Scheduler | [5 empty] | 98%
§ Market Participant Notifications | [5 empty] | 98%
MPIM | [5 empty] | 98%
Current Day Reports | [5 empty] | 98%
Outage Scheduler | [5 empty] | 98%
NMMS | [5 empty] | 98%
CRR | [5 empty] | 98%
Settlements & Billing | [5 empty] | 98%
CMM | [5 empty] | 98%
Financial Transfer | [5 empty] | 98%

## YTD Av
YTD Availabilities of Nodal Infrastructure and Applications
Effective: September, 2008 - December, 2008
Month | Gross Available Minutes | Planned Outage Minutes | Net Available Minutes | Unplanned Outage Minutes | Percent Availability | Availability Target | Notes
EDS H/W Infrastructure | [5 empty] | 98%
EMS
§ ICCP | [5 empty] | 100%
§ State Estimator Network Topology Builder Bus Load Forecast | [5 empty] | 98%
§ Alarm Processor | [5 empty] | 98%
§ Forced Outage Detection | [5 empty] | 98%
§ LFC | [5 empty] | 98%
§ Network Security Analysis | [5 empty] | 98%
§ Dynamic Ratings Processor | [5 empty] | 98%
§ Transmission Constraint Management | [5 empty] | 98%
§ Topology Consistency Analyzer | [5 empty] | 98%
§ AS Capacity Monitoring | [5 empty] | 98%
§ Resource Limit Calc | [5 empty] | 98%
§ Load Forecasting | [5 empty] | 98%
§ Archiving application | [5 empty] | 98%
§ SESTAT | [5 empty] | 98%
§ Market Operations Test Environment (MOTE) | [5 empty] | 98%
§ Voltage and Stability Analysis | [5 empty] | 98%
§ Outage Evaluation | [5 empty] | 98%
Wind Forecast | [5 empty] | 98%
MMS
§ DAM | [5 empty] | 98%
§ SASM | [5 empty] | 98%
§ RUC | [5 empty] | 98%
§ CCT | [5 empty] | 98%
§ SCED | [5 empty] | 98%
Web Services | [5 empty] | 98%
MIS
§ MIS Portal | [5 empty] | 98%
§ LMP Contour Map | [5 empty] | 98%
§ MMS UI | [5 empty] | 98%
§ Reports Explorer | [5 empty] | 98%
§ Extracts Scheduler | [5 empty] | 98%
§ Market Participant Notifications | [5 empty] | 98%
MPIM | [5 empty] | 98%
Current Day Reports | [5 empty] | 98%
Outage Scheduler | [5 empty] | 98%
NMMS | [5 empty] | 98%
CRR | [5 empty] | 98%
Settlements & Billing | [5 empty] | 98%
CMM | [5 empty] | 98%
Financial Transfer | [5 empty] | 98%

## Detailed Incident Data
ERCOT Nodal EDS IT Incident Summary
Effective: June 2008 - December 2008
Month | Market Notice Date | Issue Start Date & Time | Issue End Date & Time | Issue Duration (Hours/Mins/Secs) | Nodal Application Impacted | SLA Item Impacted (See Instructions) | SLA Item Outage Duration (Hrs/Mins/Secs) | Issue Description | Root Cause Details | Market Impact | Resolution | Date (to be) Implemented | Notes | Current Status
Example | 2008-07-09 | 2008-07-09 20:02 | 2008-07-09 20:12 | 0:10 | MMS | SCED | 0:10 | Market database is down. | Market Database is down due to node eviction. | Interval of 10 minutes was lost | An Oracle patch has been deployed for EDS MMS and same patch will be deployed to EDS EMS. | 2008-07-11 | N/A | Complete - Green status
June | 2008-06-12 | 2008-06-12 01:15 | 2008-06-12 07:55 | 6:40 | MMS | SCED | 6:40 | Market database is down. | Market Database is down due to node eviction. | Interval of 400 minutes was lost | Database is restarted. | 2008-03-12 | N/A | Oracle is looking into the problem
June | 2008-06-13 | 2008-06-12 17:30 | 2008-06-13 19:30 | 26:00 | EMS | SE, LFC | 26:00 | Problems exist after the fail over. SE is not getting a valid solution. | Settings under SE initial conditions have been changed during the migration. | N/A | Rechecked the flag under SE initial conditions. | 2008-06-13 | N/A | Complete - Green status
June | 2008-06-19 | 2008-06-19 23:40 | 2008-06-19 23:58 | 0:18 | MMS | SCED | 0:18 | Market database is down. | Market Database is down due to node eviction. | Interval of 18 minutes was lost | Database is restarted. | 2008-06-19 | N/A | Oracle is looking into the problem
June | 2008-06-26 | 2008-06-26 16:07 | 2008-06-26 16:32 | 0:25 | MMS | SCED | 0:25 | Market database is down. | Market Database is down due to node eviction. | Interval of 25 minutes was lost | Database is restarted. | 2008-06-26 | N/A | Oracle is looking into the problem
June | 2008-06-26 | 2008-06-26 22:07 | 2008-06-27 05:18 | 7:11 | MMS | SCED | 7:11 | Telemetry was lost. | RLC CC validation feature was disabled to avoid 100,000$/MWhr LMP and also to investigate why SCED was not dispacthing all CC plant physical units. | Interval of 430 minutes was lost | Flag was enabled in RLC and next ems database load will fix the inconsistencies in EMS and MMS with available CCCFGNO for each CC plant. | 2008-07-01 | N/A | Will be completed with next model push.
July | 2008-07-02 | 2008-07-02 00:07 | 2008-07-02 05:17 | 5:10 | MMS | SCED | 5:10 | Telemetry was lost. | SCED did not dispacthed all CC plant physical units. | Interval of 310 minutes was lost | Need to get the EMS and MMS databases in sync. | 2008-07-05 | N/A | Complete - Green status
July | 2008-07-09 | 2008-07-09 20:02 | 2008-07-09 20:12 | 0:10 | MMS | SCED | 0:10 | Market database is down. | Market Database is down due to node eviction. | Interval of 10 minutes was lost | An Oracle patch has been deployed for EDS MMS and same patch will be deployed to EDS EMS. | 2008-07-11 | N/A | Complete - Green status
July | 2008-07-18 | 2008-07-18 02:09 | 2008-07-18 12:45 | 10:36 | EMS | SE | 10:36 | RTNET was stuck. | SCADA fails to supply input to RTNET causing it to hang. | N/A | AREVA is looking into the problem. Currently it is still under investigation. | TBD | N/A | Under investigation.
July | 2008-07-18 | 2008-07-18 02:11 | 2008-07-18 02:21 | 0:09 | EMS | LFC | 0:09 | LFC was stuck. | SCADA fails to supply input to RTNET causing it to hang. This caused LFC to fail. | N/A | AREVA is looking into the problem. Currently it is still under investigation. | TBD | N/A | Under investigation.
July | 2008-07-23 | 2008-07-23 03:08 | 2008-07-23 05:37 | 2:29 | EMS | SE | 2:29 | RTNET was stuck. | SCADA fails to supply input to RTNET causing it to hang. | N/A | AREVA is looking into the problem. Currently it is still under investigation. | TBD | N/A | Under investigation.
July | 2008-07-24 | 2008-07-24 01:08 | 2008-07-24 08:23 | 7:15 | EMS | SE | 7:15 | RTNET was stuck. | SCADA fails to supply input to RTNET causing it to hang. | N/A | AREVA is looking into the problem. Currently it is still under investigation. | TBD | N/A | Under investigation.
July | 2008-07-24 | 2008-07-24 01:21 | 2008-07-24 01:51 | 0:30 | EMS | LFC | 0:30 | LFC was stuck. | SCADA fails to supply input to RTNET causing it to hang. This caused LFC to fail. | N/A | AREVA is looking into the problem. Currently it is still under investigation. | TBD | N/A | Under investigation.
July | 2008-07-24 | 2008-07-24 17:08 | 2008-07-24 17:22 | 0:14 | EMS | SE | 0:14 | RTNET was stuck. | SCADA fails to supply input to RTNET causing it to hang. | N/A | AREVA is looking into the problem. Currently it is still under investigation. | TBD | N/A | Under investigation.
July | 2008-07-24 | 2008-07-24 20:08 | 2008-07-24 21:18 | 1:10 | EMS | SE,LFC | 1:10 | RTNET was stuck. | SCADA fails to supply input to RTNET causing it to hang. | N/A | AREVA is looking into the problem. Currently it is still under investigation. | TBD | N/A | Under investigation.
July | 2008-07-25 | 2008-07-25 16:29 | 2008-07-25 16:34 | 0:05 | EMS | LFC | 0:05 | ERPEMSF failed. | Server failure. | N/A | Windows admin turned on ERPEMSF back online. | N/A | N/A | Complete - Green status
July | 2008-07-30 | 2008-07-30 03:57 | 2008-07-30 08:38 | 4:41 | EMS | SE | 4:41 | OLNETSEQ did not start on ERPEMSG | NETIO communication has been lost between local CFGCTRL and CFGCTRL on ERPEMSF | N/A | System admins are looking into to this issue. | N/A | N/A | Under investigation.

## Plnd Outages
Planned Outage Summary for Nodal applications
April 2008 - December 2008
Month | Planned Outage Begin Time | Planned Outage End Time | Duration (Minutes) | SLA Item Impacted | Market Notice sent? (Y / N) | Market Notice Date | Notes / Comments (If outside weekly scheduled widows, provide details. Per SLA, exceptions allowed only upon Market Notice)
Example | 2008-07-03 10:32 | 2008-07-03 10:57 | 25 | SCED | Y | 2008-07-02 | Applied a database patch to address the instabilities that have been experienced ovet the past weeks. Also LDAP maintenance will be performed to improve site stability.
April | 4/23/2008 16:10 AM | 4/23/2008 16:15 AM | 5 | LFC, SE, SCED |  |  | RLC Patch Migration
April | 4/23/2008 16:35 AM | 4/23/2008 16:40 AM | 5 | LFC, SE, SCED |  |  | RLC Patch Migration failed to standby to verify
May | 2008-05-08 09:01 | 2008-05-08 09:03 | 2 | LFC, SE, SCED |  |  | EMS failover from H to E for memory upgrade OCR30627
May | 2008-05-19 07:30 | 2008-05-19 07:35 | 5 | LFC ,SE, SCED |  |  | Migration and database load
May | 2008-05-30 08:00 | 2008-05-30 01:00 | 5 | LFC, SE, SCED |  |  | Intermittent outages during this time period (replaced ICCP servers)
June | 2008-06-06 08:00 | 2008-06-06 10:56 | 889 | SE |  |  | Production and Operations group both agreed to wait and get Areva to look at the problem with Network Online Sequence getting stuck.
June | 2008-06-10 10:00 | 2008-06-10 12:10 | 25 | LFC, SE, SCED |  |  | Site fail over from Taylor to Austin.
June | 2008-06-12 13:50 | 2008-06-12 16:10 | 140 | SE, SCED | Y | 2008-06-11 | Server fail over from ERPEMSE to ERPEMSF. Also recording definition is updated.
June | 2008-06-12 13:50 | 2008-06-12 16:10 | 10 | LFC | Y | 2008-06-11 | Server fail over from ERPEMSE to ERPEMSF. Also recording definition is updated.
July | 2008-07-02 13:00 | 2008-07-02 13:55 | 55 | LFC | Y | 2008-07-01 | New database load initiated. Fail-over between ERPEMSF and ERPEMSG has occurred.
July | 2008-07-03 10:32 | 2008-07-03 10:57 | 25 | SCED | Y | 2008-07-02 | Applied a database patch to address the instabilities that have been experienced ovet the past weeks. Also LDAP maintenance will be performed to improve site stability.
July | 2008-07-16 13:30 | 2008-07-16 13:35 | 3.8 | LFC | Y | 2008-07-16 | New database load initiated. Fail-over between ERPEMSF and ERPEMSG has occurred.
July | 2008-07-23 04:11 | 2008-07-23 09:51 | 340 | SE | Y | 2008-07-23 | RTNET is hung up. AREVA will implement a code change to fix the problem. It has been left not running intentionally.
July | 2008-07-29 09:19 | 2008-07-29 09:27 | 15 | SCED | Y | 2008-07-29 | SCED base points did not update due to the EDS network ports that were not re-established after a change was made to the network firewalls.
July | 2008-07-31 13:31 | 2008-07-31 13:36 | 4.5 | LFC | Y | 2008-07-29 | New database load initiated. Fail-over between ERPEMSF and ERPEMSG has occurred.