## 2009
| Flight Schedule for Flights | 0209 | 0609 | 1009 | 1008 | 0109 | 0409 | 0709 | 1009 | 0209 | 0609 | 1009 | 1008 | 0109 | 0409 | 0709 | 1009 | 0209 | 0609 | 1009 | 1008 | 0109 | 0409 | 0709 | 1009
|  | Date | Date | Date | Date | Date | Date | Date | Date | Days between Tasks | Days between Tasks | Days between Tasks | Days between Tasks | Days between Tasks | Days between Tasks | Days between Tasks | Days between Tasks | Day of Week | Day of Week | Day of Week | Day of Week | Day of Week | Day of Week | Day of Week | Day of Week
Activity
1 | Notice from ERCOT Retail Client Services of the next flight for Retail Market Testing (strike - Retail Testing Orientation meeting) sent to ERCOT lists.ercot.com distribution | 2008-12-10 | 2009-04-15 | 2009-08-05 | 2008-08-13 | 2008-11-05 | 2009-02-04 | 2009-05-13 | 2009-08-12 | [8 empty] | Wed | Wed | Wed | Wed | Wed | Wed | Wed | Wed
2 | TTPT to finalize scripts | 2008-12-31 | 2009-05-06 | 2009-08-26 | 2008-09-03 | 2008-11-26 | 2009-02-25 | 2009-06-03 | 2009-09-02 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | Wed | Wed | Wed | Wed | Wed | Wed | Wed | Wed
3 | (STRIKE -Market Participant Retail Testing Orientation Meeting – Meeting to inform each testing entity of testing requirements and activities. Mandatory for all Testing Participants.) Testing Worksheets are unlocked. | 2009-01-07 | 2009-05-13 | 2009-09-02 | 2008-09-10 | 2008-12-02 | 2009-03-03 | 2009-06-09 | 2009-09-08 | 7 | 7 | 7 | 7 | 6 | 6 | 6 | 6 | Wed | Wed | Wed | Wed | Tue | Tue | Tue | Tue
4 | FLIGHT DEADLINE | 2009-01-14 | 2009-05-20 | 2009-09-09 | 2008-09-17 | 2008-12-10 | 2009-03-11 | 2009-06-17 | 2009-09-16 | 7 | 7 | 7 | 7 | 8 | 8 | 8 | 8 | Wed | Wed | Wed | Wed | Wed | Wed | Wed | Wed
The following 4 steps must be completed by 5 PM CPT on the deadline:
1. CR must have submitted ERCOT LSE Application and Application Fee
2. CR must have filed for PUC REP Certification
3. TW updated on ERCOT Retail Testing Website
4. Send an email of intent to test to ERCOT at: RetailMarketTesting@ercot.com
The following steps must be completed by 5 PM CPT on the deadline for current MPs:
1. TW updated on ERCOT Retail Testing Website
2. Send an email of intent to test to ERCOT at: RetailMarketTesting@ercot.com
Testing Worksheets are locked at 5 PM CPT
5 | ERCOT Retail Client Services verifies that each new Testing Participant has completed Registration testing requirements with ERCOT | 2009-01-16 | 2009-05-22 | 2009-09-11 | 2008-09-19 | 2008-12-12 | 2009-03-13 | 2009-06-19 | 2009-09-18 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | Fri | Fri | Fri | Fri | Fri | Fri | Fri | Fri
6 | Verification and communication from PUCT Staff that Testing Participants intending to test have applied for REP Certification | 2009-01-16 | 2009-05-22 | 2009-09-11 | 2008-09-19 | 2008-12-12 | 2009-03-13 | 2009-06-19 | 2009-09-18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fri | Fri | Fri | Fri | Fri | Fri | Fri | Fri
7 | Communication from ERCOT Flight Administrator of Testing Participants to each TDSP | 2009-01-16 | 2009-05-22 | 2009-09-11 | 2008-09-19 | 2008-12-12 | 2009-03-13 | 2009-06-19 | 2009-09-18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fri | Fri | Fri | Fri | Fri | Fri | Fri | Fri
8 | (STRIKE - TW to be updated on ERCOT Retail Testing Website by all testing MPs, PGP Keys exchanged between MPs, and) MPs to start scheduling connectivity | 2009-01-19 | 2009-05-25 | 2009-09-14 | 2008-09-22 | 2008-12-15 | 2009-03-16 | 2009-06-22 | 2009-09-21 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | Mon | Mon | Mon | Mon | Mon | Mon | Mon | Mon
9 | Communication of Test Certificates from ERCOT Retail Client Services to all Testing Participants | 2009-01-19 | 2009-05-25 | 2009-09-14 | 2008-09-22 | 2008-12-15 | 2009-03-16 | 2009-06-22 | 2009-09-21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Mon | Mon | Mon | Mon | Mon | Mon | Mon | Mon
10 | TDSPs and ERCOT have completed communication of connectivity testing schedule to each Trading Partner | 2009-01-19 | 2009-05-25 | 2009-09-14 | 2008-09-22 | 2008-12-15 | 2009-03-16 | 2009-06-22 | 2009-09-21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Mon | Mon | Mon | Mon | Mon | Mon | Mon | Mon
11 | Connectivity Testing kick-off Conference Call - Mandatory for all Testing Participants (black-out ends) | 2009-01-20 | 2009-05-26 | 2009-09-15 | 2008-09-23 | 2008-12-16 | 2009-03-17 | 2009-06-23 | 2009-09-22 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | Tue | Tue | Tue | Tue | Tue | Tue | Tue | Tue
12 | Connectivity Testing begins for all Testing Participants | 2009-01-20 | 2009-05-26 | 2009-09-15 | 2008-09-23 | 2008-12-16 | 2009-03-17 | 2009-06-23 | 2009-09-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Tue | Tue | Tue | Tue | Tue | Tue | Tue | Tue
13 | Penny Test (CON52) & ACK55/56 (FA Scripts) begins for all New Testing Participants | 2009-01-20 | 2009-05-26 | 2009-09-15 | 2008-09-23 | 2008-12-16 | 2009-03-17 | 2009-06-23 | 2009-09-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Tue | Tue | Tue | Tue | Tue | Tue | Tue | Tue
14 | TDSPs communicate Test bed load to Trading Partners and ERCOT | 2009-02-09 | 2009-06-15 | 2009-09-28 | 2008-09-29 | 2009-01-05 | 2009-04-06 | 2009-06-29 | 2009-09-28 | 20 | 20 | 13 | 6 | 20 | 20 | 6 | 6 | Mon | Mon | Mon | Mon | Mon | Mon | Mon | Mon
| TDSP Test Bed Load Days* | [8 empty] | 24 | 24 | 17 | 10 | 24 | 24 | 10 | 10
15 | Flight Kick off Conference Calls - Mandatory for all Testing Participants | 2009-02-13 | 2009-06-19 | 2009-10-02 | 2008-10-03 | 2009-01-09 | 2009-04-10 | 2009-07-03 | 2009-10-02 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | Fri | Fri | Fri | Fri | Fri | Fri | Fri | Fri
16 | Daily Conference Calls begin – Day 1 Transactions flow | 2009-02-16 | 2009-06-22 | 2009-10-05 | 2008-10-06 | 2009-01-12 | 2009-04-13 | 2009-07-06 | 2009-10-05 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | Mon | Mon | Mon | Mon | Mon | Mon | Mon | Mon
17 | Flight tentatively scheduled to conclude | 2009-03-31 | 2009-08-04 | 2009-11-17 | 2008-11-18 | 2009-02-24 | 2009-05-26 | 2009-08-18 | 2009-11-17 | 43 | 43 | 43 | 43 | 43 | 43 | 43 | 43 | Tue | Tue | Tue | Tue | Tue | Tue | Tue | Tue
18 | Contingency Testing scheduled to conclude for Flight (black-out starts) | 2009-04-17 | 2009-08-25 | 2009-12-08 | 2008-12-09 | 2009-02-24 | 2009-06-16 | 2009-09-08 | 2009-12-08 | 17 | 21 | 21 | 21 | 0 | 21 | 21 | 21 | Fri | Tue | Tue | Tue | Tue | Tue | Tue | Tue
|  | 76 | 76 | 69 | 62 | 76 | 76 | 62 | 62 | 93 | 97 | 90 | 83 | 76 | 97 | 83 | 83
| Next Flight Deadline | 2009-05-20 | 2009-09-09 | 2010-01-13 | 2008-12-10 | 2009-03-11 | 2009-06-17 | 2009-09-16 |  | 0209 | 0609 | 1009 | 1008 | 0109 | 0409 | 0709 | 1009 | 0209 | 0609 | 1009 | 1008 | 0109 | 0409 | 0709 | 1009
| Time to Market** | 76 | 76 | 69 | 62 | 76 | 76 | 62 | 62 | 76 | 76 | 69 | 62 | 76 | 76 | 62 | 62
*TDSP Test Bed Load Days is calculated by subtracting the date the testing participants is communicated to the TDSPs from the date they are required to communicate the completed Test bed Load
**Time to Market is calculated by subtracting the Flight Deadline from the date Flight tentatively scheduled to conclude
Black-out period for Specified Ad-Hoc Testing and Emergency Testing
| Black-out periods | 4 days | 7 days | 14 days | 7 days
Formulas:
Date = [Date, row above]+[Days between Tasks]
Date = C7+[Days between Tasks]