## Sheet1
NPRR # | Source | Approval Status | Baseline | Essential for Go-Live | Short Description | Schedule Impact | Cost Impact | Integrated Schedule | EMS | MMS | OS | MOTE SOTE OTS | NMMS | COMS | CRR | EDW | EIP | IDA | INF | EDS IRT | MER Training | MIS | INT | MER CDR (formerly RTR) | MPIM
77 | NPRR | Approved | Post-Baseline2 | E | Incorporating the ERCOT Internal Audit Department and Other Clarifications (PRR735 companion) | None | 0 | Y | 4 | 4 | 4 | 4 | 4 | 4 | 4 |  | 4 | 4 | 4 | 4 | 4 |  | 4
78 | NPRR | Approved | Post-Baseline2 | E | Simplifying the Dispute Process | None | Minor to be absorbed | Y | 4 | 4 | 4 | 4 | 4 | 1 |  | 4 |  | 4 |  |  | 3 | 4 |  | 4 |  | Light green = Board approved
80 | NPRR | Approved | Post-Baseline2 | E | Revised Wording of Protocol Section 3.1.5.1 (Electrical buses as consequentially outaged transmission elements.) | None | 0 | Y | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 4 | 4 | 4 | 4 | Tan = draft NPRRs
81 | NPRR | Approved | Post-Baseline2 | E | Automatic Voltage Regulator (AVR) Status | None | <$50k | Y | 3 | 4 | 4 | 4 | 1 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 4 | 4 |  |  | No shading = in process
82 | NPRR | Approved | Post-Baseline2 | E | Section 8, Performance Monitoring and Compliance, Revisions to Monitoring and Qualification Tests | None | $50k-$100k | Y | 1 |  | 4 |  | 4 | 4 |  | 4 |  | 4 |  |  | 3 | 4 |  | 4 |  | Bright green = Reduction in scope
83 | NPRR | Approved | Post-Baseline2 | E | Remove Real-Time Energy Charge for a BLT from List of Real-Time Charge Types | None | 0 | Confirming | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 |  | 3 | 4 | 4 | 4 | 4 | Blue = post-implementation cost savings for ERCOT
84 | NPRR | Approved | Post-Baseline2 | E | Creating Amendment to Standard Form Market Participant Agreement | None | 0 | N/A | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 4 | 4 | 4 | 4
85 | NPRR | Approved | Post-Baseline2 | E | Revision of Digital Certificate Procedures | None | 0 | Confirming | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 4 | 3 | 3 | 2 | 4 | 4
86 | NPRR | Approved | Post-Baseline2 | E | Settlement Clarifications to RUC Capacity Shortfall Ratio Share Formula | None | 0 | Y | 1 | 1 | 4 | 2 | 4 | 1 | 4 | 4 |  | 4 | 4 |  | 4 | 4
87 | NPRR | Approved | Post-Baseline2 | E | Market Monitor Terminology Change | None | 0 | Y | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
88 | NPRR | Approved | Post-Baseline2 | E | Revision to 16.11.5, Monitoring of a Counter-Party’s Creditworthiness and Credit Exposure by ERCOT | None | 0 | N/A | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 4 | 3 | 4 | 2 | 4 | 4
89 | NPRR | Approved | Post-Baseline2 | E | Changing Posting Requirement of Certain Documents from MIS Secure to Public Area | None | 0 | Y | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 3 | 3 | 4 | 4
90 | NPRR | Approved Revised with ERCOT comments | Post-Baseline2 | E | Corrections of FIP-FOP in Energy Offers | None | <$50k | Y | 3 | 1 | 4 |  |  | 4 | 4 | 4 |  | 4 | 4 | 2 | 3 | 4 | 1
91 | NPRR | TAC 8/6/08 IA Review | Post-Baseline2 | E | Scarcity Pricing and Mitigated Offer Cap During the Period Commencing on the Nodal Market Implementation Date and Continuing for a Total of 45 Days | None | $50k-$100k | Y | 4 | 2 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 4 | 4 | 1
92 | NPRR | Approved | Post-Baseline2 | E | Remove Voltage Schedules Requirement | None | 0 | Y | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 3 | 4 | 3
94 | NPRR | Approved | Post-Baseline2 | E | Correct Reference to Credit Limit Determination | None | 0 | N/A | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 4 | 4 | 4 | 4
95 | NPRR | Approved | Post-Baseline2 | E | Clarify Recipients of McFRIs | None | 0 | N/A | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 4 | 4 | 4 | 4
96 | NPRR | Approved | Post-Baseline2 | E | Nodal Protocol Revisions to the RMR Startup Energy Payment | None | 0 | Confirming | 4 | 4 | 4 | 4 | 4 | 1 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 4 | 4 | 4 | 4
97 | NPRR | Approved | Post-Baseline2 | E | Changes to Section 8 to Incorporate role of TRE, the IMM, and the concept of Market Compliance | None | $100k-$250k | Y | 1 | 4 | 4 | 4 | 4 | 4 | 4 | 2 |  | 4 |  |  | 3 | 3 |  | 1
98 | NPRR | Approved | Post-Baseline2 | E | Protocols 4 and 6 Formula Clarifications | None | 0 | Y | 4 | 4 | 4 | 4 | 4 | 1 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 4 | 4 | 4 | 4
99 | NPRR | Approved | Post-Baseline2 | E | RMR Incentive Factor Payment | None | 0 | Confirming | 4 | 2 | 4 | 4 | 4 | 2 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 4 | 4 | 4 | 4
100 | NPRR | Approved | Post-Baseline2 | E | Removing PCRR release mechanism | None | 0 | Confirming | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 4 | 4 | 4 | 4
101 | NPRR | Approved | Post-Baseline2 | E | Modify Time Requirements for Entry of Equipment in the Outage Scheduler | None | 0 | Confirming | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 4 | 4 | 4 | 4
102 | NPRR | PRS 8/21/08 tabled | Post-Baseline2 | E | PUCT 25.505 Publication of Resource and Load Information (Disclosure of market data (PRR697 / PUCT33490)) | None | $1.5M-$2.0M | Y | 1 | 1 | 4 | 4 | 4 | 2 | 4 | 1 |  | 4 | 4 |  | 3 | 2 |  | 4
103 | NPRR | Approved | Post-Baseline2 | E | Settlement of Power Imported via DC Ties (Back to Back Ties) and Block Load Transfer Under Emergency Conditions | None | 0 | Confirming | 4 | 4 | 4 | 4 | 4 | 1 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 4 | 4 | 4 | 4
105 | NPRR | Approved | Post-Baseline2 | E | Section 23, Synchronization of Zonal Protocols | None | 0 | N/A | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 4 | 4 | 4 | 4
106 | NPRR | Approved | Post-Baseline2 | E | Section 24, Synchronization of Zonal Protocols | None | 0 | N/A | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 4 | 4 | 4 | 4
107 | NPRR | Approved | Post-Baseline2 | E | Emergency Interruptible Load Service | None | <$50k | Y | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 2 | 4 | 4 | 4
108 | NPRR | Approved | Post-Baseline2 | E | Fuel Oil Price (FOP) Clarification | None | 0 | Confirming | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 4 | 4 | 4 | 4
109 | NPRR | Approved | Post-Baseline2 | E | Section 18, Synchronization of Zonal Protocols | None | 0 | N/A | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 4 | 4 | 4 | 4
110 | NPRR | Approved | Post-Baseline2 | E | Section 20, Synchronization of Zonal Protocols | None | 0 | N/A | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 4 | 4 | 4 | 4
111 | NPRR | Approved | Post-Baseline2 | E | Timelines for Response by ERCOT to TSP Requests | None | 0 | N/A | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 4 | 4 | 4 | 4
112 | NPRR | Approved | Post-Baseline2 | E | Emergency Base Point Price Revision | None | 0 | Y | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 4 | 4 | 4 | 4
113 | NPRR | PRS 6/19/08 tabled | Post-Baseline2 | E | Load Resource Type Indicator for Ancillary Service (AS) Trades and Self-Arranged AS | TBD | TBD | Y | 1 | 4 | 4 | 4 | 4 | 4 | 4 | 4 |  | 4 | 4 |  | 3 | 4 |  | 4
114 | NPRR | Approved | Post-Baseline2 | E | Section 11, Synchronization of Zonal Protocols | TBD | TBD | N/A |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 |  |  | 3 | 4 |  | 4
117 | NPRR | Approved | Post-Baseline2 | E | Resource Registration Clarification | None | 0 | N/A | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 4 | 4 | 4 | 4
118 | NPRR | Approved | Post-Baseline2 | E | Section 14, Synchronization of Zonal Protocols | None | 0 | N/A | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 3 | 4 | 4 | 4
119 | NPRR | Approved | Post-Baseline2 | E | Resource Limit Calculator | None | 0 | Y | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 4 | 4 | 4 | 4
120 | NPRR | Approved | Post-Baseline2 | E | Corrections and Clarifications for Real Time Settlements | None | 0 | Y | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 4 | 4 | 4 | 4
122 | NPRR | Approved | Post-Baseline2 | E | Simplify Ancillary Services Settlement Formulas | None | 0 | Y | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 4 | 4 | 4 | 4
123 | NPRR | Approved | Post-Baseline2 | E | Inadvertent Energy Account Revision | None | 0 | N/A | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 4 | 4 | 4 | 4
124 | NPRR | PRS 7/17/08 tabled | Post-Baseline2 | E | Resource Node Updated Definitions | None | $100k-$150k | Y | 4 | 1 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 |  |  | 3 | 4 |  | 4
126 | NPRR | Pending 9/4/08 TAC Review | Post-Baseline2 | E | Section 19, Synchronization of Zonal Protocols | None | 0 | N/A | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 |  |  | 3 | 4 |  | 4
127 | NPRR | Approved | Post-Baseline2 | E | Section 22 Attachments A, I, J & M, Synchronization of Zonal Protocols | None | 0 | N/A |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 |  |  | 3 | 4 |  | 4
128 | NPRR | PRS Tabled until development of Impact Analysis | Post-Baseline2 | E | Combined Cycle Power Blocks with Multiple Voltage Interconnections | TBD | $100k | Y |  | 1 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 |  |  | 3 | 4 |  | 4
129 | NPRR | PRS 8/21/08 Pending Language | Post-Baseline2 | E | Section 15, Synchronization of Zonal Protocols | TBD | TBD | N | [9 empty] | 4 |  |  | 3
130 | NPRR | Approved | Post-Baseline2 | E | CRR Settlements Revenue Equalization | None | $50k-$100k | Confirming | 4 | 4 | 4 | 4 | 4 | 1 | 4 | 4 |  | 4 | 4 |  | 3 | 4 |  | 4 | 4
131 | NPRR | PRS Tabled until development of Impact Analysis | Post-Baseline2 | TBD by TPTF pending IA | Ancillary Service Trades with ERCOT | TBD | $605k | Y |  | 1 | 4 | 4 | 4 | 1 | 4 | 4 | 4 | 4 |  |  | 3 | 2 |  | 4
132 | NPRR | Approved | Post-Baseline2 | E | Outage Clarification | None | 0 | Y |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 |  |  | 3 | 4 |  | 4
133 | NPRR | Approved | Post-Baseline2 | E | Addition of PSSE Format | None | 0 | Y | 4 | 4 | 4 | 4 | 4 | 4 | 1 | 4 | 4 | 4 |  |  | 3 | 4 |  | 4
134 | NPRR | PRS Tabled until development of Impact Analysis | Post-Baseline2 | E | Section 7 Cleanup | TBD | $540k | Y |  | 1 | 4 | 4 | 4 | 1 | 2 | 4 | 1 | 4 |  |  | 3 | 4 |  | 4
135 | NPRR | PRS Voted to table until PRR is submitted and approved | Post-Baseline2 | TBD | Deletion of UFE Analysis Zone Language | TBD | TBD | N
136 | NPRR | PRS Voted to table until PRR766 is submitted and approved | Post-Baseline2 | TBD | Interim Solution for 15-Minute Settlement of Advanced Meters | TBD | TBD | N
137 | NPRR | TPTF 8/25/08 Pending Language | Post-Baseline2 | TBD | Synchronization and Update of Section 21 | TBD | TBD | N/A
138 | NPRR | PRS 8/21/08 Pending Language | Post-Baseline2 | E | Credit Monitoring and Management Reports | TBD | TBD | N
139 | NPRR | PRS 8/21/08 Pending Language | Post-Baseline2 | TBD | Available Credit Limit, Estimated Aggregate Liability, Future Credit Exposure Calculation Updates | TBD | TBD | N | [9 empty] | 4 |  |  | 3
140 | NPRR | PRS 8/21/08 Pending Language | Post-Baseline2 | TBD | Revision to CRR Obligation Margin Adder | TBD | TBD | N
141 | NPRR | TPTF 8/11/08 Pending Language | Post-Baseline2 | TBD | TDSP Energy Storage for Reliability | TBD | TBD | N
142 | NPRR | PRS 8/21/08 Pending Language | Post-Baseline2 | TBD | EECP Media Appeal Change | TBD | TBD | N
143 | NPRR | PRS 8/21/08 Pending Language | Post-Baseline2 | TBD | Section 9.9.1, Invoice Recipient Payment to ERCOT for the CRR Auction, Clean-up | TBD | TBD | N
144 | NPRR | TPTF 8/11/08 Pending Language | Post-Baseline2 | E | Five RUC Deployments Needed Before Requiring Verifiable Costs (VCWG) | TBD | TBD | N
145 | NPRR | TPTF 8/11/08 Pending Language | Post-Baseline2 | TBD | PPAs as Resource-Specific Verifiable Costs (VCWG) | TBD | TBD | N
146 | NPRR | TPTF 8/11/08 Pending Language | Post-Baseline2 | TBD | ICCP Telemetry Information Submittals | TBD | TBD | N
147 | NPRR | TPTF Pending Language | Post-Baseline2 | TBD | DAM Short Pay Changes | TBD | TBD | N
148 | NPRR | TPTF Pending Language | Post-Baseline2 | TBD | Treatment of Financial Information as Confidential | TBD | TBD | N
TBD | NPRR | Draft Pending | Post-Baseline2 |  | NPRR DC Tie | TBD | TBD | N | [9 empty] | 4 |  |  | 3
TBD | NPRR | TPTF Pending Language | Post-Baseline2 | N | Simplifying OBLRACT and OPTRACT | TBD | TBD | N | [5 empty] | 1 |  |  |  | 4 |  |  | 3
TBD | NPRR | Drafted | Post-Baseline2 | N | Failure to Update Verifiable Cost Data Results in Use of Resource Category Generic Costs | TBD | TBD | N | [5 empty] | 2 |  |  |  | 4 |  |  | 3
TBD | NPRR | TPTF Pending Language | Post-Baseline2 | E | Initiating the SWCAP at Real Time Market Opening | TBD | TBD | N | [9 empty] | 4 |  |  | 3
TBD | NPRR | TPTF Pending Language | Post-Baseline2 | N | Nodal Section 8 Protocol Revision Request (multiple NPRRs) | TBD | TBD | N | [9 empty] | 4 |  |  | 3
TBD | NPRR | Drafted | Post-Baseline2 |  | Nodal Protocols Section 3.2.3, System Adequacy Reports - Clarification Request | TBD | TBD | N | [9 empty] | 4 |  |  | 3
TBD | NPRR | Draft Pending | Post-Baseline2 |  | Scheduling and Operating Transmission Devices in the Nodal Environment | TBD | TBD | N | [9 empty] | 4 |  |  | 3
TBD | NPRR | TPTF Pending Language | Post-Baseline2 |  | Nodal Protocol Step-Up Transformer Reporting Requirements | TBD | TBD | N | [9 empty] | 4 |  |  | 3
TBD | NPRR | TPTF Pending Language | Post-Baseline2 | E | Section 16: Remove Late Fee Language | TBD | TBD | N |  | 4 | 4 | 4 |  | 4 | 4 | 4 |  | 4 |  |  | 3
TBD | NPRR | TPTF Pending Language | Post-Baseline2 |  | Removal of partial assignment of CRR Shortfall to Real-Time | TBD | TBD | N | [9 empty] | 4 |  |  | 3
TBD | NPRR | TPTF Pending Language | Post-Baseline2 |  | Post to the MIS Resource Nodes Diagrams | TBD | TBD | N | [9 empty] | 4 |  |  | 3
TBD | NPRR | TPTF Pending Language | Post-Baseline2 |  | Verifiable Cost Draft NPRR for Nodal Protocols Sections 2, 4 and 5 | TBD | TBD | N | [9 empty] | 4 |  |  | 3
TBD | NPRR | TPTF Pending Language 7/21/08 | Post-Baseline2 |  | Clarify Definition of a Generator Output Breaker in the Outage Scheduler | TBD | TBD | N
TBD | NPRR | TPTF Pending Language 7/21/08 | Post-Baseline2 |  | Generation Resource Fixed Quantity Block Offer | TBD | TBD | N