## Release Buckets
| Initial Assembly | Pipeline Testing | Firm Configurations | Performance and Security | Performance and Security Punchlist | Final functionality puchlist | Final puchlist for 168 hour test | Post 168 hour required for Go-Live
| Integration R1.0 | Integration R2.0 | Integration R3.0 | Integration R4.0 | Integration R5.0 | Integration R6.0 | Integration R7.0 | Integration R8.0
Project Deliveries | MMS4 Patch 1 | MMS4 Patch 2 | MMS4 Patch 3 | OS2.0.13 (final) | NMMS7 | MMS5 "Final" | MMS5 "Final" - Defect Release | Regression Testing of Defects found during 168 hour test
| EMS4.1.12.3 | EMS5.1.3.3 | OS2.0.13 | MMS4 Patch 5 | CMM3.3 | EDW extracts 6(NPRR 102) | MMS5 "Final" - Defect Release | Final Testing of items not required for 168 hour test
| NMMS3 | EMS5.1.4.x (VSAT/TSAT) | S&B4 | OS_UI FP1 | CMM4.3 | Regression testing | Regression testing
| OS2.0.10 | EMS5.1.5.x (OE/VSS) | CDR3C | EMS5.1.6.x (CIM / Habitat) | MMS5 "Prelim"
| OS_UI FP0 | Siebel Phase 4 | MIS9 | MIS10 | MIS11
| CRR2B | NMMS4 (Stand Alone) | MMS4 Patch 4 | OS_UI FP2 | CDR4A
| CMM3.1 | CMM3.1 | NMMS5 | CDR4 | Regression testing
| Siebel Phase 3 | CDR3B (Regression) | Regression testing | CMM4.2
| CDR3B | MIS8 |  | OS_UI FP3
| MIS7 | Regression testing |  | CMM3.2
EMS (SIG Release)
NMMS6
CMM4.1
Regression testing
Integration Components | Data Set for Integration 2.0 | Data Set for Integration 2.0 Bugs | Data Set for Integration 4.0 | Data Set for Integration 4.0 Bugs | Data Set for Integration 6.0 | Data Set for Integration 6.0 bugs | Data Set for Integration 7.0 bugs
|  | Data Set for Integration 3.0 | Data Set for Integration 3.0 Bugs | Data Set for Integration 5.0 (NMMS,EMS,MMS,CRR Synched) | Data Set for Integration 5.0 Bugs | Data Clean up prior to 168 hour test | Data Clean up prior to 168 hour test
| Registration Adapter | MP--> MMS (EWS1.15) | EMS<-->MMS Interface | CSI5.5 (to S&B) | MMS-->EDW (Extracts) | MP-->MMS (Large Messages)
| Reg --> MMS | MMS-->MP (EWS1.15) | MP<-->MMS (EWS1.16) | S&B --> MMS | EMS-->EDW (Sec8)
| Reg --> CRR | CSI 5.2 / CSI 5.3 (to S&B) | MP<-->OS (EWS1.16) | EMS-->EDW (Reporting)
| Reg --> S&B | Platts --> MMS (FIP/FOP) | EMS<-->OS Interface | S&B--> EDW (SS Extracts)
| CMM --> CRRAdapter | Platts --> S&B (FIP/FOP) | CMM --> MMS | MMS-->EDW (Rpts, Extracts) | Market Notifications
| CRR --> CMMAdapter | MP-->REG (EWS1.16) | CMM --> CRR | CSI6.2 (to CMM) | CSI7.1 (to S&B)
| CRR --> CMMP2PAdapter | CRR --> MMS | CRR --> CMM | NMMS --> EMS (FNM) | CSI7.2 (to CMM)
| CRR --> MMSP2PAdapter | REG --> MMS | OS --> EDW (Reports) | REG --> NMMS | NMMS - MMS
| NMMS Adapter | REG-CRR | CMM --> REG | OS --> NMMS
| NMMS --> S&B | REG --> CMM | EMS --> CDR3C | NMMS --> CRR
| NMMS --> OS_P2P Adapter | REG --> S&B | CSI5.4 (to S&B) | NMMS --> OS
| PlattsAdapter |  | MP<-->MMS (EWS1.17) | NMMS --> S&B
| Platts --> MMSAdapter |  | S&B --> CMM | MMS-->EDW (Rpts, Extracts)
| Platts --> SnBAdapter |  |  | EMS --> EDW (Rpts)
| Windforecaster |  |  | CSI6.3 (to CMM)
| EWS1.14 |  |  | NMMS --> MIS
|  |  | EMS<-->MMS EIP monitoring | CSI6.6 (to S&B)
|  |  | EMS<-->OS EIP monitoring | MMS --> EDW (Extracts)
|  |  | MPIM Integration | S&B - CRR
CSI6.1 (to CMM)
CSI6.5 (to CMM)
CSI6.4 (DST) (to CMM)
Operational Readiness |  | Failover Requirements Verified | Failover Plan Devlopment | Failover Development & Test | Failover Test | Failover Test | Final Bug Patches for 168 hour test | Final Defects required for Go-Live
|  | Blue Building Build out | Blue Building Build out | Blue Building Build out | Blue Building Buildout | Blue Building Active for iTest
|  | MOTE / SOTE Requirements | Mote Sote verification |  |  | Intersite Failover
|  |  | MOTE SOTE Construction | MOTE SOTE Build out
|  | Redundancy Verification | Redundancy Moves | Redundancy Moves
|  | Security Requirement Verification | SecurityTest Plan Development | Security Testing 1 | Security Testing 2 | Security Testing 3 |  | Final Security Audit
|  |  | Security Testing Initial | Security Remediation | Security Remediation | Security Remediation
|  | Performance Test Planning | Performance Testing Development | Performance Test 1 | Performance Test 2 | Performance Test 3 |  | Final Permance Signoff
|  |  | Performance Testing Initial | Performance Upgrades | Performance Upgrades | Performance Upgrades
|  | End to End Test Development | End To End Test Scripts Development | End To End 1 | End To End 2 | End To End 3 | 168 Hour Readiness Testing
|  |  | End to End Testing Starts | End to End Remediation | End to End Remediation | End to End Remediation
|  | Server moves / Austin moves to colocation | Server moves / Austin moves to colocation
MMS CPU Turn up (Dev, FAT)
Monitoring Requirements
|  | Monitoring Development | Montioring Development | Monitoring Development
|  |  |  | Monitoring Testing | Monitoring Testing | Monitoring Testing
[5 empty] | Monitoring Bug Fixes | Monitoring Bug Fixes | Final Monitoring for 168 hour testing
|  | Run Book Requirements | Run Book Requirements
|  |  | Run Book Development | Run Book Development | Run Book Development
|  |  |  | Run Book Testing | Run Book Testing | Run Book Testing
|  |  | Server Moves |  | Run book Bug Fixes | Run book Bug Fixes | Final Run Book for 168 test | Final Run Book Updates for Production Support
DST Planning
|  |  | DST | DST | DST | DST | DST

## EDS Releases
| Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7
Target EDS Release | Execute SCED with the objective of publishing LMPs for 6 months | Single Entry Model Go-Live | Continue execution of SCED for publishing LMPs for 6 months and publish reports | Continue execution of SCED for publishing LMPs for 6 months and publish reports | Publish RT and DAM settlements for Full market timeline | Continue execution of SCED for publishing LMPs for 6 months and publish reports | Continue DAM/RUC/SCED performance tests
| Publish SCED reports (RT LMPs etc) | Continue execution of SCED for publishing LMPs for 6 months and publish reports | Conduct 2 hour LFC test with CIM | LFC test analysis and reporting of results to Market Participants | Execute 48 hour LFC test | Complete posting of LMPs for 6 months | Execute DST test
| Test communication of DAM inputs and outputs | Continue execution of DAM 2 days per week with Market Data, issue notifications and publish results | Conduct 8 hour LFC test with CIM | Continue execution of DAM and DRUC 5 days per week, issue notifications and publish results | Execute EECP test | Continue execution of DAM and DRUC 5 days per week | Execute 48 hours of full market timeline without Sev 1 or Sev 2 errors
| xecute DAM 2 days per week with Market Data | Execute HRUC and DRUC 2 days per week with Market Data | Publish mock Integrated CRR auction results | Continue execution of HRUC 4 days per week | Continue execution of SCED for publishing LMPs for 6 months and publish reports | Continue execution of HRUC 4 days per week | Complete verification of MIS compliance to Requirements
| Post AS Obligation, QSE Load Ratio Share, AS plan | Publish RUC results | Execute DAM and DRUC 5 days per week, issue notifications and publish results | Continue SASM execution | Continue execution of DAM and DRUC 5 days per week | Continue publishing of DAM and RTM Settlement Statements, Invoices and extracts | Complete execution of Fail-over tests
| Issue DAM Awards and Notifications (Awarded AS, Awarded Energy bid etc) | Committed and decommitted units | Execute HRUC 4 days per week | Continue publishing of DAM and RTM Settlement Statements, Invoices and extracts | Continue execution of HRUC 4 days per week | Continue integrated CIM business process testing | Complete verification of Dispute Process
| Publish DAM hourly reports (DAM LMPs, DAM MCPC etc) | Active binding transmission constraints used in RUC | Begin SASM execution | Execute full Market timeline for 7 seven days | Continue publishing of DAM and RTM Settlement Statements, Invoices and extracts | Execute DAM/RUC/SCED performance test | 7 day forecast validations/retraining
| Conduct mock CRR annual auction | Publish Settlement Statements, Invoices and Extracts for DAM | Issue SASM notifications | Produce Settlement statements for the full market timeline | Deploy MMS with full functionality into EDS environment | Conduct DST Test with Market Participants | Conduct test monthly CRR auction for 168-Hour test
| Publish CRR auction results | DAM Settlement and Resettlement Statement | Awarded AS offers | One day dual entry of Outages into Zonal and Nodal systems | Conduct CIM business process testing | Begin verification of MIS compliance with Requirements | Begin 168-Hour Test
| Outage Scheduler open to MPs for submissions | CRR Balancing Account Invoices | Publish SASM reports |  | 7*24 support of Nodal systems | Conduct fail-over test (s) | Qualification - QSE declaration of intent to participate in Nodal
| Perform Outage Evaluation testing | DAM Invoice | SASM MCPC |  | Validate EDW Compliance Data Access
| Publish Outage Scheduler reports (Approved outages, rejected etc) | CARD Invoices | Total Ancillary Service procured
| Publish Available Credit Limit on MIS | DAM Resettlement Invoice | Aggregated Ancillary Service Offer
| Seek TPTF approval for test Network Model to be used for Settlements testing | DAM Late Fee Invoices | Publish Settlement Statements, Invoices and Extracts for RTM and DAM
|  | DAM Consolidated Operating Day Extracts | RTM Initial, Final, True-up and Resettlement Statement
|  | DAM Market Operating Day Extracts | RTM Initial, Final, True-up and Resettlement Invoice
|  | Public Reference Data Extract | RTM Consolidated Operating Day Extract (RTM CODE)
|  | Settlement Input Data Extract | RTM Market Operating Day Extract (RTM MODE)
|  | Conduct NMMS validation rules testing with TSPs | Public Reference Data Extract (PRDE)
|  | Conduct OS Performance test | Settlement Input Data Extract
|  | Publish test CRR annual auction results | Begin testing of Disputes submission process through UI and API
Conduct Integrated CRR monthly auction

## NMMS Deliveries
Project Deliveries | Description
NMMS4A
Description | Outage selection for CRR & planning models
PTC enhancement sto support PTI topology
PTI Release 2 - dsitributions ystem reduction, temp rating sets, contingency data exports
NMMS5 |  | NP12-753 Settlement Input Data Extract
* Description | Production Model business processes and workflow
Auto Model Scheduler
MIS Posting folder structure
Historical models
PTC screens to support PMCR linkage
Canned reports
NMMS Integration Points
NMMS6
PTC functionality and screens
Outage Clarification
Name Service
As Built Report

## MMS Deliveries
Project Deliveries | Description
MMS4 Patch2
* Description: | Updated MMS4 version running on V 1.12 of CIM
Defect Bundle
(3-Medium) DSI-DAM - Self Committed Resources in DAM
(3-Medium) DSI-DAM - Change 5 to 10 ramp rate
(3-Medium) ENEN-End-to-end - ENHANCEMENT: Modeling and processing of ERCOT 345 KV Bus Avg & ERCOT 345 KV Hub Avg.
(3-Medium) INFX - Hourly Limits for Generic Constraints
(3-Medium) CIM - Modeling of Non-ERCOT Non Conforming load
(3-Medium) CIM - Flowgate modeling
(3-Medium) CIM - Combined cycle configuration modeling mapping of configuration to Primary/Alternate Physical generators (SIG paper)
(3-Medium) CIM - Load Resource modeling (covered in line item 3 and SIG paper) - SIG005
(3-Medium) CIM - PUN modeling (SIG paper) - SIG002
(3-Medium) CIM - Non-Modeled generation modeling (covered in line item 10) - SIG008
(3-Medium) CIM - BLT modeling - SIG007
(3-Medium) DSI-DAM - ERCOT Action ITEM: Combined Cycle logical resource nodes
(3-Medium) CIM - Monitor/enforced flagt for all branches must come from CIM (verify in CIM schema)
(3-Medium) CIM - Contingency description from CIM into MMS schema (MAINF or MIINF)
(3-Medium) ENEN-End-to-end - Physical Resource Node Modeling
(3-Medium) CIM - SPR/RAP Activation Flow + SPS/RAP model
MMS4 Patch3
* Description: | Updated MMS4 version running on V 1.16 of CIM
Self Committed Resources in DAM
Combined cycle configuration modeling mapping of configuration to Primary/Alternate Physical generators (SIG paper)
Load Resource modeling (covered in line item 3 and SIG paper) - SIG005
PUN modeling (SIG paper) - SIG002
Non-Modeled generation modeling (covered in line item 10) - SIG008
BLT modeling - SIG007
ERCOT Action ITEM: Combined Cycle logical resource nodes
Monitor/enforced flagt for all branches must come from CIM (verify in CIM schema)
Resource Parameters API
Defect Bundle - (2-Major) - 4 Fixes, (3-Medium) - 97 Fixes, (4-Minor) - 20 Fixes
MMS4 Patch4
* Description: | MMS4 Patch 4 running on V 1.16 of CIM
Partial implementation of NPRR 102
Bug fixes
Partial fixes for NPRR124, NPRR128?
MMS4 Patch5
* Description:
MMS5 (Prelim)
* Description: | MMS 5 prelim (taken at the beginning of FAT testing)
MMS regression tested on (V TBD) of CIM
NPRR 102
NPRR 113
NPRR 131
NPRR 128
NPRR 134
What about NPRR091, NPRR124? What about any other approved NPRRs that might impact MMS?
Outstanding bug fixes from MMS4 patch 4
MMS5 (Final)
* Description: | Full Regression Testing Complete
OS 2.0.13
Description: | Bug fixes
final OS release

## EMS Deliveries
Project Deliveries | Description
EMS5.1.3.3
* Description:
EMS5.1.4.x (VSAT/TSAT)
* Description:
EMS5.1.5.x (OE/VSS)
* Description: | Outage Evaluation
Voltage Support Services
NMMS4 (Stand Alone)
CMM 3.1
Staging tables and links to internal working tables
CDR 3C
| EMS Reports | EMS --> CDR3C --> MIS (State Estimator 15 min Ave of Loads)
| EMS Reports | EMS --> CDR3C --> MIS (Transformer Flows, Voltages, & Tap Positions)
| EMS Reports | EMS --> CDR3C --> MIS (Dynamic Rating Deviation Data)
| EMS Reports | EMS --> CDR3C --> MIS (Temp Removed Contingencies)
| MMS Reports | MMS --> CDR3C --> MIS (SASM Aggregated Ancillary Service Offer Curve)
| MMS Reports | MMS --> CDR3C --> MIS (Manual over-riding of HDLs and LDLs)
EDW1C (Against Active EDS)
| EMS Reports | NP6-654-ER Total Regulation Report | EDW is already in ITEST waiting on EMS5.1.X.x (Aug Patch) data; will be about 25 days to test once data is available
EDW2C
| Shadow Settlement Extracts | NP12-743 DAM Consolidated Operating Day Extract | Waiting on COMS Data (COMS301)
| Shadow Settlement Extracts | NP12-177 DAM Consolidated Operating Day Extract
| Shadow Settlement Extracts | NP12-747 Real Time Market Consolidated Operating Day Extract
| Shadow Settlement Extracts | NP12-749 Real Time Market Operating Day Extract
| Shadow Settlement Extracts | NP12-465 Public Reference Data Extract
| Shadow Settlement Extracts | NP12-753 Settlement Input Data Extract
MIS8
MIS8 | MIS Report Links | EDW - Outage Scheduler Metrics Report
MIS8 | MIS Report Links | EDW - Critical Data Availability Statistics Report
MIS8 | MIS Report Links | EDW - ICCP Link Availability Statistics Report
MIS8 | MIS Report Links | EDW - Monthly Market Participant Real Time Availability
MIS8 | MIS Report Links | EDW - Quarterly Point Availability Statistics Report
MIS8 | MIS Report Links | EDW - RARF Receipt Report
MIS8 | MIS Report Links | EDW - Transmission Advanced Outage Schedule Statistics
MIS8 | MIS Report Links | EDW - Internal Resource Advanced Outage Schedule
MIS8 | MIS Report Links | EMS - Dispatch Instructions Compliance Metrics Report
MIS8 | MIS Report Links | EMS - Operations Shift Schedules
MIS8 | MIS Report Links | EMS - AVR Test Results and PSS Test Results
MIS8 | MIS Report Links | EMS - Non-Spin Performance Report
EWS(1.15)
| MMS Adapter | * Added SubmitTime to the BidSet header holding Bid request receipt timestamp by ERCOT (MMS4)
| MMS Adapter | * Update 3PO with SuMeFipFop and EocFipFop introduced in MMS4
| MMS Adapter | * Removed “.. .. but only one point can be specified for RegDown or OffLineNonSpin” restriction from ASOffer, ASPriceCurve based on the input from MMS team.
| MMS Adapter | * Added MultiHourBlock to CRR, PTP Oblig, Energy bid and Energy only Offer input tables
| MMS Adapter | * Added RRS_ NCLR as a new ASType for SelfArrangedAS
| MMS Adapter | * Updated ASOffer with nonControllableLoadFlag flag
| MMS Adapter | * 3.3.2 Added RRS_NCLR to the list of ASType for SelfArrangedAS
| Market Information Adapter??? | * Added hourEnding to the BindingConstraints and updated the schema diagram
| Market Information Adapter??? | * Corrected the LoadForecasts MarketInfo Noun to be plural (adding the LoadForecasts container)
| Market Information Adapter??? | * Added marketType to ASObligations to account for DAM or SASM
| Market Information Adapter??? | * 7.2.1 Tagged TransmissionOutage/Opportunity/designatedResource/station and HSL as required per OS.xsd
| Market Information Adapter??? | * Updated LoadDistributionFactors to have name and factor only – consistent with CDR interfaces
| Market Information Adapter??? | * Added Market type to the startup/shutdown instructions with possible values of HRUC, DRUC, and DAM
| Market Information Adapter??? | * Added MarketType to the get AwardSet = DAM/ADJ/RTM/SASM/RUC/SCED
| Market Information Adapter??? | * Merged in MIS Int Specification version .37 - Market Info Nouns into the section 4 of this spec – 4.3.31 thru 4.3.45
| Market Information Adapter??? | * 4.3.26 Unit Availability: Tagged BlackStart and Available megawatts as a place holder for future use.
| Market Information Adapter??? | * Added equipmentType to Dynamic Ratings and Dynamic Ratings Deviations
| Market Information Adapter??? | * Modified CompetitiveConstraints structure to hold new elements CompetitivenessStatus, deleted OperatorOverwrite – consistent with CDR Interface
| Market Information Adapter??? | * Corrected the possible values for MarketType for various Award Sets.
| Market Information Adapter??? | * Reverted back to the original external reporting interface in section 9 – adjusted with supporting MID/MIR interface
| Market Information Adapter??? | * Corrected PTP Obl. MaximumPrice/price
| OS Adapter | * Made DisclaimerAck and Disclaimer as required fields for OS
| OS Adapter | * Added enumeration to equipment Outage, Outage states. Added 3 more cancellation reasons (EXP, ERR, and ROM)
| OS Adapter | * Added notes about OS query StartTime and endTime are optional but they should not be present when an mRID is sent.
| OS Adapter | * OS – 7.2.1 Corrected the resourceType choices to UL or LR
| OS Adapter | * Updated Outage opportunity outages with opportunity duration – consistent with OS application
EWS(1.16)
EWS(1.16) | MMS AsyncAwardsAdapter | * Added NCLRFlag to awardedAS (MMS4)
EWS(1.16) | MMS AsyncAwardsAdapter | * Added crrOwnerName to Awarded CRR (MMS4)
EWS(1.16) | MMS AsyncAwardsAdapter | * Added startType and combinedCycleName to AwardedEnergyOffer (MMS4)
EWS(1.16) | MMS Adapter | * MP Resource Parameter Transaction Service (MMS4)
EWS(1.16) | Siebel Adapter (Registration Interface) | * Dispute Submission / Query (REG4)

## COMS
Project Deliveries | Description
CMM 3.1
* Description | Integration Staging tables and links to internal working tables (ROME)
CMM 3.2
* Description | ERCOT Developed Integration Components
CMM 4.1 (TBD)
CMM Custom Management:
* Credit Scoring
* Entity Component Adjustment
* Internal and External Reports
* TBD
Siebel Phase 4 | Settlements calendar
Siebel Integration Interfaces
Disputes User Interface
Dispute API
Lodestar / CSI | DAM Settlements
DAM Energy Sales / Purchases (CSI 5.4)
DAESAMT
DAEPAMT
DAM Ancillary Services (ready)
PCNSAMT
DANSAMT
PCRUAMT
DARUAMT
PCRDAMT
DARDAMT
PCRRAMT
DARRAMT
DA Makewhole (CSI 5.4)
DAMWAMT
LADAMWAMT
DA - RT Obligation (ready)
DARTOBLAMT
RT Settlements
RT Energy Imbalance (CSI 5.4)
RTEIAMT
RT Congestion (CSI 4.3)
RTCCAMT
Ancillary Services (CSI 5.3)
RTRDAMT
RTRUAMT
RTRRAMT
RTNSAMT
NSFQAMT
RDFQAMT
RUFQAMT
RRFQAMT
RTPCNSAMT
RTPCRDAMT
RTPCRUAMT
RTPCRRAMT
Base Point Deviation (CSI 5.4)
BPDAMT
LABPDAMT
Admin Fee (ready)
ESACAMT
Voltage Support (CSI 4.3)
LAVSSAMT
VSSEAMT
VSSVARAMT
Block Load Transfer (ready)
BLTRAMT
Black Start (CSI 4.3)
BSSAMT
LABSSAMT
RUC Settlements
RUC Make Whole (CSI 5.1)
RUCMWAMT
LARUCAMT
RUC Decommitment (CSI 4.3)
RUCDCAMT
LARUCDCAMT
RUC Clawback (ready)
RUCCBAMT
LARUCCBAMT
RUC Settlements
RUC Capacity Short (MMS 4 P2; CSI 5.4) (excluding DC Tie data)
RUCCSAMT
RT Settlements
RMR (MMS 4 P2; CSI 5.5)
RMREAMT
LARMRAMT
RMRSBAMT
RMRNPAMT
RMRAAMT
Emergency Energy (CSI 5.5)
EMREAMT
LAEMREAMT
CRR Settlements
DA Option/Obligation (MMS 4 P2; CSI 5.5)
DAOPTAMT
DAOBLAMT
DAOBLRAMT
DAOPTRAMT
RTM Option/Obligation (MMS 4 P2; CSI 5.5)
RTOPTAMT
RTOBLAMT
DAMRTOPTRAMT
No DAM CRR (MMS 4 P2; CSI 5.5)
NDRTOBLRAMT
NDRTFGRAMT
NDRTOPTRAMT
NDRTOPTAMT
NDRTOBLAMT
RUC Settlements
RUC Capacity Short (MMS 5; CSI 5.6) - everything
RUCCSAMT
RT Settlements
Real Time Revenue Neutrality (MMS 5; CSI 5.6)
LARTRNAMT
DC Tie (MMS 5; CSI 5.6)
RTDCIMPAMT
RTDCEXPAMT
Nodal Surcharge Fee (MMS 5; CSI 5.6)
QNSAMT
CRR Settlements
Flowgate (MMS 4 P5; CSI 5.5)
DAFGRAMT

## CSI (Bill Determinants)
Project Deliveries | Description |  | Description
CSI 5.3 (to Lodestar)
GUI - Part I
| CSI Event / Data Transfer ( 5 Billing Determinants) | DAILY_CRROWNERSHIP2STL
| Billing Determinant | DAFGR (<CO><FGR>)
| Billing Determinant | DAOBL (<CO><SRSP><SKSP>)
| Billing Determinant | DAOBLR (<CO><SRSP><SKSP>)
| Billing Determinant | OPT (<CO><SRSP><SKSP>)
| Billing Determinant | OPTR (<CO><SRSP><SKSP>)
| CSI Event / Data Transfer (18 Billing Determinants) | DAILY_DAMINPUT2STL
| Billing Determinant | DAHSL (<Q><R><SP>)
| Billing Determinant | DALSL (<Q><R><SP>)
| Billing Determinant | DAMEO (<Q><R><SP>)
| Billing Determinant | DANSO (<Q>)
| Billing Determinant | DAPERFIP (<Q><R><SP>)
| Billing Determinant | DAPERFOP (<Q><R><SP>)
| Billing Determinant | DARDO (<Q>)
| Billing Determinant | DARRO (<Q>)
| Billing Determinant | DARUO (<Q>)
| Billing Determinant | DASANSQ (<Q>)
| Billing Determinant | DASARDQ (<Q>)
| Billing Determinant | DASARRQ (<Q>)
| Billing Determinant | DASARUQ (<Q>)
| Billing Determinant | DASUO - Cold (<Q><R><SP><ST>)
| Billing Determinant | DASUO - Int (<Q><R><SP><ST>)
| Billing Determinant | DASUO -Hot (<Q><R><SP><ST>)
| Billing Determinant | ENECURVE 3PT Energy Offers (Quantity and Price)
| Billing Determinant | VTPSOFLAG (<Q><R><SP>)
| CSI Event / Data Transfer (16 Billing Determinants) | DAILY_DAMOUTPUT2STL
| Billing Determinant | DAEP (<Q><SP>)
| Billing Determinant | DAES (<Q><SP>)
| Billing Determinant | DAESR (<Q><R><SP>)
| Billing Determinant | DAMCOMMITFLAG (<Q><R><SP>)
| Billing Determinant | DASP (<C>)
| Billing Determinant | DASPP (<SP>)
| Billing Determinant | DASTARTTYPE (<Q><R><SP>)
| Billing Determinant | MCPCNS (<M>)
| Billing Determinant | MCPCRD (<M>)
| Billing Determinant | MCPCRR (<M>)
| Billing Determinant | MCPCRU (<M>)
| Billing Determinant | PCNSR (<Q><R><M>)
| Billing Determinant | PCRDR (<Q><R><M>)
| Billing Determinant | PCRRR (<Q><R><M>)
| Billing Determinant | PCRUR (<Q><R><M>)
| Billing Determinant | RTOBL (<Q><SRSP><SKSP>)
| CSI Event / Data Transfer (11 Billing Determinants) | DAILY_DRUCINPUT2STL
| Billing Determinant | HHSLSNAP_<Q>_<R>_<SP>_<RUC>
| Billing Determinant | HLSLSNAP_<Q>_<R>_<SP>_<RUC>
| Billing Determinant | HNSSNAP_<Q>_<R>_<SP>_<RUC>
| Billing Determinant | HRDSNAP_<Q>_<R>_<SP>_<RUC>
| Billing Determinant | HRRSNAP_<Q>_<R>_<SP>_<RUC>
| Billing Determinant | HRUSNAP_<Q>_<R>_<SP>_<RUC>
| Billing Determinant | RTQQEPSNAP (<Q><SP><RUC>)
| Billing Determinant | RTQQESSNAP (<Q><SP><RUC>)
| Billing Determinant | RUCCPSNAP (<Q><RUC>)
| Billing Determinant | RUCCSSNAP (<Q><RUC>)
| Billing Determinant | STATUSSNAP (<Q><R><SP><RUC>)
| CSI Event / Data Transfer ( 4 Billing Determinants) | DAILY_DRUCOUTPUT2STL
| Billing Determinant | DSTARTTYPE (<Q><R><SP>)
| Billing Determinant | RUC (<Q><R><SP><RUC>)
| Billing Determinant | RUC Processes
| Billing Determinant | RUCD (<Q><R><SP><RUC>)
| CSI Event / Data Transfer (11 Billing Determinants) | DAILY_EMS2STL
| Billing Determinant | EECP
| Billing Determinant | FQDEVFLAG
| Billing Determinant | GSSPLITSCA_<R>
| Billing Determinant | LFORERCOT
| Billing Determinant | ONDSRFLAG <Q><R><SP>
| Billing Determinant | RRSFLAG
| Billing Determinant | TELHSLFLAG_<Q>_<R>_<SP>
| Billing Determinant | TGFTH <Q><R><SP>
| Billing Determinant | TOFO_<Q>_<R>_<SP>
| Billing Determinant | TWAR <Q><R><SP>
| Billing Determinant | TWTG_<Q>_<R>_<SP>
| CSI Event / Data Transfer (29 Billing Determinants) | DAILY_ENDOFADJ2STL
| Billing Determinant | DEC Energy Offers (Quantity and Price)
| Billing Determinant | ENECURVE 3PT Energy Offers (Quantity and Price)
| Billing Determinant | HHSLADJ_<Q>_<R>_<SP>
| Billing Determinant | HLSLADJ_<Q>_<R>_<SP>
| Billing Determinant | HNSADJ_<Q>_<R>_<SP>
| Billing Determinant | HRDADJ_<Q>_<R>_<SP>
| Billing Determinant | HRRADJ_<Q>_<R>_<SP>
| Billing Determinant | HRUADJ_<Q>_<R>_<SP>
| Billing Determinant | HSL (<Q><R><SP>)
| Billing Determinant | INC Energy Offers (Quantity and Price)
| Billing Determinant | LSL (<Q><R><SP>)
| Billing Determinant | MEO (<Q><R><SP>)
| Billing Determinant | NSFQ (<Q>)
| Billing Determinant | RDFQ (<Q>)
| Billing Determinant | RMRAFLAG (<Q><R><SP>)
| Billing Determinant | RRFQ (<Q>)
| Billing Determinant | RTPERFIP (<Q><R><SP>)
| Billing Determinant | RTPERFOP (<Q><R><SP>)
| Billing Determinant | RTQQEPADJ (<Q><SP>)
| Billing Determinant | RTQQESADJ (<Q><SP>)
| Billing Determinant | RUCCPADJ (<Q>)
| Billing Determinant | RUCCSADJ (<Q>)
| Billing Determinant | RUFQ (<Q>)
| Billing Determinant | SSQ (<Q><SRSP><SKSP>)
| Billing Determinant | SSSK (<Q><SKSP>)
| Billing Determinant | SSSR (<Q><SRSP>)
| Billing Determinant | SUO - Cold (<Q><R><SP><ST>)
| Billing Determinant | SUO - Hot (<Q><R><SP><ST>)
| Billing Determinant | SUO - Int (<Q><R><SP><ST>)
| CSI Event / Data Transfer ( 2 Billing Determinants) | DAILY_FINAL2STL
| Billing Determinant | RTQQEP (<Q><SP>)
| Billing Determinant | RTQQES (<Q><SP>)
| CSI Event / Data Transfer (11 Billing Determinants) | DAILY_HRUCINPUT2STL
| Billing Determinant | HHSLSNAP_<Q>_<R>_<SP>_<RUC>
| Billing Determinant | HLSLSNAP_<Q>_<R>_<SP>_<RUC>
| Billing Determinant | HNSSNAP_<Q>_<R>_<SP>_<RUC>
| Billing Determinant | HRDSNAP_<Q>_<R>_<SP>_<RUC>
| Billing Determinant | HRRSNAP_<Q>_<R>_<SP>_<RUC>
| Billing Determinant | HRUSNAP_<Q>_<R>_<SP>_<RUC>
| Billing Determinant | RTQQEPSNAP (<Q><SP><RUC>)
| Billing Determinant | RTQQESSNAP (<Q><SP><RUC>)
| Billing Determinant | RUCCPSNAP (<Q><RUC>)
| Billing Determinant | RUCCSSNAP (<Q><RUC>)
| Billing Determinant | STATUSSNAP (<Q><R><SP><RUC>)
| CSI Event / Data Transfer ( 5 Billing Determinants) | DAILY_HRUCOUTPUT2STL
| Billing Determinant | RUC (<Q><R><SP><RUC>)
| Billing Determinant | RUC Processes
| Billing Determinant | RUCD (<Q><R><SP><RUC>)
| Billing Determinant | STARTTYPE (<Q><R><SP>)
| Billing Determinant | STARTTYPE +1
| CSI Event / Data Transfer ( 1 Billing Determinant) | DAILY_OUTPUTSCH2STL
| Billing Determinant | TWOS (<Q><R><SP>)
| CSI Event / Data Transfer ( 1 Billing Determinant) | DAILY_RTOPTPRINFO2STL
| Billing Determinant | RTOPTPRINFO_<SRSP>_<SKSP>
| CSI Event / Data Transfer ( 1 Billing Determinant) | DAILY_RTRMPR2STL
| Billing Determinant | RTRMPR_<B>
| CSI Event / Data Transfer ( 9 Billing Determinant) | DAILY_SASMOUTPUT2STL
| Billing Determinant | Ancillary Service Markets
| Billing Determinant | MCPCNS (<M>)
| Billing Determinant | MCPCRD (<M>)
| Billing Determinant | MCPCRR (<M>)
| Billing Determinant | MCPCRU (<M>)
| Billing Determinant | PCNSR (<Q><R><M>)
| Billing Determinant | PCRDR (<Q><R><M>)
| Billing Determinant | PCRRR (<Q><R><M>)
| Billing Determinant | PCRUR (<Q><R><M>)
| CSI Event / Data Transfer ( 1 Billing Determinant) | DAILY_SPP2STL
| Billing Determinant | RTSPP (<SP>)
| CSI Event / Data Transfer | MONTHLY_AUCTION2STL
CSI 5.4 (to Lodestar)
| CSI Event / Data Transfer | DAILY_DAMPODOUTPUT2STL
| Billing Determinant | RTOPT (<CO><SRSP><SKSP>)
| Billing Determinant | RTOPTR (<CO><SRSP><SKSP>)
| CSI Event / Data Transfer | DAILY_DAMSFTOUTPUT2STL
| Billing Determinant | CRRSFTVIOL (<C>)
| Billing Determinant | DAWASF (<SP><C>)
| CSI Event / Data Transfer | DAILY_DRUCINPUT2STL
| Billing Determinant | DCIMPSNAP (<Q><SP><RUC>)
| CSI Event / Data Transfer | DAILY_EMS2STL
| Billing Determinant | AABP_<Q>_<SP>_<R>
| Billing Determinant | CCTELEMETERSTATUS
| Billing Determinant | DEVDIRFLAG_<Q>_<R>_<SP>
| Billing Determinant | LACTERCOT
| Billing Determinant | RESSTATSYNCH
| Billing Determinant | TELRESFLAG_<Q>_<R>_<SP>
| CSI Event / Data Transfer | DAILY_ENDOFADJ2STL
| Billing Determinant | STATUSADJ (<Q><R><SP>)
| Billing Determinant | EOCQFFLAG
| Billing Determinant | BSSAFLAG (<Q><R>)
| Billing Determinant | DCIMPADJ(<Q><SP>)
| Billing Determinant | NSRP (<Q>)
| Billing Determinant | RDRP (<Q>)
| Billing Determinant | RRRP (<Q>)
| Billing Determinant | RTSANSQ (<Q>)
| Billing Determinant | RTSARDQ (<Q>)
| Billing Determinant | RTSARRQ (<Q>)
| Billing Determinant | RTSARUQ (<Q>)
| Billing Determinant | RURP (<Q>)
| CSI Event / Data Transfer | DAILY_FINAL2STL
| Billing Determinant | RTDCIMP (<Q><SP>)
| Billing Determinant | RTDCNEEXP (<Q><SP>)
| Billing Determinant | SWCAP
| CSI Event / Data Transfer | DAILY_HRUCINPUT2STL
| Billing Determinant | DCIMPSNAP (<Q><SP><RUC>)
| CSI Event / Data Transfer | DAILY_NDRTFGRPR2STL
| Billing Determinant | NDRTFGRPR (<FGR>)
| CSI Event / Data Transfer | DAILY_OUTPUTSCH2STL
| Billing Determinant | TWOSQ (<Q><R><SP>)
| Billing Determinant | TWOSFLAG (<Q><R><SP>)
| CSI Event / Data Transfer | DAILY_SCED2STL
| Billing Determinant | DSRFLAG
| CSI Event / Data Transfer | YEARLY_AUCTION2STL
| Billing Determinant | FGRPAMT
| Billing Determinant | FGRSAMT
| Billing Determinant | OBLPAMT
| Billing Determinant | OBLSAMT
| Billing Determinant | OPTPAMT
| Billing Determinant | OPTSAMT
| Billing Determinant | PCRROBLAMT
| Billing Determinant | PCRROPTAMT
Interfaces
CSI 5.5 (to Lodestar)
* Description: | CSI Event / Data Transfer | DAILY_DAMOUTPUT2STL
| Bill Determinant | DASPFGR (<C>)
| CSI Event / Data Transfer | DAILY_DAMRUNTIME2STL
| Bill Determinant | Time DAM was run webservice
| CSI Event / Data Transfer | DAILY_DAMSFTOUTPUT2STL
| Bill Determinant | CRRSFTVIOLFGR (<C>)
| CSI Event / Data Transfer | DAILY_DRUCINPUT2STL
| Bill Determinant | RUCHSL (<Q><R><SP><RUC>)
| CSI Event / Data Transfer | DAILY_HRUCINPUT2STL
| Bill Determinant | RUCHSL (<Q><R><SP><RUC>)
| EIP TIBCO Adapter | S&B to CMM: Invoices
| EIP TIBCO Adapter | S&B to CMM: Statements
| EIP TIBCO Adapter | S&B to CMM: Payments & Refunds
| EIP TIBCO Adapter | S&B to CMM: Data
| EIP TIBCO Adapter | NMMS to S&B
CSI6.2 (to Lodestar)
| CSI Operational Readiness | DST (Longday-Shortday)
| CSI Support | Reports
| CSI Support | GUI - Part II

## CDR Deliveries
Project Deliveries | Description
CDR 3C
* Descripton | EMS Reports | EMS --> CDR3C --> MIS (State Estimator 15 min Ave of Loads)
| EMS Reports | EMS --> CDR3C --> MIS (Transformer Flows, Voltages, & Tap Positions)
| EMS Reports | EMS --> CDR3C --> MIS (Dynamic Rating Deviation Data)
| EMS Reports | EMS --> CDR3C --> MIS (Temp Removed Contingencies)
| MMS Reports | MMS --> CDR3C --> MIS (SASM Aggregated Ancillary Service Offer Curve)
| MMS Reports | MMS --> CDR3C --> MIS (Manual over-riding of HDLs and LDLs)
| CDR Infrastructure | Appworx workflows for Load Balancing
| CDR Infrastructure | Client infrastructure for Load Balancing
| CDR Infrastructure | Server infrastructure for Load Balancing
| CDR Infrastructure | Single Site DR for Load Balancing
| CDR Infrastructure | Load balancing for Load Balancing
| CDR Infrastructure | Velocity Templates to client - Optimization
| CDR Infrastructure | DB Call optimization from Client - Optimization
| CDR Infrastructure | Handling TimeOuts - WS, DB, Large Reports - Optimization
| CDR Infrastructure | Spool audit log for CDR Db Failover
| CDR Infrastructure | Report XSDs
| CDR Infrastructure | Update detailed design for section 1
CDR 4
* Descripton | CDR Infrastructure | Cross Site Failover
| CDR Infrastructure | Design, development and unit testing of application GUI for reproducability and services
| CDR Infrastructure | RSS Replication
| CDR Infrastructure | Stress & performance Testing
| EMS Reports | State Estimator Load Report
CDR 4A
* Descripton | Refactor based on final delivery of MMS, EMS

## EDW Deliveries
Project Deliveries | Description
EDW1C (Against Active EDS)
| EMS Reports | NP6-654-ER Total Regulation Report
EDW2B
| Shadow Settlement Extracts | NP12-743 DAM Consolidated Operating Day Extract
| Shadow Settlement Extracts | NP12-177 DAM Consolidated Operating Day Extract
| Shadow Settlement Extracts | NP12-747 Real Time Market Consolidated Operating Day Extract
| Shadow Settlement Extracts | NP12-749 Real Time Market Operating Day Extract
| Shadow Settlement Extracts | NP12-465 Public Reference Data Extract
| Shadow Settlement Extracts | NP12-753 Settlement Input Data Extract
EDW2C
SE Statistics Extract
SE reports:
Electrical Buses Not Meeting Telemetry Accuracy Requirements Rpt (NP3-363-ER)
MW Residuals SE vs. RTCA Base Case for Congested Transmission Element Rpt (NP3-579-ER)
MW Residuals vs. Telemetry for Maor Transmission Elements Rpt (NP3-581-ER)
MW Residuals vs. Telemetry for Congested Transmission Elements Rpt (NP3-580-ER)
State Estimator Convergence Rpt (NP3-578-ER)
Voltage Residuals SE vs Telemetry for Critical Buses Rpt (NP3-582-ER)
Monthly Telemetry reports:
NP8-284-ER ICCP Link Availability Statistics
NP8-365-ER Monthly Market Participant Real Time Availability Statistics
Quarterly Telemetry reports:
NP8-146-ER Critical Data Availability Statistics
NP8-475-ER Quarterly Point Availability Statistics
EDW-MMS R1 (Extracts)
NP6-584-ER Security Violations & Binding Transmission Constraints
EDW-MMS R1 (Section 8 Data)
NP8-140-ER COP Report
NP8-568-ER RUC Report
EDW-OS R1 (Reports)
Outage Scheduler reports:
Transmission advanced outage schedule statistics
Resource Advanced Outage Schedule Statistics
Internal Resource Advanced Outage Schedule Statistics
Monthly Planned vs. Actual Resource Outage Statistics
Annual Planned vs. Actual Resource Outage Statistics
Monthly Planned vs. Actual Transmission Outage Statistics
Annual Planned vs. Actual Transmission Outage Statistics
EDW-EMS R1 (Reports)
NP6-216-ER Dynamically Adjusted Transmission Elements
EDW-EMS R1 (Section 8 Reports)
EMS Section 8 reports:
Non-spin performance report NP8-383
Provided regulation NP8-501
Historic non-spin availability NP8-504
Controllable load qualification test NP8-517
Responsive reserve performance report NP8-541
Responsive reserve availability report NP8-542
QSE ICCP Link Availability NP8-472-ER
EDW-COMS R1 (Non-Shadow Settlment Extracts)
COMS Non-Shadow Settlment extracts:
NP9-308 and NP9-565 Late Fee Extract
ESI ID Service History & Usage extract: Daily, Initial, Supplemental
Market Participant Dispute Extract
Settlement Calendar Extract
CRR Auction Revenue Distribution (CARD) Extract
EDW-COMS R1 (COMS Web Services extracts)
COMS Web Services extracts:
Provide all ESI ID extract records (COMS-438)
Provide data aggregation records (COMS-440)
Provide ESI ID extract records for logical keys (COMS-442)
Provide IDR usage data for a trade date (COMS-447)
Provide ESI ID account records (COMS-441)
Provide public data extract (COMS-452)
Provide CMZONE assignments for a trade date (COMS-439)
EDW-MMS Rel 2 MMS NPRR102 Extracts Release 1, EDW migrates extract into ITEST
Release 1 (9 extracts):
48 hr Aggregate Energy Supply Curves from Non-Wind Resources
48 hr Aggregate Energy Supply Curves from WGRs
48 hr Aggregate Minimum Energy Supply Curves
48 hr Aggregate Energy Demand Curve
48 hr Aggregate Cleared Energy Bids and Energy-Only Offers
48 hr Aggregate AS Offers
48 hr Self-Arranged AS
48 hr Cleared DAM AS
48 hr Aggregate Point-to-Point Bids
EDW-MMS Rel 2 MMS NPRR102 Extracts Release 2, EDW migrates extract into ITEST
Release 2 (4 extracts):
48 hr Highest Price Offered in SCED
48 hr Aggregate Supply Curve for Non-Wind Resources
48 hr Aggregate Supply Curve for WGR
48 hr Aggregate Inc/Dec Offer Curves in SCED
EDW-MMS Rel 2 MMS NPRR102 Extracts Release 3, EDW migrates extract into ITEST
Release 3 (13 extracts):
61 day QSE-specific Self Arranged AS in DAM
61 day Generation Resource data in DAM
61 day Generation Resource AS Offers in DAM
61 day Load Resource data in DAM
61 day Load Resource AS Offers in DAM
61 day Settlement Point Data in DAM-Energy Only Offers
61 day Settlement Point Data in DAM-Energy Only Offer Award
61 day Settlement Point Data in DAM-Energy Bids
61 day Settlement Point Data in DAM-Bids Award
61 day Settlement Point Data in DAM-CRR Offers
61 day Settlement Point Data in DAM-CRR Awards
61 day Settlement Point Data Point-to-Point Obligation Bids
61 day Settlement Point Data Point-to-Point Obligation Awards
EDW-MMS R2 (MMS NPRR102 Extracts Release 4)
Release 4 (4 extracts):
61 day QSE-specific Self Arranged AS in SCED
61 day INC/DEC Offer Curves in SCED
61 day DC Tie Power Flow in SCED
7 day Event trigger Posting when LMP exceeds 50xFIP
EDW-MMS R2 (MMS NPRR102 Extracts Release 5)
Release 5 (6 extracts):
48 hr Aggregate Output Schedules for non-DSR
48 hr Aggregate Output Schedules for DSR
48 hr Aggregate Generation Summary
48 hr Aggregate Load Summary
48 hr Aggregate Dynamically Schedules Resources and Load
48 hr Resource Control Report
EDW-MMS R2 (MMS NPRR102 Extracts Release 6)
Release 6 (4 extracts):
61 day Generation Resource data in SCED
61 day Load Resource data in SCED
61 day Dynamically Scheduled Resource and Loads in SCED
61 day Settlement Metered Net Energy for Generation Resources
EDW-MMS R2 (MMS NPRR102 Extracts Release 7)
Release 7 (20 extracts; 4 for each one listed):
48 hr Aggregate Supply Curve for Non-Wind Resources
48 hr Aggregate Supply Curve for WGR
48 hr Aggregate Output Schedules for DSR
48 hr Aggregate Inc/Dec Offer Curves in SCED
48 hr Point-to-Point Obligation Bids
EDW-MMS R2 (MMS NPRR102 Extracts Release 8)
Release 8 (24 extracts; 4 for each one listed):
48 hr Aggregate Output Schedules for non-DSR
48 hr Aggregate Generation Summary
48 hr Aggregate Energy Supply Curves from Non-wind Resources
48 hr-Aggregate Energy Supply Curves from WGRs
48 hr Aggregate Minimum Energy Supply Curves
48 hr Aggregate Energy Demand Curve

## MIS Portal
Project Deliveries | Description | Description
MIS 9
Real-Time Market Late Fee Invoices "ESI ID Service History & Usage Extract (Daily, Initial, Supplemental)" Settlement Calendar Extract CRR Auction Revenue Distribution (CARD) Invoice
Planned vs. Actual Resource Outage Statistics
Planned vs. Actual Transmission Outage Statistics
Load Profile ID Exceptions
Load Profile Validation Test Reports
Planned Service Four Coincident Peak Calculations
Weather Responsiveness Change Report
Annual Distribution Loss Factors Report
TDSP Approved Distribution Loss Factors – Methodology
Audit Reports
Annual Planning Model Data Submittal Schedule
Black Start Procedure Submittal Report
TSP Backup Plan
RUC Report
QSE Backup Plan
CDR 3C support
MIS 8
EDW - Outage Scheduler Metrics Report
EDW - Critical Data Availability Statistics Report
EDW - ICCP Link Availability Statistics Report
EDW - Monthly Market Participant Real Time Availability
EDW - Quarterly Point Availability Statistics Report
EDW - RARF Receipt Report
EDW - Transmission Advanced Outage Schedule Statistics
EDW - Internal Resource Advanced Outage Schedule
EMS - Dispatch Instructions Compliance Metrics Report
EMS - Operations Shift Schedules
EMS - AVR Test Results and PSS Test Results
EMS - Non-Spin Performance Report
MIS 7
EMS - Black Start Restoration Plan
EMS - Generic Constraints Based on Offline Manual Studies
CDR - Annual Competitive Constraints
CDR - Monthly Competitive Constraints
CDR - Suspended Competitive Constraints
CDR - Temperature Adjusted Dynamic Ratings
CDR - Total Amount of Regulation Services Deployed
CDR - Average Monthly Deviation Data
CDR - Peaker Net Margin and System-Wide Offer Cap
CDR - Dynamic Rating Deviation Data
CDR - Topology Consistency
CDR - Transformer Flows, Voltages and Tap Position
CDR - LMPs by Resource Node
CDR - Settlement Point Prices at Hubs and Load Zones
MIS - All State Estimator Reports and Extracts Page
MIS - Active Public Links (to ercot.com) throughout MIS
MIS - Groups and Rules Landing page (with active links)
MIS - Reports Landing Page (Alpha list of all Reports)
MIS - Notification Portlet

## EIP Adapter Versions
EWS(1.15)
| MMS Adapter |  | * Added SubmitTime to the BidSet header holding Bid request receipt timestamp by ERCOT (MMS4)
| MMS Adapter |  | * Update 3PO with SuMeFipFop and EocFipFop introduced in MMS4
| MMS Adapter |  | * Removed “.. .. but only one point can be specified for RegDown or OffLineNonSpin” restriction from ASOffer, ASPriceCurve based on the input from MMS team.
| MMS Adapter |  | * Added MultiHourBlock to CRR, PTP Oblig, Energy bid and Energy only Offer input tables
| MMS Adapter |  | * Added RRS_ NCLR as a new ASType for SelfArrangedAS
| MMS Adapter |  | * Updated ASOffer with nonControllableLoadFlag flag
| MMS Adapter |  | * 3.3.2 Added RRS_NCLR to the list of ASType for SelfArrangedAS
| Market Information Adapter |  | * Added hourEnding to the BindingConstraints and updated the schema diagram
| Market Information Adapter |  | * Corrected the LoadForecasts MarketInfo Noun to be plural (adding the LoadForecasts container)
| Market Information Adapter |  | * Added marketType to ASObligations to account for DAM or SASM
| Market Information Adapter |  | * 7.2.1 Tagged TransmissionOutage/Opportunity/designatedResource/station and HSL as required per OS.xsd
| Market Information Adapter |  | * Updated LoadDistributionFactors to have name and factor only – consistent with CDR interfaces
| Market Information Adapter |  | * Added Market type to the startup/shutdown instructions with possible values of HRUC, DRUC, and DAM
| Market Information Adapter |  | * Added MarketType to the get AwardSet = DAM/ADJ/RTM/SASM/RUC/SCED
| Market Information Adapter |  | * Merged in MIS Int Specification version .37 - Market Info Nouns into the section 4 of this spec – 4.3.31 thru 4.3.45
| Market Information Adapter |  | * 4.3.26 Unit Availability: Tagged BlackStart and Available megawatts as a place holder for future use.
| Market Information Adapter |  | * Added equipmentType to Dynamic Ratings and Dynamic Ratings Deviations
| Market Information Adapter |  | * Modified CompetitiveConstraints structure to hold new elements CompetitivenessStatus, deleted OperatorOverwrite – consistent with CDR Interface
| Market Information Adapter |  | * Corrected the possible values for MarketType for various Award Sets.
| Market Information Adapter |  | * Reverted back to the original external reporting interface in section 9 – adjusted with supporting MID/MIR interface
| Market Information Adapter |  | * Corrected PTP Obl. MaximumPrice/price
| OS Adapter |  | * Made DisclaimerAck and Disclaimer as required fields for OS
| OS Adapter |  | * Added enumeration to equipment Outage, Outage states. Added 3 more cancellation reasons (EXP, ERR, and ROM)
| OS Adapter |  | * Added notes about OS query StartTime and endTime are optional but they should not be present when an mRID is sent.
| OS Adapter |  | * OS – 7.2.1 Corrected the resourceType choices to UL or LR
| OS Adapter |  | * Updated Outage opportunity outages with opportunity duration – consistent with OS application
EWS(1.16)
EWS(1.16) | MMS AsyncAwardsAdapter |  | * Added NCLRFlag to awardedAS (MMS4)
EWS(1.16) | MMS AsyncAwardsAdapter |  | * Added crrOwnerName to Awarded CRR (MMS4)
EWS(1.16) | MMS AsyncAwardsAdapter |  | * Added startType and combinedCycleName to AwardedEnergyOffer (MMS4)
EWS(1.16) | MMS Adapter |  | * MP Resource Parameter Transaction Service (MMS4)
EWS(1.16) | Siebel Adapter (Registration Interface) |  | * Dispute Submission / Query (REG4)
Integration Release 1.0 Deployments
EIP Integration Adapters | Registration Adapter v0.3.0.3
EIP Integration Adapters | Reg -> MMS v0.3.0.2
EIP Integration Adapters | Reg -> CRR v0.3.0.2
EIP Integration Adapters | Reg -> S & B v0.3.0.2
EIP Integration Adapters | CMM-CRRAdapter v0.1.2.8
EIP Integration Adapters | CRR-CMMAdapter v0.1.2.8
EIP Integration Adapters | CRR-CMMP2PAdapter v0.1.0.4
EIP Integration Adapters | CRR-MMSP2PAdapter v0.1.0.4
EIP Integration Adapters | NMMS -> Adapter v0.1.0.2
EIP Integration Adapters | NMMS -> S&B v0.1.0.2
EIP Integration Adapters | NMMS-OS_P2P Adapter v0.1.0.2
EIP Integration Adapters | PlattsAdapter v0.1.0.4
EIP Integration Adapters | Platts-MMSAdapter v0.1.0.2
EIP Integration Adapters | Platts-SnBAdapter v0.1.0.3
EIP Integration Adapters | Windforecaster v0.1.2.6
EIP Integration Adapters | WSRB v0.6.1.27
EIP Integration Adapters | MMS Adapter v0.6.1.27
EIP Integration Adapters | OS Adapter v0.6.1.27
EIP Integration Adapters | MMSAdapterAsyncAwards v0.6.2.28
EIP Integration Adapters | MMSAdapterSynchAwards v0.6.2.28
Integration Release 2.0 Deployments
Interfaces | EMS - MMS interface updated for SCED EMS - MMS interface updated for DAM / RUC EMS - OS Interface Registration Adapter Reg - MMS Reg - CRR Reg - S & B CMM-CRRAdapter CRR-CMMAdapter CRR-MMSP2PAdapter CRR-CMMP2PAdapter NMMS - Adapter NMMS - S&B NMMS-OS_P2P PlattsAdapter Platts-MMSAdapter Platts-SnBAdapter MMS Sync and Async Awards Notifications EMS EMS - CSI | CMM - CSI EMS - CSI CMM - MMS S&B - CMM NMMS - OS OS - NMMS EMS/MMS EWS (CDR-EIP) NMMS - CRR REG - S&B (MP Details) REG - S&B (resource details) REG - MMS REG-CMM | NMMS-EMS NMMS - MMS NMMS - S&B CRR - MMS S&B - CRR REG - NMMS CMM - REG REG - CRR S&B - MMS (Ver cost) S&B - MMS (RMR) S&B - MMS (Cap factor) S&B - MMS (Load Ratio Share) | NMMS --> MIS NMMS-EMS NMMS - MMS NMMS - S&B EMS-Notification (EIP) EMS-Notification (AREVA) EIP notifications
EIP and UI submission items for DAM on latest version of spec (EIP V 1.17?)
* DAM Energy Only Offer
* Ancillary Services Offer
* CRR Offer
* Three-Part Supply Offers for Energy (all Three parts)
* AS Trade
* Energy Trade
* Capacity Trade
* DAM Energy Bid
* PTP Obligation Bid
* Self Arranged Ancillary Services (AS)
* Self Schedule
* DC Tie Schedule