| Flight Schedule for Version 3.0 Flights in 2009 | 0209 |
| --- | --- |
| Activity | Calendar Date |
| Notice from ERCOT Retail Client Services of the next flight for Retail Market Testing sent to ERCOT lists.ercot.com distribution | Dec. 10, 2008 |
| TTPT to finalize scripts | Dec. 31, 2008 |
| Testing Worksheets are unlocked | Jan. 7, 2009 |
| FLIGHT DEADLINE The following 4 steps must be completed by 5pm cpt. on the deadline: CR must have submitted ERCOT LSE Application and Application Fee CR must have filed for PUC REP Certification TW updated on ERCOT Retail Testing Website Send an e-mail of intent to test to ERCOT at: RetailMarketTesting@ercot.com The following steps must be completed by 5pm cpt. on the deadline for current MPs: TW updated on ERCOT Retail Testing Website Send an email of intent to test to ERCOT at: RetailMarketTesting@ercot.com Testing Worksheets are locked at 5pm cpt. | Jan. 14, 2009 |
| ERCOT Retail Client Services verifies that each new Testing Participant has completed Registration testing requirements with ERCOT | Jan. 16, 2009 |
| Verification and communication from PUCT Staff that Testing Participants intending to test have applied for REP Certification | Jan. 16, 2009 |
| Communication from ERCOT Flight Administrator of Testing Participants to each TDSP | Jan. 16, 2009 |
| Communication of Test Certificates from ERCOT Retail Client Services to all Testing Participants | Jan. 20, 2009 |
| TDSPs and ERCOT have completed communication of connectivity testing schedule to each Trading Partner | Jan. 20, 2009 |
| Connectivity Testing Kick Off Conference Call - Mandatory for all Testing Participants (blackout ends) | Jan. 20, 2009 |
| Connectivity Testing begins for all Testing Participants | Jan. 20, 2009 |
| Penny Test (CON52) & ACK55/56 (FA Scripts) begins for all New Testing Participants | Jan. 20, 2009 |
| TDSPs communicate Test bed load to Trading Partners and ERCOT | Feb. 9, 2009 |
| Flight Kick Off Conference Call - Mandatory for all Testing Participants | Feb. 13, 2009 |
| Daily Conference Calls begin – Day 1 Transactions flow | Feb. 16, 2009 |
| Flight tentatively scheduled to conclude; Internal Regression Testing | Mar. 31, 2009 |
| Contingency Testing scheduled to conclude for Flight (blackout starts) | Apr. 17, 2009 |

| Flight Schedule for Version 3.0 Flights in 2009 | 0609 |
| --- | --- |
| Activity | Calendar Date |
| Notice from ERCOT Retail Client Services of the next flight for Retail Market Testing sent to ERCOT lists.ercot.com distribution | Apr. 15, 2009 |
| TTPT to finalize scripts | May 6, 2009 |
| Testing Worksheets are unlocked | May 13, 2009 |
| FLIGHT DEADLINE The following 4 steps must be completed by 5pm cpt. on the deadline: CR must have submitted ERCOT LSE Application and Application Fee CR must have filed for PUC REP Certification TW updated on ERCOT Retail Testing Website Send an e-mail of intent to test to ERCOT at: RetailMarketTesting@ercot.com The following steps must be completed by 5pm cpt. on the deadline for current MPs: TW updated on ERCOT Retail Testing Website Testing Worksheets are locked at 5pm cpt. | May 20, 2009 |
| ERCOT Retail Client Services verifies that each new Testing Participant has completed Registration testing requirements with ERCOT | May 22, 2009 |
| Verification and communication from PUCT Staff that Testing Participants intending to test have applied for REP Certification | May 22, 2009 |
| Communication from ERCOT Flight Administrator of Testing Participants to each TDSP | May 22, 2009 |
| Communication of Test Certificates from ERCOT Retail Client Services to all Testing Participants | May 26, 2009 |
| TDSPs and ERCOT have completed communication of connectivity testing schedule to each Trading Partner | May 26, 2009 |
| Connectivity Testing Kick Off Conference Call - Mandatory for all Testing Participants (blackout ends) | May 26, 2009 |
| Connectivity Testing begins for all Testing Participants | May 26, 2009 |
| Penny Test (CON52) & ACK55/56 (FA Scripts) begins for all New Testing Participants | May 26, 2009 |
| TDSPs communicate Test bed load to Trading Partners and ERCOT | Jun. 15, 2009 |
| Flight Kick Off Conference Call - Mandatory for all Testing Participants | Jun. 19, 2009 |
| Daily Conference Calls begin – Day 1 Transactions flow | Jun. 22, 2009 |
| Flight tentatively scheduled to conclude; Internal Regression Testing | Aug. 4, 2009 |
| Contingency Testing scheduled to conclude for Flight (blackout starts) | Aug. 25, 2009 |
| Flight Schedule for Version 3.0 Flights in 2009 | 1009 |
| Activity | Calendar Date |
| Notice from ERCOT Retail Client Services of Retail Testing Orientation meeting sent to ERCOT lists.ercot.com distribution | Aug. 5, 2009 |
| TTPT to finalize scripts | Aug. 26, 2009 |
| Testing Worksheets are unlocked. | Sept. 2, 2009 |
| FLIGHT DEADLINE The following 4 steps must be completed by 5pm cpt. on the deadline: CR must have submitted ERCOT LSE Application and Application Fee CR must have filed for PUC REP Certification TW updated on ERCOT Retail Testing Website Send an e-mail of intent to test to ERCOT at: RetailMarketTesting@ercot.com The following steps must be completed by 5pm cpt. on the deadline for current MPs: TW updated on ERCOT Retail Testing Website Send an email of intent to test to ERCOT at: RetailMarketTesting@ercot.com Testing Worksheets are locked at 5pm cpt. | Sept. 9, 2009 |
| ERCOT Retail Client Services verifies that each new Testing Participant has completed Registration testing requirements with ERCOT | Sept. 11, 2009 |
| Verification and communication from PUCT Staff that Testing Participants intending to test have applied for REP Certification | Sept. 11, 2009 |
| Communication from ERCOT Flight Administrator of Testing Participants to each TDSP | Sept. 11, 2009 |
| Communication of Test Certificates from ERCOT Retail Client Services to all Testing Participants | Sept. 14, 2009 |
| TDSPs and ERCOT have completed communication of connectivity testing schedule to each Trading Partner | Sept. 14, 2009 |
| Connectivity Testing Kick Off Conference Call - Mandatory for all Testing Participants (blackout ends) | Sept. 15, 2009 |
| Connectivity Testing begins for all Testing Participants | Sept. 15, 2009 |
| Penny Test (CON52) & ACK55/56 (FA Scripts) begins for all New Testing Participants | Sept. 15, 2009 |
| TDSPs communicate Test bed load to Trading Partners and ERCOT | Sept. 28, 2009 |
| Flight Kick Off Conference Call - Mandatory for all Testing Participants | Oct. 2, 2009 |
| Daily Conference Calls begin – Day 1 Transactions flow | Oct. 5, 2009 |
| Flight tentatively scheduled to conclude; Internal Regression Testing | Nov. 17, 2009 |
| Contingency Testing scheduled to conclude for Flight (blackout starts) | Dec. 8, 2009 |