## Slide 1: TPTF Update for TAC September 4, 2008 Stacy Bridges sbridges@ercot.com
http://nodal.ercot.com <number>
Notes: <number>

## Slide 2: Agenda:
http://nodal.ercot.com <number>
Item | Description | Purpose
1. Meeting Summary | Summary of recent TPTF activities | For Review
2. NPRR Summary | Summary of NPRR activity at TPTF in August | For Review
3. Vote Summary | Summary of recent TPTF Votes | For Review
4. Next Meetings | Upcoming activities | For Review
5. Approval of Milestones | Request TAC acknowledge TPTF completion of the following Milestones: MMS DAM and SASM Requirements MIS/CRR/NMMS CRR Map Requirements | For Vote
6. Approval of Readiness Metrics | Request TAC approving ERCOT moving forward with these new Readiness Metrics: MP21, Wind Generating Resources ICCP Telemetry MP22, New Entrant Readiness Request TAC approving ERCOT moving forward with these completed Readiness Metrics: MP2, QSE with Resources Connectivity to EDS Environment MP3, QSE with Resources Upload of SCED Offers to EDS MP5, ICCP Point to Point Telemetry Test MP8, QSE Ability to Submit Transactions Via MIS MP9, QSE Ability to Submit Web Service Transactions | For Vote
Notes: <number>

## Slide 3: Agenda:
http://nodal.ercot.com <number>
Item | Description | Purpose
6. Approval of Readiness Metrics (continued) | Request TAC approve ERCOT moving forward with these revised Readiness Metrics: MP1, MP Engagement MP6, QSER and TSP Compliance with the Nodal Protocols Section 3.10.7.5 Telemetry Criteria MP10, Mapping of Resources to Resource Nodes and Resources to EPS Meters MP11, MP Registration Activities MP12, MP Completes Nodal Market Related Training MP13, MP Completes Nodal Operations Related Training MP14-A, MP EDS 2, Release 3 Trials Participation MP14-B, MP EDS 2, Release 4 Trials Participation MP14-C, MP EDS 2, TSP Model Validation Participation MP15-A, MP EDS 3, Releases 5 and 6 Participation MP15-B, MP EDS 3, Release 7 Trials Participation MP17, MP Qualification Activities MP19, Load Serving Entitles Engagement and Readiness MP20, MP Ability to Submit Outage - Connectivity Test | For Vote
Notes: <number>

## Slide 4
http://nodal.ercot.com <number>
Meeting Summary:
TPTF met two times since the last TAC Meeting:
  August 11 – 12, 2008
  August 25 – 27, 2008
Notes: <number>

## Slide 5
http://nodal.ercot.com <number>
Meeting Summary – August 11 – 12:
On August 11, TPTF discussed:
  Nodal Status Report
    Discussed the status of the nodal program, including the nodal delivery approach, the nodal reporting structure, the status of the CIM Importer and other software deliveries, key dates for the new integrated nodal program schedule, and the nodal budget
  Project Status Updates
    Received update on the status of nodal projects, including NMMS, EMS, MMS, CRR, COMS, EIP, and INT
  Schedule Revision Updates
    Discussed drivers, benefits, risks, and progress for the new integrated nodal program schedule
  EDS Status Update
  DAM Process Overview
    Received an overview of DAM Processes and the DAM Desktop Operating Procedure
Notes: <number>

## Slide 6
http://nodal.ercot.com <number>
Meeting Summary – August 11 – 12:
On August 12, TPTF discussed:
  Verifiable Cost Implementation Plan
    Reviewed market comments for the Verifiable Cost Implementation Plan v0.17
    TPTF deferred discussion of this document until after the TPTF reviews the delivery dates proposed in the new integrated nodal program schedule
  NPRR145, PPAs as Resource-Specific Verifiable Costs Documentation
    Reviewed market comments for NPRR145
    Discussed issues related to PPA confidentiality and to the guidelines identified for submitting PPAs as Resource-specific verifiable costs documentation
    The TPTF consensus was to not submit formal comments to the Protocol Revision Subcommittee (PRS)
  NPRR144, Five RUC Deployments Needed Before Requiring Verifiable Costs PRS
    Reviewed market comments for NPRR144, including recommendation to change the timeline for requiring submissions of verifiable costs so that it is applicable to a single calendar year rather than a rolling 12-month period
    TPTF recognized NPRR144 as “Needed for Go-Live” and endorsed formal comments to be submitted to PRS
Notes: <number>

## Slide 7
http://nodal.ercot.com <number>
Meeting Summary – August 11 – 12:
On August 12, TPTF discussed (continued):
  Working Readiness Metrics Inventory
    TPTF deferred approving the revised Readiness Metrics until the August 25-27 TPTF meeting
  NPRR102, Implementation of PUC Subst. R. 25.505(f), Publication of Resource and Load Information
    TPTF recognized NPRR102 as “Needed for Go-Live” and endorsed formal comments to be submitted to PRS
  NPRR146, ICCP Telemetry Information Submittals
    TPTF assigned NPRR146 to the Quick Response Working Group (QRWG) to address ERCOT Staff comments (dated Aug. 8) and potential impacts for NMMS; additional discussion scheduled for the August 25-27 TPTF meeting
  NPRR141, TDSP Energy Storage for Reliability
    TPTF endorsed formal comments to be submitted to PRS to indicate that the metering exemption identified for “storage devices installed as part of a transmission reliability project” applied specifically to the battery units included in the reliability improvements for Presidio approved by the ERCOT Board of Directors in July 2008
    TPTF deferred assigning an essentiality status (Needed for “Go-Live”, Nodal Approved Post “Go-Live, or Deferred Projects) for NPRR141 until after it is reviewed by PRS
Notes: <number>

## Slide 8
http://nodal.ercot.com <number>
Meeting Summary – August 25 – 27:
On August 25, TPTF discussed:
  Nodal Status Update
    Discussed recent progress and upcoming key review dates for the new Nodal Integrated Program Schedule
  Project Status Updates
  Change-Control Update
    Discussed Post-Baseline 2 NPRRs categorized by approval status, essentiality status, schedule impact, cost impact, and relationship to the integrated nodal program schedule
  Quality Center Update
    Discussed Quality Center Reports and the current approach to leveraging historical testing data for the new integrated nodal program schedule
  Readiness Update
    Discussed the status of ERCOT and Market Participant readiness on the Nodal Readiness Scorecard
  Process Update
    Discussed the Business Process for RUC
  NPRR141, TDSP Energy Storage for Reliability
    TPTF deferred assigning an essentiality status for NPRR141 to await PUCT and PRS action on battery ownership issues related to the companion PRR768
Notes: <number>

## Slide 9
http://nodal.ercot.com <number>
Meeting Summary – August 25 – 27:
On August 25, TPTF discussed (continued):
  Nodal Readiness Metrics
    On August 25, 2008, TPTF endorsed ERCOT moving forward with the new Readiness Metric MP22, New Entrant Readiness and endorsed ERCOT moving forward with revisions to the following Readiness Metrics:
      MP1, MP Engagement
      MP6, QSER and TSP Compliance with the Nodal Protocols Section 3.10.7.5
      MP10, Mapping of Resources to Resource Nodes and Resources to EPS Meters
      MP11, MP Registration Activities
      MP12, MP Completes Nodal Market Related Training
      MP13, MP Completes Nodal Operations Related Training
      MP14-A, MP EDS 2, Release 3 Trials Participation
      MP14-B, MP EDS 2, Release 4 Trials Participation
      MP14-C, MP EDS 2, TSP Model Validation Participation
      MP15-A, MP EDS 3, Releases 5 and 6 Participation
      MP15-B, MP EDS 3, Release 7 Trials Participation
      MP17, MP Qualification Activities
      MP19, Load Serving Entitles Engagement and Readiness
      MP20, MP Ability to Submit Outage - Connectivity Test
    This endorsement carried by roll-call vote with 100% in favor and one abstention (Calpine). The Consumer Market Segment was not represented for the vote.
Notes: <number>

## Slide 10
http://nodal.ercot.com <number>
Meeting Summary – August 25 – 27:
On August 25, TPTF discussed (continued):
  Nodal Readiness Metrics (continued)
    On August 25, 2008, TPTF endorsed forwarding the following Readiness Metrics to TAC for concurrence that these metrics have been completed as presented by ERCOT staff and as attested to by the EDS Test Team:
      MP2, QSE with Resources Connectivity to EDS Environment
      MP3, QSE with Resources Upload of SCED Offers to EDS
      MP5, ICCP Point to Point Telemetry Test
      MP8, QSE Ability to Submit Transactions Via MIS
      MP9, QSE Ability to Submit Web Service Transactions
    The endorsement carried by roll-call vote with 100% in favor and two abstentions (Calpine, CitiGroup). The Consumer Market Segment was not represented for the vote.
Notes: <number>

## Slide 11
http://nodal.ercot.com <number>
Meeting Summary – August 25 – 27:
On August 26, TPTF discussed:
  NPRR146, ICCP Telemetry Information Submittals
    TPTF endorsed formal TPTF comments for NPRR146 to be submitted to PRS; TPTF did not assign an essentiality status for go-live
  EDS Service Level Agreement (SLA) for Nodal EDS Environments
    Discussed availability targets, Outage windows, and systems monitoring in the EDS environment
    Discussed revisions for the recently updated EDS SLA for Nodal EDS Environments
    TPTF approved the updated EDS SLA for Nodal EDS Environments
  System Implementation Group (SIG) White Papers
    Reviewed updates to reflect market feedback for the following SIG White Papers:
      SIG0008 Non-Modeled Generation
      SIG0002 Private Use Networks
      SIG0022 Transmission Constraint Model for RT CCP Dispatch
      SIG0020 Rounding of MW Values
      SIG0011 Net Generation
      SIG0009 Resource Node Location
Notes: <number>

## Slide 12
http://nodal.ercot.com <number>
Meeting Summary – August 25 – 27:
On August 26, TPTF discussed (continued):
  Registration Update
    Discussed status of metric MP10, Mapping of Resources to Resource Nodes and Resources to Revenue Quality Meters
    Discussed status of metric MP11, MP Registration Activities
    Discussed Draft Generation Site Topology Form and Non-Modeled Generation Declaration Form
  NPRR137, Synchronization and Update of Section 21
    TPTF tabled discussion NPRR137 until after the ERCOT Board of Directors acts upon PRR753, PRR Appeals Process
  NPRR140, Revision to CRR Obligation Margin Adder
    TPTF deferred discussion of NPRR140 to allow CMM/CRR SMEs to address market comments
  NPRR148, Treatment of Financial Information as Confidential
    TPTF endorsed formal TPTF comments for NPRR148 to be submitted to PRS
  NPRR147, DAM Short Pay Charges
    TPTF tabled discussion of NPRR147, noting that some policy considerations need to be resolved before TPTF can make a nodal implementation decision. TPTF recommended that PRS refer the policy issues to the WMS for further discussion
Notes: <number>

## Slide 13
http://nodal.ercot.com <number>
Meeting Summary – August 25 – 27:
On August 26, TPTF discussed (continued):
  NPRR139, Available Credit Limit (ACL), Estimated Aggregate Liability (EAL), Future Credit Exposure (FCE) Calculation Updates
    TPTF endorsed formal comments for NPRR139 to be submitted to PRS and recognized NPRR139 as “Needed for Go-Live”
  Review of changes to media appeal requirements:
    Endorsed NPRR142, EECP Media Appeal Change, and recognized it as “Needed for Go-Live”
    Endorsed NOGRR022, EECP Media Appeal Change
Notes: <number>

## Slide 14
http://nodal.ercot.com <number>
Meeting Summary – August 25 – 27:
On August 27, TPTF discussed:
  MIS/CRR/NMMS CRR Map Requirements
    Reviewed market comments and approved the Requirements as submitted
  Texas Nodal Market Single-Entry Model (SEM) Go-Live Procedure
    TPTF reviewed market comments, recommended additional revisions, and approved this procedure document as amended by TPTF
  Draft NPRR, Clarify Definition of a Generator Output Breaker in the Outage Scheduler
    TPTF reviewed this draft NPRR, recommended that it be submitted to PRS by the sponsor, and requested the opportunity to review it again once the NPRR is processed by Market Rules
  Outage Scheduler Update
    Discussed options to address previous TPTF request to provide functionality for QSEs and Resources to enter their own Outages in the nodal Outage Scheduler
    Discussed the need to clearly indicate QSE/Resource accountability for any equipment Outages entered in proxy by TSPs on a contract basis
    TPTF deferred further discussion until additional impact analyses can be performed by ERCOT and the vendor for addressing Outage entry issues via expanded Owner/Operator roles, metric measurement, and possible Nodal Protocol changes
Notes: <number>

## Slide 15
http://nodal.ercot.com <number>
NPRR Summary - NPRR Activity at TPTF in August:
NPRR | Description | Essentiality Status | TPTF Discussion
Draft | Clarify Definition of a Generator Output Breaker in OS | Pending | September 9
Draft | Generation Resource Fixed Quantity Block Offer | Pending | September 9
NPRR102 | Implementation of PUC Subst. R. 25.505(f), Publication of Resource and Load Information | Needed for Go-Live | August 12
NPRR124 | Resource Node Updated Definitions | Needed for Go-Live | August 12
NPRR137 | Synchronization and Update of Section 21 | Pending: | Discussion tabled at TPTF pending Board Action on PRR753
NPRR139 | ACL, EAL, FCE Calculation Updates | Needed for Go-Live | August 26
NPRR140 | Revision to CRR Obligation Margin Adder | Pending | September 8
NPRR141 | TDSP Energy Storage for Reliability | Pending PRS action on PRR768 | August 12
NPRR142 | EECP Media Appeal Change | Needed for Go-Live | August 26
NPRR143 | Section 9.9.1, Invoice Recipient Payment to ERCOT for the CRR Auction, Clean-up | Pending | September 8
NPRR144 | Five RUC Deployments Needed Before Requiring Verifiable Costs PRS | Needed for Go-Live | August 12
NPRR145 | PPAs as Resource-Specific VC Documentation | Pending | August 12
NPRR146 | ICCP Telemetry Information Submittals | Pending | August 25
NPRR147 | DAM Short Pay Changes | Pending | Discussion tabled at TPTF pending WMS Action
NPRR148 | Treatment of Financial Information as Confidential | Pending | August 26
Notes: <number>

## Slide 16
Vote Summary: August 11 - 12, 2008
Vote Item | Sector | For | Against | Abstention
On August 12, 2008, TPTF reviewed NPRR102 and endorsed formal comments to be submitted to PRS | Cooperative | ■ |  | 
 | Municipal | ■ |  | 
 | Investor Owned Utility | ■ |  | Luminant, AEP
 | Independent Generator | ■ |  | 
 | Consumer |  |  | 
 | Independent REP | ■ |  | 
 | Independent Power Marketer | ■ |  | 
Note: the votes in the above summary are available for pick-up from the Aug. 11-12 TPTF Meeting Page.
Vote Item | Sector | For | Against | Abstention
On August 12, 2008, TPTF recognized the following NPRRS as Needed for "Go-Live": NPRR102, NPRR124, NPRR138, NPRR144 | Cooperative | ■ |  | 
 | Municipal | ■ |  | 
 | Investor Owned Utility | ■ |  | 
 | Independent Generator | ■ |  | 
 | Consumer |  |  | City of Allen, City of Eastland
 | Independent REP | ■ |  | 
 | Independent Power Marketer | ■ |  | 
http://nodal.ercot.com <number>
Notes: <number>

## Slide 17
Vote Summary: August 11 - 12, 2008
Vote Item | Sector | For | Against | Abstention
On August 12, 2008, TPTF reviewed NPRR141, TSP and/or DSP Energy Storage for Reliability, and endorsed formal comments to be submitted to PRS | Cooperative | ■ |  | 
 | Municipal | ■ |  | 
 | Investor Owned Utility | ■ |  | Luminant
 | Independent Generator | ■ |  | 
 | Consumer | ■ |  | 
 | Independent REP |  |  | Stream Energy, StarTex Power, Strategic Energy, Accent Energy, Cirro Group, Green Mountain Energy, Integrys Energy
 | Independent Power Marketer |  |  | Shell Energy, Exelon, Reliant
http://nodal.ercot.com <number>
Note: the vote in the above summary is available for pick-up from the Aug. 11-12 TPTF Meeting Page.
Notes: <number>

## Slide 18
Vote Summary: August 11 - 12, 2008
Vote Item | Sector | For | Against | Abstention
On August 12, 2008, TPTF reviewed NPRR144, Five RUC Deployments Needed Before Requiring Verifiable Costs, and endorsed formal comments to be submitted to PRS | Cooperative | ■ |  | 
 | Municipal | ■ |  | 
 | Investor Owned Utility | ■ |  | AEP
 | Independent Generator | ■ |  | 
 | Consumer |  |  | City of Dallas, Town of Flower Mound, City of Allen, City of Eastland
 | Independent REP | ■ |  | 
 | Independent Power Marketer | ■ |  | Reliant
http://nodal.ercot.com <number>
Note: the vote in the above summary is available for pick-up from the Aug. 11-12 TPTF Meeting Page.
Notes: <number>

## Slide 19
Vote Summary: August 25 – 27, 2008
Note: the votes in the above summary are available for pick-up from the Aug. 25-27 TPTF Meeting Page.
Vote Item | Sector | For | Against | Abstention
On August 25, 2008, TPTF endorsed forwarding Readiness Metrics MP2, MP3, MP5, MP8, MP9 to TAC for concurrence that they have been completed as presented by ERCOT staff and as attested to by the EDS Test Team: | Cooperative | ■ |  | 
 | Municipal | ■ |  | 
 | Investor Owned Utility | ■ |  | 
 | Independent Generator | ■ |  | Calpine
 | Consumer |  |  | 
 | Independent REP | ■ |  | 
 | Independent Power Marketer | ■ |  | CitiGroup
http://nodal.ercot.com <number>
Vote Item | Sector | For | Against | Abstention
On August 25, 2008, TPTF reviewed NPRR146, ICCP Telemetry Information Submittals, and endorsed formal comments to be submitted to PRS | Cooperative | ■ |  | 
 | Municipal | ■ |  | 
 | Investor Owned Utility | ■ |  | 
 | Independent Generator |  |  | 
 | Consumer |  |  | City of Allen, City of Eastland
 | Independent REP | ■ |  | 
 | Independent Power Marketer | ■ |  | 
Notes: <number>

## Slide 20
Vote Summary: August 25 – 27, 2008
Vote Item | Sector | For | Against | Abstention
On August 25, 2008, TPTF endorsed ERCOT moving forward with the new Readiness Metric MP22 and the revised Readiness Metrics MP1, MP6, MP10, MP11, MP12, MP13, MP14-A, MP14-B, MP14-C, MP15-A, MP15-B, MP17, MP19, and MP20 | Cooperative | ■ |  | 
 | Municipal | ■ |  | 
 | Investor Owned Utility | ■ |  | 
 | Independent Generator | ■ |  | Calpine
 | Consumer |  |  | 
 | Independent REP | ■ |  | 
 | Independent Power Marketer | ■ |  | 
http://nodal.ercot.com <number>
Note: the vote in the above summary is available for pick-up from the Aug. 25-27 TPTF Meeting Page.
Notes: <number>

## Slide 21
Vote Summary: August 25 – 27, 2008
Vote Item | Sector | For | Against | Abstention
On August 26, 2008, TPTF approved the updated EDS Service Level Agreement (SLA) for Nodal EDS Environments v5.3 | Cooperative | ■ |  | 
 | Municipal | ■ |  | 
 | Investor Owned Utility | ■ |  | 
 | Independent Generator | ■ |  | 
 | Consumer | ■ |  | 
 | Independent REP | ■ |  | 
 | Independent Power Marketer | ■ |  | 
http://nodal.ercot.com <number>
Note: the votes in the above summary are available for pick-up from the Aug. 25-27 TPTF Meeting Page.
Vote Item | Sector | For | Against | Abstention
On August 26, 2008, TPTF reviewed NPRR139, “ACL, EAL, FCE Calculation Updates,” and endorsed formal comments to be submitted to PRS. TPTF recognized NPRR139 as “Needed for Go-Live.” | Cooperative | ■ |  | 
 | Municipal | ■ |  | 
 | Investor Owned Utility | ■ |  | 
 | Independent Generator |  |  | 
 | Consumer |  |  | 
 | Independent REP | ■ |  | 
 | Independent Power Marketer | ■ |  | 
Notes: <number>

## Slide 22
Vote Summary: August 25 – 27, 2008
Vote Item | Sector | For | Against | Abstention
On August 26, 2008, TPTF endorsed the changes for EECP Media Appeal in NPRR142 and NOGRR022 as submitted and recognized the change as "Needed for Go-Live" | Cooperative | ■ |  | 
 | Municipal | ■ |  | 
 | Investor Owned Utility | ■ |  | 
 | Independent Generator |  |  | 
 | Consumer |  |  | 
 | Independent REP | ■ |  | 
 | Independent Power Marketer | ■ |  | 
http://nodal.ercot.com <number>
Note: the votes in the above summary are available for pick-up from the Aug. 25-27 TPTF Meeting Page.
Vote Item | Sector | For | Against | Abstention
On August 16, 2008, TPTF reviewed NPRR148, Treatment of Financial Information as Confidential, and endorsed formal comments to be submitted to PRS | Cooperative | ■ |  | 
 | Municipal | ■ |  | 
 | Investor Owned Utility | ■ |  | CenterPoint
 | Independent Generator |  |  | 
 | Consumer | ■ |  | 
 | Independent REP | ■ |  | 
 | Independent Power Marketer | ■ |  | 
Notes: <number>

## Slide 23
Vote Summary: August 25 – 27, 2008
Vote Item | Sector | For | Against | Abstention
On August 27, 2008, TPTF approved the MIS/CRR/NMMS CRR Map Requirements v0.93 as submitted to TPTF | Cooperative | ■ |  | 
 | Municipal | ■ |  | 
 | Investor Owned Utility | ■ |  | CenterPoint
 | Independent Generator | ■ |  | 
 | Consumer |  |  | 
 | Independent REP | ■ |  | 
 | Independent Power Marketer | ■ |  | 
http://nodal.ercot.com <number>
Note: the votes in the above summary are available for pick-up from the Aug. 25-27 TPTF Meeting Page.
Vote Item | Sector | For | Against | Abstention
On August 27, 2008, TPTF endorsed the draft NPRR Clarify Definition of a Generator Output Breaker in the Outage Scheduler | Cooperative | ■ |  | 
 | Municipal | ■ |  | 
 | Investor Owned Utility | ■ |  | 
 | Independent Generator | ■ |  | 
 | Consumer |  |  | 
 | Independent REP | ■ |  | 
 | Independent Power Marketer | ■ |  | Shell Energy, Tenaska Power
Notes: <number>

## Slide 24
Vote Summary: August 25 – 27, 2008
Vote Item | Sector | For | Against | Abstention
On August 27, 2008, TPTF approved the Single Entry Model Go-Live Procedure v0.08 | Cooperative | ■ |  | 
 | Municipal | ■ |  | 
 | Investor Owned Utility | ■ |  | 
 | Independent Generator | ■ |  | 
 | Consumer |  |  | 
 | Independent REP | ■ |  | 
 | Independent Power Marketer | ■ |  | 
http://nodal.ercot.com <number>
Note: the vote in the above summary is available for pick-up from the Aug. 25-27 TPTF Meeting Page.
Notes: <number>

## Slide 25
http://nodal.ercot.com <number>
Next Meetings:
Next Meetings:
  September 8 – 9
  September 22 – 24
  October 13 – 14
  October 27 – 29
Visit the 2008 TPTF Calendar
Notes: <number>

## Slide 26
http://nodal.ercot.com <number>
Next Meetings (continued):
During the September 8 – 9 TPTF meeting, likely topics include:
  Integrated Schedule Review
  Discussion of NPRRs:
    Draft NPRR, Corrections of Entities Able to Bid for PTP Obligations in DAM
    NPRRXXX, Clarify Definition of a Generator Output Breaker in the Outage Scheduler
    NPRR136, Interim Solution for 15-Minute Settlement of Advanced Meters
    NPRR140, Revision to CRR Obligation Margin Adder
    NPRR143, Section 9.9.1, Invoice Recipient Payment to ERCOT for the CRR Auction, Clean-up
    NPRR149, Change the Name of EECP to Energy Emergency Alert (EEA)
    NPRR150, Responsive Reserve Service Offer Floor
  Other Discussions:
    System Implementation Group (SIG) White Papers
    Nodal System Change Process
    Mock Credit Exposure Reports
Notes: <number>

## Slide 27
http://nodal.ercot.com <number>
Approval of Milestones:
On May 23, 2008, TPTF approved revisions to incorporate functionality for co-optimization for Self-Committed units in DAM into the MMS DAM and SASM Requirements. The approval carried by roll-call vote with 100% in favor and one abstention (PSEG). The Consumer Market Segment was not represented for the vote.
On August 27, 2008, TPTF approved the MIS/CRR/NMMS CRR Map Requirements as submitted to TPTF. The approval carried by roll-call vote with 100% in favor and one abstention from the Investor Owned Utility Market Segment. The Consumer Market Segment was not represented for the vote.
The Transition Plan says: “Any declaration of the accomplishment of a major milestone (business requirements, conceptual design, and successful completion of Market Participant testing) or a decision to proceed is contingent on the approval of both ERCOT and TAC.”
Request TAC acknowledge TPTF completion of the following Milestones:
  MMS DAM and SASM Requirements
  MIS/CRR/NMMS CRR Map Requirements
Notes: <number>

## Slide 28
http://nodal.ercot.com <number>
Approval of New Readiness Metrics:
On July 22, 2008, TPTF endorsed ERCOT moving forward with the new Readiness Metric: MP21, Wind Generating Resources Inter-Control Center Communication Protocol (ICCP). The endorsement carried by roll-call vote with 100% in favor and one abstention form the Independent Power Marker Market Segment. All Market Segments were represented for the vote.
On August 25, 2008, TPTF endorsed ERCOT moving forward with the new Readiness Metric MP22, New Entrant Readiness. The endorsement carried by roll-call vote with 100% in favor and one abstention (Calpine). The Consumer Market Segment was not represented for the vote.
Request TAC approval for these new Readiness Metrics.
Notes: <number>

## Slide 29
http://nodal.ercot.com <number>
Approval of Completed Readiness Metrics:
On August 25, 2008, TPTF endorsed forwarding the following Readiness Metrics to TAC for concurrence that these metrics have been completed as presented by ERCOT staff and as attested to by the EDS Test Team:
  MP2, QSE with Resources Connectivity to EDS Environment
  MP3, QSE with Resources Upload of SCED Offers to ED
  MP5, ICCP Point to Point Telemetry Test
  MP8, QSE Ability to Submit Transactions Via MIS
  MP9, QSE Ability to Submit Web Service Transactions
The endorsement carried by roll-call vote with 100% in favor and two abstentions (Calpine, CitiGroup). The Consumer Market Segment was not represented for the vote.
Request TAC approval to recognize these Readiness Metrics as completed.
Notes: <number>

## Slide 30
http://nodal.ercot.com <number>
Approval of Revised Readiness Metrics:
On August 25, TPTF endorsed ERCOT moving forward with revisions to the following Readiness Metric as discussed by TPTF on August 25, 2008:
  MP1, MP Engagement
  MP6, QSER and TSP Compliance with the Nodal Protocols Section 3.10.7.5
  MP10, Mapping of Resources to Resource Nodes and Resources to EPS Meters
  MP11, MP Registration Activities
  MP12, MP Completes Nodal Market Related Training
  MP13, MP Completes Nodal Operations Related Training
  MP14-A, MP EDS 2, Release 3 Trials Participation
  MP14-B, MP EDS 2, Release 4 Trials Participation
  MP14-C, MP EDS 2, TSP Model Validation Participation
  MP15-A, MP EDS 3, Releases 5 and 6 Participation
  MP15-B, MP EDS 3, Release 7 Trials Participation
  MP17, MP Qualification Activities
  MP19, Load Serving Entitles Engagement and Readiness
  MP20, MP Ability to Submit Outage - Connectivity Test
The endorsement carried by roll-call vote with 100% in favor and one abstention (Calpine). The Consumer Market Segment was not represented for the vote.
Request TAC approval for ERCOT moving forward with the revisions for these Readiness Metrics
Notes: <number>

## Slide 31
http://nodal.ercot.com <number>
Questions
?
Notes: <number>