## Slide 1: Texas Nodal Market Implementation: Program Update
September 4, 2008
TAC
Ron Hinsley
Notes: <number>

## Slide 2: Agenda
Texas Nodal Program Update
September 4, 2008
Program Status
Integrated Schedule Progress
AREVA CIM Status
Single Entry Model Status
ERCOT Staff / Market Participant Readiness
Cost
Supplemental Slides: Project Work Performed to Date
Notes: <number>

## Slide 3: Program Status
Texas Nodal Program Update
September 4, 2008
`
Nodal Delivery status is:
ERCOT Staff Readiness status is:
Market Participant Readiness status is:
Cost
Schedule
Scope / Quality
Nodal Delivery
Amber status driven by limited response from entities needing to modify their RARFs
Red status driven by quality, schedule, and cost impacts
Red
Red
Amber
Amber status driven primarily by E8, the staffing metric
Red*
* Final cost unknown until new schedule confirmed
Red
Amber
Amber
 | Scope | Quality | Schedule | Cost
Green | Program is aligned with current protocols | All Nodal products currently achieve quality standards | Go-Live = 12/1/2008 | Estimate at Complete =< 319M
Amber | Program is aligned to previous protocol versions | Most Nodal products currently achieve quality standards | Go-Live =< 30 days | Estimate at Complete =< 319M +10%
Red | Program is not aligned to protocols | Product quality not sufficient for Nodal launch | Go-Live =>30 days+ | Estimate at Complete => 319M +10%
Notes: <number>
<number>

## Slide 4: Nodal Integrated Schedule Update – as of Aug. 28
Texas Nodal Program Update
September 4, 2008
Work completed to date
  Critical path through Nodal Go-Live is documented
  All project schedules are integrated
  Identified areas of possible resource constraints
  Business owners have reviewed project schedules
  Security, testing, and transition, MPIM, activities have been reviewed and updates incorporated
  PERT estimates reviewed and updated
  Running PERT analysis and Monte Carlo simulations
Remaining work
  Complete PERT analysis and Monte Carlo simulations
  Create integrated schedule views (MPs, Executives, PMO)
  Determine schedule contingency and include in schedule
  Present to ERCOT executives Aug. 29
  Present to TPTF for initial review Sep. 8 and incorporate feedback
  Present to TPTF for second review Sep. 22 and incorporate feedback
  Present to TAC Oct. 2 and incorporate feedback
  Present to TPTF Oct. 13
  Present to Board of Directors Oct. 21 and incorporate feedback
  Baseline Nodal integrated schedule
Notes: <number>

## Slide 5: AREVA CIM Status
Texas Nodal Program Update
September 4, 2008
Completed two weeks of data correction / testing at ERCOT
  Number of data issues have been reduced from over 20,000 (week of Aug. 8) to 54 (week of Aug. 29)
  New NMMS model provided on Aug. 29 – target of this release is to reduce to zero data issues
ERCOT SMEs continue to test with AREVA to identify and resolve issues
  Running validation and cross validation routines – all run successfully except Generation and ICCP
  Running individual applications
    SCADA – running successfully, but addressing three data errors
    ICCP – not started due to one data and code issue
    Generation – limited success, but addressing 50 data errors and a potential code issue
    Dynamic Rating – testing has not started
    Network Applications – Study Load flow and State Estimator ran successfully; Contingency Analysis has limited success due to configuration data and code issue
Notes: <number>
<number>

## Slide 6: Single Entry Model Status
Texas Nodal Program Update
September 4, 2008
Go-live procedure approval
  Endorsed by ROS on Aug. 14; approved by TPTF on Aug. 27
  Up for TAC approval on Sep. 4
  Once the procedure is approved, it becomes a binding document that ERCOT and MPs are required to abide
Documentation
  NMMS team is currently working on the business rules validation document and the modeling guidelines document
  These two documents will be published for MP review in the next few weeks
Testing (Rules and Data Validation)
  Once Siemens implements the business rules validation (as part of NMMS 5), ERCOT will conduct CIM business process test and business rules validation testing with the TSPs
  Simultaneously ERCOT will also work on data validation, to ensure the Nodal model that we upon SEM is as good as (or better than) the zonal model
Once MP testing and model validation are complete, SEM is ready for go-live
Notes: <number>
<number>

## Slide 7: ERCOT Readiness
Texas Nodal Program Update
September 4, 2008
Engagement (green)
  new survey results came out at the end of July - ERCOT remains fully engaged
Training (amber)
  training efforts are on-going
Process (green)
  all departments are meeting target performance levels
  470 procedures; 87% complete
Staffing (amber)
  ERCOT is currently 96% staffed
  (98% required for green status)
  recruitment is on-going
Testing (green)
  no recent developments
ERCOT Staff Readiness status is AMBER
Notes: <number>

## Slide 8: Market Participant Readiness
Texas Nodal Program Update
September 4, 2008
Market Participant Readiness status is AMBER
Engagement (green)
  increase in survey response drives green status
Connectivity (green)
  several new entrants to the market have been successfully tested
Registration and Qualification (red)
  for QSEs, limited testing from entities new to the market is driving the amber status (MP8)
  for QSEs with Resources, limited response from entities needing to modify their RARFs is driving the red status (MP11)
Telemetry (green)
  no change
Training (green)
  Increase in survey response drives green status
Trials Participation (green)
  no change
Notes: <number>

## Slide 9
Texas Nodal Program Update
September 4, 2008
Variance
(over)/under
Cost Element
Budget
Actual
Budget
Internal Labor
$ 38.7
$ 38.6
$ 0.1
External Labor
155.9
164.2
(8.3)
Hardware / Software
59.5
59.9
(0.4)
Travel and Other
11.2
6.9
4.3
Subtotal
$ 265.3
$ 269.6
$ (4.3)
Finance Charge
8.7
8.6
0.1
Total
$ 274.0
$ 278.2
$ (4.2)
Nodal Program
Cost Element Summary
($ Millions)
Through July 2008
When the integrated schedule has been finalized and the financial impact determined we will incorporate this into an updated forecast
Cost: Element Summary

## Slide 10
<number>
Texas Nodal Program Update
September 4, 2008
Project Work Performed to Date
Notes: <number>

## Slide 11
Developed EMS exporter for extracting zonal data to initially seed the nodal network model as a starting point for data population
Released functionality to enable ERCOT Transmission Service Providers (TSPs) to enter descriptions of Network Operations Model Change Requests (NOMCRs), with the following components:
  Information Model Manager – database to support operational network models, dataset management service that is capable of producing time based operations models, and services that import/export models in CIM XML/RDF bulk formats
  Project Tracker and Coordinator – allows user to describe construction projects or any changes to the network model parameters, and to perform some validation of submitted projects
  Topology Processor – converts operations models to planning models
  Planning Model On Demand – capabilities to manage multiple planning projects and to produce and manage multiple time-based planning models
Completed NMMS training for TSPs on steps to complete a NOMCR
Completed development of the four core Network Model Group business procedures needed to support business workflows after Single Entry Model Go-Live
  Generate, Post, and Distribute Models & Files, Conduct NOMCR Validation, Respond to Model Changes & Interim Updates, Maintain Network Model
Although functionality has been delivered, NMMS has not yet successfully passed FAT
Work Performed to Date – NMMS
Texas Nodal Program Update
September 4, 2008
Notes: <number>

## Slide 12
Released the base EMS system which facilitates the data exchange between ERCOT and MPs, monitoring of generation, load frequency control, assessment of the network security of the ERCOT system through applications such as:
  SCADA (in EDS)
    ICCP interface, Local calculations, Alarming, ERCOT Control Rooms interface to the EMS Applications
  Dynamic Ratings (in EDS)
    Temperature dependent limits (better use of existing facilities)
  Forced Outage Detection (in EDS)
    Extends alarming beyond SCADA (detects and alarms on discrepancies between SCADA, Current Operating Plan and Outage Schedules)
  Generation Functions (in EDS)
    Load Frequency Control, energy deployment, Ancillary Service performance monitoring, Resource qualification testing, Resource Limit Calculator
  Load Forecasting (in EDS)
    Seven-Day hourly, past pattern and weather based
  Wind Power Forecasting (in EDS)
    Short-Term Wind Power Forecast (expected power for 2 days), Wind-Powered Generation Resource Production Potential (80% probability, for 2 days), Long-Term Wind Power Forecast (provided by resources)
Work Performed to Date – EMS
Texas Nodal Program Update
September 4, 2008

## Slide 13: Work Performed to Date – EMS
Released the base EMS system (continued)
  State Estimator (in EDS)
    Real-Time estimate of the true and complete state of the system; identify real-time violations, inconsistencies between different measurements, and critical locations for measurements; Study version for debugging
  Network Security and Stability Analysis (in EDS)
    Real-Time Contingency thermal overload analysis; Voltage and Transient stability analysis (completed FAT); Transmission Congestion management;
    Backup scheme when State Estimator fails to provide solution for extended time;
    Determination of look-ahead limits for use in market functions
  Voltage Support Requirements Specification (in FAT)
    Finds a suggested voltage profile to correct Real-Time voltage problems
  Outage Evaluation (in FAT)
    Multi-hour, multi-model reliability analysis to determine if requested outages can be approved
  Interfaces to downstream applications
    MMS (most in EDS, some in FAT), EDW (most in EDS, some future work), All Wind Service (in EDS), External Load Forecast (in EDS), Weather Service (in EDS), Settlement & Billing (in EDS)
    Alarms and Notification to market participants (in FAT)
  Supply Data to Reporting functions
    Telemetry standards; congestion reports; SE performance monitoring
  Data Model Import (in process)
    Import and processing of CIM models needed for security assessment, generation control and outage evaluation
Texas Nodal Program Update
September 4, 2008

## Slide 14: Work Performed to Date – MMS
Delivered four releases through MMS4 that includes baseline 0, 1 & 2 functions in support of Day-Ahead (DAM), adjustment, and operating period markets
  Continuing work on MMS Processes & Procedures to support these markets
Testing and all testing-related documentation through initial release of MMS4 FAT is completed
Delivered and received approval for all requirements and conceptual design documentation through baseline 2 and any other approved changes (e.g., co-optimizing energy & AS for self-committed resources in DAM changes)
Continuing work on functional & detailed design specifications, as changes are needed
Continuing work on additional documentation that includes:
  Test plans, test cases, test scripts, test results, traceability matrix for MMS4 patches and MMS5
  DAM, RUC, adjustment period & real-time process documentation development in progress
  DAM, RUC, adjustment period & real-time procedure documents development in progress
Evaluated and planning for inclusion (into MMS5) of all post-baseline 2 NPRRs approved by the board or deemed essential for go-live by TPTF (seven total as of Aug. 25, 2008)
Texas Nodal Program Update
September 4, 2008

## Slide 15: Work Performed to Date – CRR
Delivered a fully tested CRR system that meets the functionality and performance measures in accordance with approved requirements by using manually uploaded production files
Resolved all defects found during Pre-FAT and FAT testing cycles
Delivered a CRR process that is fully traceable and compliant with the respective Protocols as well as other official published defining documents
Full Non Opt-In Entity (NOIE) participation in EDS testing of Allocation Markets
Texas Nodal Program Update
September 4, 2008

## Slide 16: Work Performed to Date – COMS
Planning and Documentation
  Completed Market Requirements and Conceptual Design documentation and received approval from TPTF
  Created Detailed Designs (Living Documents)
  Created Test Plans, Cases, and Scripts (over 11,000 testing artifacts)
Development
  Completed Lodestar core development; targeted to deploy with Lodestar 4.7 Upgrade in September 2008
  Completed core development of batch cycle for DAM, RTM, and CRR
  Completed and deployed builds for Commercial Systems Integration to support EMS, SASM, CRR, DAM, GUI, and 70% of all billing determinants
  Completed and deployed three Registration releases to ERCOT production (zonal) that includes TML screens, Siebel screens, Metadata, and EIS changes
  Deployed base CMM product, critical calculations build, and build 3.1 (critical interfaces)
Testing
  Completed testing of all MMS patches from ABB (up to MMS4 patch 2) in support of market based solution for settlements
  Continuing testing of Siebel Phase 4
  Completed framework testing of shadow settlements extracts
Texas Nodal Program Update
September 4, 2008

## Slide 17: Work Performed to Date – EIP
Simple, reliable and secure Market Participant interaction with ERCOT
  Delivered interfaces for and supported all EDS testing activities since August 07
  Nodal Web Services have been used 250,000 times since March 2008 by 315 different Market Participant identities
  Supported Market Participants’ efforts to develop their side of the Nodal services including workshops, Google, samples, sandbox and regular meetings
Automated and controlled internal interfaces for all Nodal systems
  Provided the interfaces that enable ERCOT’s new MMS and OS user interfaces
  Designed 35 of the total 36 interfaces required for Nodal
  Constructed 30 of the total 36 interfaces required for Nodal
  Deployed 19 of the total 36 interfaces required for Nodal to iTest or equivalent
Established a service oriented architecture platform for future enhancements
  New common services and design pattern library that ensure interfaces are reliable, controlled, simple to extend and maintain
  Comprehensive TIBCO-based infrastructure and description of all services and interfaces to improve and simplify maintenance and extension
Texas Nodal Program Update
September 4, 2008

## Slide 18: Work Performed to Date – CDR
Reporting Engine
  Schedules and creates reports based on time from the source systems (MMS and EMS) and inserts them into the ERCOT common data storage known as the Market Information Repository (MIR)
Direct Posting to MIR
  Inserts the file to the MIR database directly without using any brokers or middleware thereby significantly decreasing the time to insert files, especially large ones
Reports and Extracts – 38 complete, 8 pending completion
  Outage Scheduler (4 of 4 complete); Day Ahead Market (7 of 7 complete)
  Reliability Unit Commitment (3 of 3 complete)
  Security-Constrained Economic Dispatch (3 of 3 complete)
  Load/Demand Forecasts (6 of 6 complete); State Estimator (2 of 5 complete)
  System Adequacy – PUCT (1 of 1 complete)
  Distribution Factors (1 of 1 complete); Ancillary Services (4 of 5 complete)
  Locational Marginal Prices and Settlement Point Prices (2 of 2 complete)
  System Data (3 of 6 complete); QSE specific data (1 of 2 complete)
  Weather Data (1 of 1 complete)
Texas Nodal Program Update
September 4, 2008

## Slide 19: Work Performed to Date – EDW
Infrastructure and software are in place for data replication to store Real-time Nodal information for EMS, MMS, CMM, CRR, Lodestar
Energy Management System data marts are built to support future reporting requirements
All State Estimator reports and data extracts completed in iTest using Nodal data, allowing MPs and ERCOT to track convergence and violations that occur during State Estimator execution
All Telemetry reports are completed in iTest using Nodal data, allowing MPs and ERCOT to identify equipment failures and communications issues
XSDs and DDLs for State Estimator and Telemetry reports posted for MP use
All Shadow Settlement extracts currently in iTest; DDLs and XSDs posted for MP use
All COMS Non-Shadow settlement extracts under development
Texas Nodal Program Update
September 4, 2008

## Slide 20: Work Performed to Date – MIS
Deployed Portal framework and supporting infrastructure to EDS
Designed, created and deployed 16 Landing Pages containing approximately 40 portlets
Deployed the following reports and extracts to EDS
  11 sample Settlement Statement and Invoices
  36 CDR Reports, 4 MMS Reports, 9 EDW Reports and Extracts, 3 CMM Reports, and 6 COMS Reports and Extracts
Deployed links to launch CRR, MMS and OS UI applications to EDS
Implemented Simple Search functionality
Deployed LMP Contour Map dashboard to iTest
Implemented Protocol View
Texas Nodal Program Update
September 4, 2008

## Slide 21: Work Performed to Date – Infrastructure
Infrastructure Process Changes
  Completed operational procedures for a fundamental technology change of Unix platforms and Oracle platforms
  Implemented a release management process capable of supporting a 500% increase in releases
  Implemented an SLA for the EDS systems which will become the Nodal SLA
Infrastructure deployments and upgrades
  Licensed all database and supporting software
  Implemented the Market Participant Identity Management (MPIM) solution currently in production
  Revised the architecture of the monitoring tools to support the high availability needs of Nodal
  Deployed most infrastructure components required expected to be needed to support the new market prior to performance tests
  Consolidated 91 Unix servers to 4 to support both the Zonal and Nodal markets
  Upgraded the architecture of the data warehouse to support the availability and throughput requirements of the new market
  Implemented a virtualized development environment to maximize data center capacity
  Completed all possible data center power conservation activities
Texas Nodal Program Update
September 4, 2008

## Slide 22: Work Performed to Date – INT
Testing Infrastructure / Tools
  Documented overall Nodal Test Strategy and Procedures
  Purchased and implemented a central defect tracking tool and process across the program
  Purchased and Implemented test automation tools for integration, performance, and regression testing
  Partially completed Integration Test Environment (supported by INF)
Test Planning
  Documented test plans for CRR, Siebel, and CMM functional testing
  Developed approximately 600 test cases
  Developed approximately 18,000 test scripts
  Created automated testing suites for approximately 60 integration adapters
  Created automated testing scripts to support functional regression testing of MIS, CRR, CMM, CDR, and EIP systems
  Created test data generation tools to facilitate early testing of software
Test Execution in FAT
  Executed approximately 18,000 test scripts
Texas Nodal Program Update
September 4, 2008

## Slide 23: Work Performed to Date – EDS
Test Planning
  Developed and gained approval on EDS 1, 2, 3, & 4 Test Plans
  Developed and gained approval on 168Hr Test & Go-Live Procedures
Test Execution
  Supported all MPs through initial connectivity and use of all Nodal systems (MMS, CRR, Outage Scheduler, NMMS)
  Completed Real-time system connectivity (ICCP)
  10 months of generating LMPs (SCED)
  13 Day-Ahead Markets, 2 SASMs, 6 DRUC and 2 HRUCs
  2 Monthly and 1 annual CRR Auction
  2Hr Total System LFC Test, including 5 open preparatory tests
Market Support
  Hosted ~100 test status calls & 10 face-face workshops
  Answered ~6000 emails
Texas Nodal Program Update
September 4, 2008

## Slide 24
<number>
Texas Nodal Program Update
September 4, 2008
Questions?
Notes: <number>