## MTP2 Status
ERCOT System Change | Req # | Description | CERT Test (Y/N)
MT | 1 | Market: Make the order of all buttons consistent on all sub-types | N
MT | 2 | Market: Create a Parent Project Type for DEV Issues | N
MT | 3 | Market: Make all transitions consistent within MarkeTrak | N
MT | 6 | Market: Modify Search Arrow next to ID Search | N
MT | 14 | Market: Add Columns to Escalation Email Attachment | N
MT | 21 | ERCOT: Siebel Status/Sub-status Auto Update Upon Completion | N
MT | 23 | ERCOT: Part 1- Add ability to turn on/off Automation for ESIID and Status/Sub-Status | N
MT | 41 | ERCOT: Correct logic used in the StartTime fields on DEVLSE Issues | N
MT | 42 | ERCOT: Correct logic used in the StopTime fields on DEVLSE Issues | N
MT | 19 | ERCOT: Populate ERCOT Owner and Siebel Status/Sub-status on ERCOT Initiated Issues | N
Bucket 1 Above: June Release - MT Only (GUI & minimal API)
MT | 8 | Market: Do not capture Non-ERCOT Owner during “Begin Working” unless the owner field is empty | Recommend to Move to Release 2 on 02/07/2008
MT | 32 | Market: Capture Modify/Reassign StartTime and/or StopTime fields on DEVLSE Issues and Make Them Available on the Issue | Recommend to Move to Release 2 on 02/07/2008
MT | 23 | ERCOT: Part 2- Add ability to turn on/off Automation for IAG and DEV | N
MT/TIBCO | 7 | Market: Do not allow changes to the Title Field on MarkeTrak Issues | N
MT/TIBCO | 13 | Market: Update to Transaction Type during "Submit" and Add New Required Tran Type During "Re-Assign" | Y
MT/TIBCO | 16 | Market: Changes to Usage and Billing Sub-type | Y (moved to bucket 2 due to cross dependency on REQ 13
MT/SBL/TIBCO | 15 | Market: Validate ESI ID/TDSP Association | Y
MT/TIBCO | 18 | Market: Standardize Sub-type Names within DEV LSE Issues | N
MT/SBL/TIBCO | 22 | ERCOT: Validation of CR for Siebel Change | N
MT/TIBCO | 24 | ERCOT: Change the layout of the DEV Analysis Fields on GUI Screen for applicable DEV LSE Sub-types | N
MT/SBL/TIBCO | 26 | Market: Premise Type Field | N
MT/TIBCO | 27 | Market: Add “Close” Capability for Submitting MP for the Day to Day and Inadvertent Gain Workflows | Y
MT/TIBCO | 28 | Various Changes to Cancel With Approval | Y
MT/TIBCO | 29 | Market: Various Changes to Cancel Without Approval | N
MT/TIBCO | 35 | Market: Add Close Capability for Submitting MP for all DEV Workflows | Y
MT/SBL/TIBCO | 43 | ERCOT: IAG Analysis Automation | N Moved to release 3
MT/SBL/TIBCO | 44 | ERCOT: DEV Analysis Automation | N
MT/TIBCO/SBL data | 25 | Market: Inadvertent Gain | Y
Bucket 2A Above : Test Bundle 1 Aug. Release (IAG and DEVLSE Automation-SBL Change/Impacts)
MT/TIBCO | 5 | Market: Add Bulk Insert Number to Issues | Y
MT/TIBCO | 9 | Market: Require Comments for Siebel Chg/Info Sub-types | N
MT/TIBCO | 10 | Market: Add Service Period Start Date Field to Missing Transaction, Projects, Siebel Chg/Info, Other, Usage and Billing and REP of Record Sub-types. Add Service Period Stop Date Field to REP of Record and Usage and Billing Sub-types | Y
MT/TIBCO | 11 | Market: Add ISA Field to Submit for 997, Projects, and Other Sub-types | Y
MT/TIBCO | 12 | Market: Add a new required field to the Reject Sub-type to provide the Reject Reason | N
MT/TIBCO | 20 | ERCOT: Provide “First Touched Date” | N
MT/TIBCO | 30 | Market: Add “New Total” Required Field to Certain DEV IDR Sub-types | Y
TIBCO | 34 | Special Characters | Y Moved to release 3
Bucket 2B Above: Test Bundle 2 Aug Release (API, Workflow Fields)
MT/TIBCO | 4 | Market: Create Bulk Insert Templates and default Submit Validation Flags for API and Bulk Insert default to “Off” | Y
MIR/MT | 17 | Market: Reporting Improvements | Y
MT/TIBCO | 31 | Market: Change the format of Service History with DUNS for Effected Period and add it to “Submit” when submitter is a TDSP for given DEV LSE Sub-types. Add Logic to determine under which circumstances this field is necessary | Y
MT/TIBCO | 36 | Market: Add Email Button and Email Capture | Y
MT/TIBCO | 37 | Market: New Premise Type and Service Address Subtypes | Y
MT/TIBCO | 38 | Market: Add New D2D Sub-type titled “Safety Net Order” | Y
MT/TIBCO | 39 | – Market: Add New D2D Sub-type titled “Service Order – 650” | Y
MT/TIBCO | 40 | Market: Add New D2D Sub-type titled “Move Out With Meter Removal” | Y
MT/TIBCO | 45 |  | N
MT/TIBCO | 33 | Market: Provide Update Via API Whenever a Market Participants Visibility to an Issue Has Been Removed | Y - moved from Bucket 2 to balance code/testing load.
Bucket 3: December Release (New Workflows, API, Reporting, all else) |  |  | 0