| NPRR Number | 146 | NPRR Title | ICCP Telemetry Information Submittals |
| --- | --- | --- | --- |
| Date Posted |  | July 31, 2008 |  |
| Nodal Protocol Section Requiring Revision |  | 3.10.1, Time Line for Network Operations Model Change Requests |  |
| Requested Resolution |  | Normal |  |
| Revision Description |  | This Nodal Protocol Revision Request (NPRR) changes the ICCP data object names submittal to 15 days. |  |
| Reason for Revision |  | In many instances, the RTU configuration and point list is not available three months ahead of equipment change implementation. This change will require Transmission Service Providers (TSPs) and Qualified Scheduling Entities (QSEs) to provide only the real-time ICCP data object names 15 days prior to change and will allow ERCOT adequate opportunity to test the Network Operations Model prior to moving to production. |  |
| Overall Market Benefit |  | Improve the quality of information ERCOT receives on ICCP data object names. |  |
| Overall Market Impact |  | Reduced burden on TSPs and QSEs to provide needed information in a timely and correct manner. Will also prevent TSPs and ERCOT from modeling ICCP data object names that may not ever exist and then removing them at a later date. |  |
| Consumer Impact |  | None |  |
| Credit Implications |  | No |  |
| Reason for Revision (from Transition Plan Task Force (TPTF) Charter Scope) |  | (1) Revisions resulting from Commission orders; (2) Clarifications of Protocol language that do not change the intent or technical specifications of the Protocols; (3) Correction of technical errors or processes that are found to not be technically feasible; (4) Revisions to the Protocols necessary to implement the results of the value engineering analysis or to otherwise avoid severe cost impacts; or (5) Other (describe): |  |
| TPTF Review (Yes or No, and summary of conclusion) |  |  |  |

Quantitative Impacts and Benefits

| Assumptions | 1 | ERCOT can complete model testing for telemetry data in less than 7 days for new telemetry points. |  |
| --- | --- | --- | --- |
|  | 2 |  |  |
|  | 3 |  |  |
|  | 4 |  |  |
| Market Cost |  | Impact Area | Monetary Impact |
|  | 1 | None | No additional implementation cost |
|  | 2 |  | No additional staffing cost. Possible contractor reduction. |
|  | 3 |  |  |
|  | 4 |  |  |
| Market Benefit |  | Impact Area | Monetary Impact |
|  | 1 | Enhanced TSP and ERCOT efficiency due to not having to enter data multiple times into the NMMS. There is no reason to add data three months ahead of time and then to have to go back and change it later. | 200 man-hours per year @ $65/hour |
|  | 2 | Enhanced MP efficiency | More accurate telemetry data, less likely to test incorrectly. Save 120 man-hours per year at $65/hr for settlements & billing information. |
|  | 3 | Reduced congestion cost | Potential to reduce congestion cost with more accurate telemetry data. |
|  | 4 |  |  |
| Additional Qualitative Information | 1 | Will give ERCOT shorter time period for telemetry testing from 90 to 7 days. This only affects the ICCP data, all other model information will still be provided to ERCOT as required. |  |
|  | 2 | Fewer model changes for ERCOT models. Testing will be reduced due to fewer changes. |  |
|  | 3 |  |  |
|  | 4 |  |  |
| Other Comments | 1 | ERCOT systems require less changes and better modeling of telemetry information. |  |
|  | 2 | Fewer work-arounds and better telemetry information. |  |
|  | 3 |  |  |
|  | 4 |  |  |

| Sponsor |  |
| --- | --- |
| Name | Jim Jacoby |
| E-mail Address | jwjacoby@aep.com |
| Company | American Electric Power |
| Phone Number | 214-777-1144 |
| Cell Number |  |
| Market Segment | Investor Owned Utility (IOU) |

| Market Rules Staff Contact |  |
| --- | --- |
| Name |  |
| E-Mail Address |  |
| Phone Number |  |

Proposed Protocol Language Revision

3.10.1	Time Line for Network Operations Model Change Requests

(1)	ERCOT shall perform periodic updates to the ERCOT Network Operations Model.  Market Participants may provide Network Operations Model updates to ERCOT to implement planned transmission and Resource construction one year before the required submittal date below.  TSPs and Resource Entities must timely submit Network Operations Model changes pursuant to the schedule in this Section to be included in the updates.

(2)	For a facility addition, revision, or deletion to be included in any Network Operations Model update, all technical modeling information must be submitted to ERCOT pursuant to the ERCOT NOMCR process.

(3)	TSPs and Resource Entities shall submit Network Operations Model updates at least three months prior to the physical equipment changeERCOT shall update the Network Operations Model according to the following table:

| Deadline to Submit Information to ERCOT Note 1 | Model Complete and Available for Test Note 2 | Updated Network Operations Model Testing Complete Note 3 | Update Network Operations Model Production Environment | Target Physical Equipment In-Service Date Note 4 |
| --- | --- | --- | --- | --- |
| Jan 1 | Feb 15 | March 15 | April 1 | Month of April |
| Feb 1 | March 15 | April 15 | May 1 | Month of May |
| March 1 | April 15 | May 15 | June 1 | Months of June–August SUMMER MODEL |
| June 1 | July 15 | August 15 | September 1 | Month of September |
| July 1 | August 15 | September 15 | October 1 | Month of October |
| August 1 | September 15 | October 15 | November 1 | Month of November |
| September 1 | October 15 | November 15 | December 1 | Month of December |
| October 1 | November 15 | December 15 | January 1 | Month of January (the next year) |
| November 1 | December 15 | January 15 | February 1 | Month of February (the next year) |
| December 1 | January 15 | February 15 | March 1 | Month of March (the next year) |

Notes:

1.	Transmission and Resource data submissions complete per ERCOT Network Operations Model Change Request process for inclusion in next update period.

2.	Network Operations Model data changes and preliminary fidelity test complete by using the Network Operations Model test facility described in Section 3.10.4(3).  The test version of the Network Operations Model will be available for market review and further testing by Market Participants.

3.	Testing of the Network Operations Model by Market Participants is complete and ERCOT begins the Energy Management System testing prior to placing the new model into the production environment.

4.	Updates include changes starting at this date and ending within the same month.

(4) 	ERCOT shall only approve energization requests when the Transmission Element is satisfactorily modeled in the Network Operations Model.

(5)	In order to allow for construction schedules, TSPs may use pseudo-breakers and switches to designate future facilities configurations such that the Network Operations Model topology may be correctly implemented as construction of new facilities is accomplished.

(6)	NOMCR submittals containing only ICCP data object names shall be provided no later than fifteen (15) days prior to the proposed Energize Date for Transmission Elements represented by the ICCP data object names and shall not be subject to IMM and PUC reporting (reference 3.10.4 ERCOT Responsibilities (5)).