|  |  | System Planning Division |
| --- | --- | --- |
|  |  | Monthly Status Report to Reliability and Operations Subcommittee for August 2008 |
|  | Report Highlights |  |
| Item |  |  |
| 1. | ERCOT is currently tracking 246 active generation interconnection requests totaling over 105,000 MW. This includes almost 52,000 MW of wind generation. 59 MW of new wind generation began commercial operation bringing the currently installed total of wind power capacity to 5,871 MW. |  |
| 2. | Regional Planning is currently reviewing proposed transmission improvements with a total cost of $501.3 Million Transmission Projects approved in 2008 to date total $217 Million All projects (in engineering, routing, licensing and construction) totals approximately $3.8 Billion Transmission Projects energized in 2008 total about $375 Million Oncor’s Renner Dynamic Reactive Project for Board review this month |  |

Table of Contents

1.	Generation Interconnection	1

1.1.	New Generation Beginning Commercial Operations	1

1.2.	Summary of Active Generation Interconnection Requests	1

1.3.	Potential Future Generation Interconnections	1

2.	Regional Planning Group Project Reviews	1

3.	Congestion Report	1

4.	Other Notable Activities	1

# 1.	Generation Interconnection

Additional information regarding detailed generation interconnection and impact studies is contained in the “Generation Project Interconnection Information” folder in the “Operations and System Planning” area on the ERCOT website:  http://planning.ercot.com/login/login.

## New Generation Beginning Commercial Operations

# Ocotillo Wind Farm (04INR0017) in Howard County for 59 MW

## The total installed wind capacity is now 5,871 MW.

## Summary of Active Generation Interconnection Requests

| GENERATION INTERCONNECTION REQUESTS CURRENTLY BEING PROCESSED |
| --- |
| Currently tracking 243 active generation interconnection or change requests As of August 31, 2008 |
|  | North | South | West | Total |
| Security Screening Study |  | 2 | 11 | 10 | 23 |
| SSS Completed |  | 7 | 12 | 30 | 49 |
| Full Interconnect Study |  | 31 | 26 | 74 | 131 |
| FIS Completed |  | 1 | 8 | 0 | 9 |
| Interconnect Agreement Completed |  | 7 | 9 | 18 | 34 |
| Capacity for Grid, MW |  | 25,019 | 36,434 | 44,113 | 105,566 |
| Wind Capacity, MW |  | 2,261 | 9,500 | 40,793 | 52,554 |
| Fuel | Non-Public (MW) | Public (MW) | Total (MW) |
| Combined Cycle - Gas | 23,407 | 5,524 | 28,931 |
| Combustion Turbine - Gas | 915 | 505 | 1,420 |
| Nuclear | 3,200 | 9,186 | 12,386 |
| Coal | 4,144 | 4,131 | 8,275 |
| Wind | 43,429 | 9,125 | 52,554 |
| Other | 1,535 | 145 | 1,680 |
| Totals | 76,630 | 28,616 | 105,246 |

## Potential Future Generation Interconnections

The table below summarizes the publicly known potential future generation projects for the ERCOT region.  (IA=Interconnect Agreement, PL=Public Letter, XX= cancelled)

| Future Generation Interconnections (Public Projects) as of August 31, 2008 |
| --- |
| INR | SiteName | Status | County | Region | In-Service Date | Fuel | MW Into Grid | Change from Last Report |
| 04INR0011b | Mesquite Wind Phase 4 | IA | Shackelford | West | Aug-08 | Wind | 136 |  |
| 04INR0011c | Cottonwood Wind | IA | Shackelford | West | Aug-08 | Wind | 100 |  |
| 08INR0055 | Capricorn Ridge III | IA | Coke | West | Aug-08 | Wind | 249 |  |
| 06INR0012a | Sherbino Mesa Wind Farm 1 | IA | Pecos | West | Sep-08 | Wind | 150 |  |
| 07INR0034 | Wolf Ridge Windfarm | IA | Cooke | North | Oct-08 | Wind | 113 |  |
| 07INR0037 | Bull Creek Wind Plant | IA | Borden | West | Oct-08 | Wind | 180 |  |
| 08INR0050 | Victoria Power Station | IA | Victoria | South | Oct-08 | GasCC | 332 | date |
| 07INR0027 | South Houston Green Pwr Exp Prj1 | IA | Galveston | South | Nov-08 | GasCC | 244 | date |
| 07INR0045a | Airtricity Pyron Wind Farm | IA | Scurry | West | Nov-08 | Wind | 249 |  |
| 07INR0045b | Airtricity Inadale | IA | Scurry | West | Nov-08 | Wind | 197 |  |
| 08INR0037 | Airtricity Panther Creek 2 | IA | Howard | West | Nov-08 | Wind | 115 |  |
| 04INR0011e | Hackberry Wind Farm | IA | Shackelford | West | Dec-08 | Wind | 165 |  |
| 05INR0015a | Gulf Wind 1 | IA | Kenedy | South | Dec-08 | Wind | 283 |  |
| 06INR0022a | Penascal Wind Farm 1 | IA | Kenedy | South | Dec-08 | Wind | 202 |  |
| 07INR0005 | Notrees-1 | IA | Ector | West | Dec-08 | Wind | 151 |  |
| 07INR0011 | Turkey Track Energy Center | IA | Nolan | West | Dec-08 | Wind | 170 |  |
| 07INR0029 | South Trent Wind Farm | IA | Taylor | West | Dec-08 | Wind | 101 |  |
| 08INR0025 | Pistol Hill Energy Center | PL | Ector | West | Dec-08 | Wind | 300 |  |
| 08INR0053 | Elbow Creek Wind Project | IA | Howard | West | Dec-08 | Wind | 117 |  |
| 08INR0059 | Gray Wind Project | PL | Borden | West | Dec-08 | Wind | 141 |  |
| 09INR0026a | Sterling Energy Center | PL | Sterling | West | Dec-08 | Wind | 200 |  |
| 07INR0036 | Coyote Run Windfarm | IA | Borden | West | Mar-09 | Wind | 225 |  |
| 08INR0046 | Bosque Expansion | IA | Bosque | North | Mar-09 | GasCC | 255 |  |
| 08INR0065 | Buffalo Gap 4 and 5 | PL | Nolan | West | Mar-09 | Wind | 465 |  |
| 08INR0038 | M Bar Wind | PL | Andrews | West | Apr-09 | Wind | 194 | date |
| 09INR0072 | Dansby3 | PL | Brazos | North | Apr-09 | GasCT | 48 |  |
| 08INR0040 | Lenorah Project | PL | Martin | West | May-09 | Wind | 350 |  |
| 09INR0028 | V H Braunig 6 | PL | Bexar | South | May-09 | GasCT | 185 |  |
| 09INR0060 | Wind Tex - Stephens Wind Farm | PL | Borden | West | May-09 | Wind | 141 |  |
| 08INR0035 | Cedar Bayou 4 | IA | Chambers | South | Jun-09 | GasCC | 544 |  |
| 09INR0026 | Sterling Energy Center | PL | Sterling | West | Jun-09 | Wind | 300 |  |
| 09INR0036 | McAdoo Energy Center II | PL | Dickens | West | Jun-09 | Wind | 500 |  |
| 08INR0003 | Sandow 5 | IA | Milam | North | Jul-09 | Coal | 581 |  |
| 09INR0006a | Oak Grove SES 1 | IA | Robertson | North | Jul-09 | Coal | 855 |  |
| 09INR0027 | Winchester Power Park | IA | Fayette | South | Jul-09 | GasCT | 178 |  |
| 05INR0015b | Gulf Wind 2 | PL | Kenedy | South | Sep-09 | Wind | 400 |  |
| 08INR0033 | Lufkin | IA | Angelina | North | Sep-09 | Other | 45 |  |
| 08INR0018 | Gunsight Mountain | IA | Howard | West | Oct-09 | Wind | 120 | date |
| 09INR0015 | Comanche Peak 1&2 Upgrade | PL | Somervell | North | Oct-09 | Nuclear | 86 |  |
| 09INR0038 | Barney Davis 2 Repowering | IA | Nueces | South | Nov-09 | GasCC | 360 |  |
| 09INR0039 | Nueces Bay 7 Repowering | IA | Nueces | South | Nov-09 | GasCC | 327 |  |
| 09INR0045 | Sand Hill Peakers | PL | Travis | South | Nov-09 | GasCT | 94 |  |
| 09INR0034 | Gatesville Wind Farm | PL | Coryell | North | Dec-09 | Wind | 200 |  |
| 06INR0029 | Jackson Mountain | IA | Nolan | West | Jan-10 | Wind | 90 |  |
| 09INR0006b | Oak Grove SES 2 | IA | Robertson | North | Jan-10 | Coal | 855 |  |
| 09INR0037 | Scurry County Wind III | PL | Scurry | West | Mar-10 | Wind | 350 |  |
| 06INR0006 | Cobisa-Greenville | PL | Hunt | North | May-10 | GasCC | 1,750 |  |
| 09INR0002 | J K Spruce 2 | IA | Bexar | South | Jun-10 | Coal | 750 |  |
| 05INR0015c | Gulf Wind 3 | PL | Kenedy | South | Sep-10 | Wind | 400 |  |
| 06INR0012b | Sherbino Mesa Wind Farm 2 | IA | Pecos | West | Oct-10 | Wind | 150 |  |
| 06INR0026 | Wild Horse Mountain | IA | Howard | West | Dec-10 | Wind | 120 |  |
| 12INR0003 | Throckmorton Wind Farm | PL | Throckmorton | West | Dec-10 | Wind | 400 |  |
| 10INR0020 | Panda Temple Power | PL | Bell | North | May-11 | GasCC | 1,092 |  |
| 10INR0010 | Jack County 2 | PL | Jack | North | Jun-11 | GasCC | 620 |  |
| 09INR0007 | Nacogdoches Project | PL | Nacogdoches | North | Apr-12 | Other | 100 |  |
| 07INR0004 | Pampa Energy Center | PL | Gray | West | May-12 | Coal | 165 |  |
| 09INR0001 | Sandy Creek 1 | IA | McLennan | North | Jun-12 | Coal | 925 |  |
| 09INR0024 | B&B Panhandle Wind | PL | Carson | West | Jun-12 | Wind | 1,001 |  |
| 12INR0004 | Fort Concho Wind Farm | PL | Tom Green | West | Jul-12 | Wind | 400 |  |
| 11INR0011 | Victoria City Nuclear | PL | Victoria | South | Jan-15 | Nuclear | 3,200 |  |
| 15INR0002 | Comanche Peak 3 and 4 | PL | Somervel | North | Jan-15 | Nuclear | 3,200 |  |
| 15INR0008 | STP 3 and 4 | PL | Matagorda | South | Jan-15 | Nuclear | 2,700 |  |
|  |  |  |  |  |  | Total | 28,616 |  |

# Regional Planning Group Project Reviews

# Oncor submitted a project to add a 300 Mvar dynamic reactive device at Renner station (tentative) by summer 2010.  This cost of this project will be $35 M.  TAC voted in support of this project on August 7th, 2008 and it was endorsed by the ERCOT Board of Directors on August 19th, 2008.

# American Electric Power Service Corporation submitted a project to construct 2 new 138 kV substations, rebuild a 138 kV circuit, build  2 new 138 kV circuits, and install a new 138/69 kV autotransformer in the Abilene/San Angelo area.  The estimated cost of this project is $105.9 M.  This project is in ERCOT Independent Review.

# Luminant Energy submitted the Twin Butte – Kendall 345 kV double circuit line with series compensation.  It is a $327 million project comprised of 170 miles of 345 kV double circuits with both circuits in place, substation and breaker additions at Twin Butte and Kendall, and a 50% series compensation in each circuit.  This project is currently in ERCOT Independent Review.

# Luminant submitted a set of projects to reduce North to South Congestion.  It consists of several 138 kV line upgrades and series reactor installations.  The total cost for all projects is approximately $31 M. This project is currently in ERCOT Independent Review.

# Oncor submitted a project to add a 345 kV transmission line from Nacogdoches Southeast to Lufkin Switch with an estimated cost of $29.2 M .  This project was a result of the 2007 Five-Year Plan.  This project is will be presented to TAC on September 4, 2008 and to the ERCOT Board of Directors on September 16, 2008.

- CPS Energy submitted a project to add a 138 kV line from Westover Hills to their Anderson substation to complete a new circuit from VLSI substation to Anderson substation.  The VLSI to Westover Hills 138 kV portion will be in-service in 2009 to serve new load at Westover Hills.  This project was a result of the 2007 Five-Year Plan.  The estimated cost of this project is $8.2 M with an in-service date of peak 2010.

- Transmission Projects energized in Q2 of 2008 include:

    - Temple Pecan Creek - Lake Creek 138 kV line

    - Fairdale Load 69 kv to 138 kV voltage conversion

    - Walnut - Fairdale 69 kV line

    - Manvel

    - Hidalgo - S. McAllen 69 kV upgrade including transformers & equipment

    - Nolanville - Harker Heights 138 kV line

    - Putnam, replace 69/138 kV transformer

    - Waterport - Loma Alta 138 kV Circuit

    - Key Substation equipment upgrade

    - Exxon-Bertron Reconfiguration and Baytown - Rohmas substation

    - Bunker – Hood rebuild

    - Olney Auto

    - Capote Substation conversion to 138 kV

    - Exxon Sharon Ridge Substation upgrade

    - Pancake – Gatesville rebuild

# Congestion Report

Local congestion costs appear to be declining since 2003 and are below what they were for the same January through July time period in 2007.  However, June and July, 2008 have shown an increase in OOM Down costs.

| Million$ | OOMC | LBEDN | LBEUP | OOM Down | OOM Up | Total |
| --- | --- | --- | --- | --- | --- | --- |
| 2007 total | 44.35 | 18.80 | 5.65 | 30.31 | 30.27 | 129.38 |
| 2007 thru July | 29.33 | 11.75 | 4.10 | 15.20 | 23.40 | 83.78 |
| 2008 thru July | 26.45 | 6.33 | 3.64 | 28.41 | 6.53 | 71.36 |

MCPE for 2003-2008:

# Other Notable Activities

All postings referred to below can be found at http://planning.ercot.com/login/login unless otherwise indicated.

- ERCOT TPIT report for 08/01/2008 completed (3rd quarter) and posted on 08/18/2008.

- ERCOT Regional Planning is continuing work on the 2013 case to be used for reliability analysis and RPG analysis.  The purpose of this effort is to extend the 2007 Five-Year plan from 2012 to 2013.  The initial unserved energy and resulting reliability project set has been sent to the Transmission Owners.  Several Transmission Owners have responded to confirm ERCOTs project set or to suggest alternatives.  The dynamic line ratings have been removed from the case and reliability analysis will be redone to ensure all load can still be served.