| # Flight Schedule for Version 3.0 Flights in 2009 | ## 0209 |
| --- | --- |
| Activity | ## Calendar Date |
| Notice from ERCOT Retail Client Services of the next flight for Retail Market Testing sent to ERCOT lists.ercot.com distribution | #### Dec. 10, 2008 |
| TTPT to finalize scripts | ## Dec. 31, 2008 |
| Testing Worksheets are unlocked | #### Jan. 7, 2009 |
| FLIGHT DEADLINE The following 4 steps must be completed by 5pm cpt. on the deadline: - CR must have submitted ERCOT LSE Application and Application Fee - CR must have filed for PUC REP Certification - TW updated on ERCOT Retail Testing Website - Send an e-mail of intent to test to ERCOT at: RetailMarketTesting@ercot.com The following steps must be completed by 5pm cpt. on the deadline for current MPs: - TW updated on ERCOT Retail Testing Website - Send an email of intent to test to ERCOT at: RetailMarketTesting@ercot.com Testing Worksheets are locked at 5pm cpt. | ### Jan. 14, 2009 |
| ERCOT Retail Client Services verifies that each new Testing Participant has completed Registration testing requirements with ERCOT | #### Jan. 16, 2009 |
| Verification and communication from PUCT Staff that Testing Participants intending to test have applied for REP Certification | #### Jan. 16, 2009 |
| Communication from ERCOT Flight Administrator of Testing Participants to each TDSP | #### Jan. 16, 2009 |
| Communication of Test Certificates from ERCOT Retail Client Services to all Testing Participants | #### Jan. 20, 2009 |
| TDSPs and ERCOT have completed communication of connectivity testing schedule to each Trading Partner | #### Jan. 20, 2009 |
| Connectivity Testing Kick Off Conference Call - Mandatory for all Testing Participants (blackout ends) | #### Jan. 20, 2009 |
| Connectivity Testing begins for all Testing Participants | #### Jan. 20, 2009 |
| Penny Test (CON52) & ACK55/56 (FA Scripts) begins for all New Testing Participants | #### Jan. 20, 2009 |
| TDSPs communicate Test bed load to Trading Partners and ERCOT | #### Feb. 9, 2009 |
| Flight Kick Off Conference Call - Mandatory for all Testing Participants | Feb. 13, 2009 |
| Daily Conference Calls begin – Day 1 Transactions flow | Feb. 16, 2009 |
| Flight tentatively scheduled to conclude; Internal Regression Testing | ##### Mar. 31, 2009 |
| Contingency Testing scheduled to conclude for Flight (blackout starts) | ##### Apr. 17, 2009 |

| # Flight Schedule for Version 3.0 Flights in 2009 | ## 0609 |
| --- | --- |
| Activity | ## Calendar Date |
| Notice from ERCOT Retail Client Services of the next flight for Retail Market Testing sent to ERCOT lists.ercot.com distribution | #### Apr. 15, 2009 |
| TTPT to finalize scripts | ## May 6, 2009 |
| Testing Worksheets are unlocked | #### May 13, 2009 |
| FLIGHT DEADLINE The following 4 steps must be completed by 5pm cpt. on the deadline: - CR must have submitted ERCOT LSE Application and Application Fee - CR must have filed for PUC REP Certification - TW updated on ERCOT Retail Testing Website - Send an e-mail of intent to test to ERCOT at: RetailMarketTesting@ercot.com The following steps must be completed by 5pm cpt. on the deadline for current MPs: - TW updated on ERCOT Retail Testing Website Testing Worksheets are locked at 5pm cpt. | ### May 20, 2009 |
| ERCOT Retail Client Services verifies that each new Testing Participant has completed Registration testing requirements with ERCOT | #### May 22, 2009 |
| Verification and communication from PUCT Staff that Testing Participants intending to test have applied for REP Certification | #### May 22, 2009 |
| Communication from ERCOT Flight Administrator of Testing Participants to each TDSP | #### May 22, 2009 |
| Communication of Test Certificates from ERCOT Retail Client Services to all Testing Participants | #### May 26, 2009 |
| TDSPs and ERCOT have completed communication of connectivity testing schedule to each Trading Partner | #### May 26, 2009 |
| Connectivity Testing Kick Off Conference Call - Mandatory for all Testing Participants (blackout ends) | #### May 26, 2009 |
| Connectivity Testing begins for all Testing Participants | #### May 26, 2009 |
| Penny Test (CON52) & ACK55/56 (FA Scripts) begins for all New Testing Participants | #### May 26, 2009 |
| TDSPs communicate Test bed load to Trading Partners and ERCOT | #### Jun. 15, 2009 |
| Flight Kick Off Conference Call - Mandatory for all Testing Participants | Jun. 19, 2009 |
| Daily Conference Calls begin – Day 1 Transactions flow | Jun. 22, 2009 |
| Flight tentatively scheduled to conclude; Internal Regression Testing | ##### Aug. 4, 2009 |
| Contingency Testing scheduled to conclude for Flight (blackout starts) | ##### Aug. 25, 2009 |
| # Flight Schedule for Version 3.0 Flights in 2009 | ## 1009 |
| Activity | ## Calendar Date |
| Notice from ERCOT Retail Client Services of Retail Testing Orientation meeting sent to ERCOT lists.ercot.com distribution | #### Aug. 5, 2009 |
| TTPT to finalize scripts | ## Aug. 26, 2009 |
| Testing Worksheets are unlocked. | #### Sept. 2, 2009 |
| FLIGHT DEADLINE The following 4 steps must be completed by 5pm cpt. on the deadline: - CR must have submitted ERCOT LSE Application and Application Fee - CR must have filed for PUC REP Certification - TW updated on ERCOT Retail Testing Website - Send an e-mail of intent to test to ERCOT at: RetailMarketTesting@ercot.com The following steps must be completed by 5pm cpt. on the deadline for current MPs: - TW updated on ERCOT Retail Testing Website - Send an email of intent to test to ERCOT at: RetailMarketTesting@ercot.com Testing Worksheets are locked at 5pm cpt. | ### Sept. 9, 2009 |
| ERCOT Retail Client Services verifies that each new Testing Participant has completed Registration testing requirements with ERCOT | #### Sept. 11, 2009 |
| Verification and communication from PUCT Staff that Testing Participants intending to test have applied for REP Certification | #### Sept. 11, 2009 |
| Communication from ERCOT Flight Administrator of Testing Participants to each TDSP | #### Sept. 11, 2009 |
| Communication of Test Certificates from ERCOT Retail Client Services to all Testing Participants | #### Sept. 14, 2009 |
| TDSPs and ERCOT have completed communication of connectivity testing schedule to each Trading Partner | #### Sept. 14, 2009 |
| Connectivity Testing Kick Off Conference Call - Mandatory for all Testing Participants (blackout ends) | #### Sept. 15, 2009 |
| Connectivity Testing begins for all Testing Participants | #### Sept. 15, 2009 |
| Penny Test (CON52) & ACK55/56 (FA Scripts) begins for all New Testing Participants | #### Sept. 15, 2009 |
| TDSPs communicate Test bed load to Trading Partners and ERCOT | #### Sept. 28, 2009 |
| Flight Kick Off Conference Call - Mandatory for all Testing Participants | Oct. 2, 2009 |
| Daily Conference Calls begin – Day 1 Transactions flow | Oct. 5, 2009 |
| Flight tentatively scheduled to conclude; Internal Regression Testing | ##### Nov. 17, 2009 |
| Contingency Testing scheduled to conclude for Flight (blackout starts) | ##### Dec. 8, 2009 |