- MINUTES OF THE ERCOT

NODAL TRANSITION PLAN TASK FORCE (TPTF) MEETING

ERCOT Austin Office

- 7620 Metro Center Drive

- Austin, TX 78744

- August 25 – 27, 2008

- Meeting Attendance:

Voting Attendees:

| Name | Market Segment | Representing |
| --- | --- | --- |
| Abernathy, Rick | Independent Power Marketer | Eagle Energy |
| Brewster, Chris | Consumer | City of Eastland |
| Burkhalter, Ryan | Independent Power Marketer | CitiGroup (via teleconference) |
| Emesih, Valentine | Investor Owned Utility | CenterPoint |
| Green, Bob | Municipal | City of Garland (via teleconference) |
| Greer, Clayton | Independent Power Marketer | J. Aron and Co. |
| Gresham, Kevin | Independent Power Marketer | Reliant Energy, Inc. |
| Jackson, James | Municipal | CPS Energy San Antonio |
| Jones, Randy | Independent Generator | Calpine (via teleconference) |
| Kroskey, Tony | Cooperative | Brazos Electric Power (via teleconference) |
| Lovelace, Russell | Independent Power Marketer | Shell Energy |
| Marsh, Tony | Independent Power Marketer | Westar Energy |
| McEvoy, Kevin | Independent Power Marketer | Exelon |
| Munoz, Manny | Investor Owned Utility | CenterPoint |
| Reynolds, Jim | Independent REP | Power and Gas Consulting |
| Richard, Naomi | Cooperative | LCRA |
| Ross, Trina | Investor Owned Utility | AEP |
| Spangler, Bob | Investor Owned Utility | Luminant |
| Trefny, Floyd | Independent Power Marketer | Reliant Energy, Inc. |
| Trenary, Michelle | Independent Power Marketer | Tenaska Power Services |

Assigned Proxies:

- Melanie Harden (Large Commercial Consumers, Town of Flower Mound) to Nick Fehrenbach

- Stephen Massey (City of Allen) to Chris Brewster

- James Uhelski (Pioneer Natural Resources USA, Inc.) to John Rainey

Assigned Alternates:

- Steve Madden (StarTex Power), Read Comstock (Strategic Energy), Timothy Hamilton (Accent Energy), Timothy Rogers (Cirro Group), Michelle Cutrer (Green Mountain Energy), Brian Berend (Stream Energy), and Guy Souheaver(Integrys Energy Services) to Jim Reynolds

- Don Wilson (City of Eastland) to Chris Brewster

- Stanley Newton (Westar Energy, Inc.) to Tony Marsh

Non-Voting Attendees:

| Name | Representing |
| --- | --- |
| Alford, Anthony | CenterPoint (via teleconference) |
| Anderson, Clinton | Sungard |
| Bailey, Dan | City of Garland (via teleconference) |
| Barrow, Les | CPS Energy San Antonio (via teleconference) |
| Boyd, Tom | Tenaska |
| Bradley, Beth | Aces Power (via teleconference) |
| Briscoe, Judy | BP (via teleconference) |
| Castillo, Phyllis | Reliant Energy, Inc. (via teleconference) |
| Chang, Robin | The Structure Group (via teleconference) |
| Cochran, Seth | Sempra Energy |
| Crozier, Richard | Brownsville Public Utilities |
| Dickinson, Kenneth | BP (via teleconference) |
| Fehrenbach, Nick | City of Dallas (via teleconference) |
| Fox, Kip | AEP |
| Garrett, Shelia | PNM Resources (via teleconference) |
| Goff, Eric | Reliant Energy, Inc. |
| Gurley, Larry | TXU |
| Harrell, Patty | DC Energy (via teleconference) |
| Jacoby, Jim | AEP (via teleconference) |
| Jennings, Kenneth | Duke Energy (via teleconference) |
| John, Ebby | CenterPoint (via teleconference) |
| Jones, Calpine | Calpine (via teleconference) |
| Jones, Dan | Potomac Economics |
| Jou, Ching | AEP (via teleconference) |
| Kolodziej, Eddie | Customized Energy Solutions |
| Krajecki, Jim | APX, Inc. |
| Lucas, Ross | Sungard Energy (via teleconference) |
| Marx, Eddie | Power Costs, Inc. (via teleconference) |
| McMurray, Mark | Direct Energy |
| Morris, Sandra | LCRA (via teleconference) |
| Ogelman, Kenan | CPS Energy San Antonio |
| Palani, Ananth | EnergyCo (via teleconference) |
| Petoskey, Lisa | PNM Resources (via teleconference) |
| Quin, Scott | Power Costs, Inc. |
| Rambo, Carla | CPS Energy San Antonio (via teleconference) |
| Ramirez, Richard | LCRA (via teleconference) |
| Shumate, Walt | Shumate & Assoc. |
| Siddiqi, Shams | Crescent Power |
| Stanfield, Leonard | CPS Energy San Antonio (via teleconference) |
| Stappers, Hugo | SoftSmiths (via teleconference) |
| Starr, Lee | Bryan Texas Utilities (via teleconference) |
| Traffan, Jill | LCRA (via teleconference) |
| Woodard, Stacey | Austin Energy (via teleconference) |

ERCOT Staff:

Name

Anderson, SallyRose

Anderson, Troy

Barry, Stacy

Bauld, Amanda (via teleconference)

Boren, Ann

Brenner, Tobi (via teleconference)

Bridges, Stacy

Bridges, Stacy (via teleconference)

Caufield, Dennis (via teleconference)

Clarke, Linda (via teleconference)

Coon, Patrick

Cote, Daryl

Crews, Curtis

Day, Betty (via teleconference)

Deller, Art (via teleconference)

Economides, Brett (via teleconference)

Forfia, David

Garner, Ingrid (via teleconference)

Garza, Beth

Hackett, David (via teleconference)

Hall, Eileen

Hansen, Charles

Hensley, Stacy (via teleconference)

Hilton, Keely (via teleconference)

Hobbs, Kristi (via teleconference)

Horne, Kate (via teleconference)

Howard, Richard (via teleconference)

Kasparian, Ken (via teleconference)

Kerr, Stephen (via teleconference)

Koeppl, Sheri (via teleconference)

Krishnaswamy, Sankara (via teleconference)

Lamoree, Karen

Levine, John

Madden, Terry (via teleconference)

Martinez, Adam

Matlock, Robert (via teleconference)

Maxwell, Beth (via teleconference)

McIntyre, Kenneth (via teleconference)

Middleton, Scott

Moorty, Sainath

Nixon, Murray (via teleconference)

Pabbisetty, Suresh

Patterson, Mark

Peljto, Haso (via teleconference)

Ply, Janet

Ragsdale, Kenneth

Raina, Gokal (via teleconference)

Ren, Yongjun (via teleconference)

Rickerson, Woody

Robinson, Jeff (via teleconference)

Rose, Erica (via teleconference)

Sarasa, Raj

Smallwood, Aaron

Spencer, Julia (via teleconference)

Sumanam, Kalyan

Surendran, Resmi (via teleconference)

T1indall, Sandra (via teleconference)

Tindall, Sandra (via teleconference)

Tucker, Carrie (via teleconference)

Wang, Sharon (via teleconference)

White, Steve (via teleconference)

Yager, Cheryl

Yan, Kangning (via teleconference)

Unless otherwise noted, all Market Segments were present for the vote.

Call to Order

Stacy Bridges called the TPTF meeting to order at 9:30 a.m. on Monday, August 25, 2008.

Antitrust Admonition

Mr. Bridges read the Antitrust Admonition as displayed. He asked those who have not yet reviewed the Antitrust Guidelines to do so. Copies of the Antitrust Guidelines were available.

Review Of Meeting Agenda (See Key Documents)

Mr. Bridges reviewed the agenda for the three-day meeting.

Confirm Future Meetings

Mr. Bridges confirmed the following future TPTF meetings at the ERCOT Met Center:

- September 8 – 9, 2008

- September 22 – 24, 2008

- October 13 – 14, 2008

- October 27 – 29, 2008

TPTF Housekeeping Items (See Key Documents)

Mr. Bridges discussed four revisions that were made to vote tallies from the May 22 – 23, 2008 and July 7 – 8, 2008 TPTF meetings to reflect representation for PSEG Energy Resources and Trade in the Independent Power Marketer (IPM) Market Segment. No one objected to the revisions.

Consider Approval of Meeting Minutes (See Key Documents)

Mr. Bridges reviewed market comments for the August 11 – 12, 2008 TPTF meeting minutes. Randy Jones moved to approve the meeting minutes as amended by market comments. James Jackson seconded the motion. The motion carried by voice vote with one abstention from the Cooperative Market Segment. The Independent Generator and Consumer Market Segments were not represented for the vote.

Nodal Status Report (See Key Documents)

Adam Martinez provided an update on the status of the integrated nodal program schedule, noting that all project schedules were integrated; that critical path was documented through nodal go-live; that areas of possible resource constraints had been identified; that ERCOT Business Owners had finished reviewing individual project schedules; that Market Participant Identity Management (MPIM), security, testing, and transition activities had been reviewed; that Project Evaluation and Review Technique (PERT) estimates were being reviewed and updated; and that simulations based upon Monte Carlo methods were being employed to help analyze risks in the new schedule. Mr. Martinez also discussed remaining work for the new schedule, including determinations for schedule contingencies.

Floyd Trefny opined that contingencies in the new schedule would reduce the sense of urgency necessary for nodal projects to make timely progress, and he recommended that ERCOT avoid incorporating contingencies into the new schedule.

Mr. Martinez proposed the following key dates for reviewing the new integrated schedule:

- Review with ERCOT executives on August 27, 2008

- Review with TPTF on September 8, 2008 (first review)

- Review with Technical Advisory Committee (TAC) on October 2, 2008

- Review with TPTF on October 13, 2008 (second review)

Market Participants requested that ERCOT provide an additional review of the integrated schedule at TPTF on September 22, 2008 so that TPTF could have the opportunity to complete two full review sessions before considering its endorsement of the new integrated schedule on October 13, 2008. Mr. Martinez confirmed that an additional review could be scheduled for September 22, 2008.

Market Participants requested that the initial meeting materials for the first TPTF review session be posted by September 3, 2008.

Change-Control Update (See Key Documents)

Troy Anderson provided an update on the status of change control, including a spreadsheet identifying post-Baseline 2 Nodal Protocol Revision Requests (NPRRs) and their respective approved status, essentiality, schedule impact, and cost impact. Mr. Anderson identified the NPRRs that had been included in the new integrated program schedule. Market Participants suggested revising the spreadsheet to include a column identifying the origination of each NPRR (i.e., Market Participant, ERCOT Staff, working group, etc.) to help clarify the factors driving the Nodal Protocol change process.

Nodal Project Status Updates (See Key Documents)

Mr. Martinez discussed the status of nodal projects, including the Network Model Management System (NMMS), the Energy Management System (EMS), the Market Management System (MMS), Commercial Systems (COMS), Congestion Revenue Rights (CRR), the Enterprise Integration Project (EIP), Integration and Product Testing (INT), and Web Services usage.

Quality Center Update (See Key Documents)

Eileen Hall provided an update on Quality Center reports, including nodal active defects by project, by vendor, and by severity trend. She also discussed ERCOT’s approach for leveraging historical testing data into the testing windows identified in the new integrated program schedule, noting that the EMS project had been used as a case study to illustrate the large amount of time required for defect management if sufficient testing time is not provided in the lower testing environments.

Nodal Question and Answer Session (See Key Documents)

Janet Ply provided a nodal question and answer session, noting that:

- Approval from the Texas Regional Entity (TRE) and North American Electric Reliability Corporation (NERC) is not currently expected to be necessary for nodal go-live, and the Public Utility Commission of Texas (PUCT) order is expected to be sufficient

- TPTF will be provided with a second review of the new schedule as requested on September 22, 2008, and interim WebExTM meetings will be scheduled as needed

- Everything in the integrated program-schedule framework is built out, but the Common Information Model (CIM) will still need to be delivered before a final go-live date is declared

- The current critical path for the new integrated schedule does not include any contingency; however, once the PERT estimates and Monte Carlo simulations identify the most probable ways to secure a realistic schedule, buffer tasks will be incorporated in strategic places (e.g., immediately prior to critical milestone dates on the critical path) to provide points of absorption for unknowns that might otherwise cause re-work

- ERCOT will try to distribute a package of materials related to the new schedule on September 3, 2008 so that TPTF will have some time to review the materials prior to the September 8 – 9, 2008 TPTF meeting

- ERCOT will try to identify what will be included in the package by Thursday, August 28, 2008; materials are expected to include activities on the critical path and activities with less than five days of float

Readiness Update (See Key Documents)

Karen Lamoree provided an update on ERCOT readiness, Market Participant readiness, ERCOT staffing, and the Cycle 4 Survey.

Readiness Metrics Inventories (See Key Documents)

Karen Lamoree and SallyRose Anderson discussed recent revisions and additions to the nodal Readiness Metrics.

RE: Completed Readiness Metrics

Ms. Lamoree and Ms. Anderson proposed closing selected Readiness Metrics as attested by the Early Delivery Systems (EDS) team. Mr. Trefny moved to forward the following Readiness Metrics to TAC for concurrence that they have been completed as presented by ERCOT staff and as attested to by the EDS Test Team:

- MP2, Qualified Scheduling Entity (QSE) with Resources Connectivity to EDS Environment

- MP3, QSE with Resources Upload of Security Constrained Economic Dispatch (SCED) Offers to EDS

- MP5, Inter-Control Center Communication Protocol (ICCP) Point-To-Point (PTP) Telemetry Test

- MP8, QSE Ability to Submit Transactions Via Market Information System (MIS)

- MP9, QSE Ability to Submit Web Service Transactions

Jim Reynolds seconded the motion. The motion carried by roll-call vote with 100% in favor and two abstentions from the Independent Generator and IPM Market Segments. The Consumer Market Segment was not represented for the vote.

It was noted that Readiness Metrics recognized as completed will be moved from the Active Readiness Metric Inventory into a Completed Metric Inventory document before forwarding to TAC approval.

RE: New and revised Readiness Metrics

Ms. Lamoree and Ms. Anderson discussed revisions for the Readiness Metrics as previously reviewed by TPTF. They also proposed activating a new metric, MP22, New Entrant Readiness, to measure new Market Participants according to criteria carried from MP2, MP3, MP5, MP8, and MP9 (recognized as completed in the vote above). It was noted that the new metric MP22 also includes additional measurement criteria related to Outage Scheduler and Load Frequency Control (LFC) testing. No one objected to activating the new metric. Additional revisions were incorporated as recommended by TPTF. Mr. Trefny moved to endorse ERCOT moving forward with the new Readiness Metric MP22, New Entrant Readiness, and to endorse ERCOT moving forward with revisions to the following Readiness Metric as discussed by TPTF on August 25, 2008:

- MP1, Market Participant Engagement,

- MP6, QSE and Transmission Service Provider (TSP) Telemetry/ICCP System Availability

- MP10, Mapping of Resources to Resource Nodes and Resources to ERCOT-Polled Settlement (EPS) Meters is Complete

- MP11, Market Participant Registration Activities

- MP12, Market Participant Completes Nodal Market Related Training

- MP13, Market Participant Completes Nodal Operations Related Training

- MP14-A, Market Participant EDS 2, Release 3 Trials Participation

- MP14-B, Market Participant EDS 2, Release 4 Trials Participation

- MP14-C, Market Participant EDS 2, TSP Model Synchronization Participation

- MP15-A, Market Participant EDS 3, Releases 5 and 6 Participation

- MP15-B, Market Participant EDS 3, Release 7 Trials Participation

- MP17, Market Participant Qualification Activities

- MP19, Load Serving Entitles (LSE) Engagement and Readiness

- MP20, Market Participant Ability to Submit Outage - Connectivity Test

Naomi Richard seconded the motion. The motion carried by roll-call vote with 100% in favor and one abstention from the Independent Generator Market Segment. The Consumer Market Segment was not represented for the vote.

Process Update (See Key Documents)

Mark Patterson discussed the Reliability Unit Commitment (RUC) Business Process, noting that an updated version would be published and distributed through TPTF Review following the meeting.

Mr. Patterson reminded TPTF that the Day-Ahead Market (DAM) Process and DAM Desk Procedure documents were still in review through August 28, 2008 and could be discussed in more detail during a future TPTF meeting.

NPRR141, Transmission/Distribution Service Provider Energy Storage for Reliability (See Key Documents)

TPTF tabled the discussion of NPRR141 to await PUCT and Protocol Revision Subcommittee (PRS) action on battery ownership issues related to the companion PRR768, TDSP Energy Storage for Reliability.

Meeting Recess and Resumption

Mr. Bridges recessed the TPTF meeting at 4:57 p.m. on Monday, August 25, 2008. The meeting resumed and was called to order at 8:30 a.m. on Tuesday, August 26, 2008.

NPRR146, ICCP Telemetry Information Submittals (See Key Documents)

Kip Fox discussed comments developed collaboratively by the Quick Response Working Group (QRWG) and ERCOT staff to recommend revising the submittal timeline to 15 days in NPRR146. Curtis Crews confirmed that the 15-day timeline was a suitable compromise and that it will need to be reflected by business processes, although it will not require significant system changes. Manny Munoz moved to endorse forwarding TPTF comments to PRS for NPRR146 as discussed at TPTF on August 26, 2008. Mr. Fox seconded the motion. The motion carried by roll-call vote with 100% in favor and two abstentions from the Consumer Market Segment. The Independent Generator Market Segment was not represented for the vote.

EDS Service Level Agreement for Nodal EDS Environments (See Key Documents)

David Forfia discussed EDS monitoring. Aaron Smallwood discussed recent updates for the EDS Service Level Agreement (SLA) for Nodal EDS Environments. Mr. Trefny moved to approve the updated EDS SLA for Nodal EDS Environments v5.3 as discussed by TPTF on August 26, 2008. Ms. Richard seconded the motion. The motion carried by unanimous roll-call vote.

System Implementation Group White Papers (See Key Documents)

Kenneth Ragsdale reviewed updates to incorporate market feedback for the following System Implementation Group (SIG) White Papers:

- SIG0008 Non-Modeled Generation

- SIG0002 Private Use Networks (PUNs)

- SIG0022 Transmission Constraint Model (TCM) for Real-Time Combined-Cycle Plant (CCP) Dispatch

- SIG0020 Rounding of Megawatt (MW) Values

- SIG0011 Net Generation

- SIG0009 Resource Node Location

TPTF provided additional feedback for these white papers and requested that all available SIG white papers be noticed for a possible vote during the September 8 – 9, 2008 TPTF meeting.

It was noted that additional information regarding impacts for the SIG0020 Rounding of MW Values white paper would be reported to TPTF following vendor assessments to be conducted in September 2008.

Registration Update (See Key Documents)

Scott Middleton provided an update on Registration activities, including the status of metrics MP11, Market Participant Registration Activities, and MP10, Mapping of Resources to Resource Nodes and Resources to EPS Meters. Mr. Middleton also introduced two new draft registration forms related to MP11—the Generation Site Topology form and the Non-Modeled Generation Declaration form. Mr. Middleton described some of the details for the Generation Site Topology form, noting its purpose to help ERCOT create a master inventory of Resource-owned transmission assets and to clarify ownership in parallel with TSP activities. The draft form is required for ERCOT to process Network Operations Model Change Requests (NOMCRs). Mr. Middleton confirmed that ERCOT will populate as much of this form as possible using available data before distributing the form to Resource Entities. He noted that the process for tracking the form will be rolled into metric MP11. The full details and timelines for both draft forms will be discussed during an upcoming WebEx market call (time and date to be determined). Mr. Middleton encouraged Market Participants to send any questions or suggestions regarding the upcoming WebEx to nodalmarkettransition@ercot.com.

Mr. Middleton noted that ERCOT will use service requests as the primary artifacts to demonstrate closure for metrics MP10 and MP11.

NPRR137, Synchronization and Update of Section 21

TPTF tabled discussion of NPRR137 until after the ERCOT Board of Directors (hereafter, the Board) acts upon PRR753, PRR Appeals Process.

NPRR140, Revision to CRR Obligation Margin Adder (See Key Documents)

Clayton Greer discussed market comments for NPRR140. Beth Garza and Cheryl Yager agreed to work offline with Shams Siddiqi to align LCRA comments with the current CRR implementation. Additional discussion of LCRA comments will be scheduled on the next TPTF agenda.

NPRR148, Treatment of Financial Information as Confidential (See Key Documents)

Mr. Greer discussed NPRR148, noting its purpose to include an additional line item (listed in the NPRR as item (y)) in Nodal Protocols Section 1.3.1.1, Items Considered Protected Information, to clarify that non-public information provided to ERCOT is to be treated as Protected Information. TPTF concurred with the proposed additional line item but recommended striking the non-substantive format and style changes provided by ERCOT Market Rules and addressing them in a separate NPRR when Section 1.3.1.1 is updated to be consistent with NPRRR102, Implementation of PUC Subst. R. 25.505(f), Publication of Resource and Load Information. Bob Spangler moved to endorse TPTF comments to accept item (y) as modified by TPTF on August 26, 2008 and to reject Market Rules changes in NPRR148. TPTF recommended that the Market Rules changes should be provided in a separate NPRR when this section is updated to be consistent with NPRR102. Russell Lovelace seconded the motion. The motion carried by roll-call vote, with 100% in favor and one abstention from the Investor Owned Utility (IOU) Market Segment. The Independent Generator Market Segment was not represented for the vote.

NPRR147, DAM Short Pay Changes (See Key Documents)

Mr. Greer discussed the revised DAM short-pay methodology proposed by NPRR147. Kevin Gresham discussed Reliant comments as posted by ERCOT Market Rules, noting that more time may be needed to review the short-pay methodology to ensure it is equitable, that it sufficiently minimizes potential cost impacts to any single Market Participant, and that it takes collections from appropriate entities according to the value of their participation in the DAM and Real-Time markets. In light of Reliant comments, TPTF noted that the policy issues related to NPRR147 would need to be resolved before TPTF proceeds with its nodal implementation determination. TPTF requested that PRS remand NPRR147 to the Wholesale Market Subcommittee (WMS) for further discussion with the understanding that TPTF will revisit NPRR147 following WMS feedback.

NPRR139, Available Credit Limit, Estimated Aggregate Liability, Future Credit Exposure Calculation Updates (See Key Documents)

Ms. Yager reviewed NPRR139 and made additional modifications to the document as recommended by TPTF. Mr. Spangler moved to endorse forwarding TPTF comments to PRS for NPRR139 as modified by TPTF on August 26, 2008 and to recognize NPRR139 as "Needed for Go-Live." Mr. Jackson seconded the motion. The motion carried by unanimous roll-call vote. The Independent Generator and Consumer Market Segments were not represented for the vote.

Emergency Electric Curtailment Plan Media Appeal Change (See Key Documents)

Ann Boren discussed revisions to the energy conservation media appeal requirement for Emergency Electric Curtailment Plan (EECP) Step Two as proposed by NPRR142, EECP Media Appeal Change. She noted that the revisions had been synchronized in Nodal Operating Guide Revision Request (NOGRR) 022, EECP Media Appeal Change. No comments were received for either document during the TPTF review ending August 6, 2008. TPTF did not recommend any additional revisions. Mr. Munoz moved to endorse the changes for EECP Media Appeal in NPRR142 and NOGRR022 as submitted to TPTF on August 26, 2008 and to recognize the change as "Needed for Go-Live." Mr. Reynolds seconded the motion. The motion carried by unanimous roll-call vote. The Independent Generator and Consumer Market Segments were not represented for the vote.

Meeting Recess and Resumption

Mr. Bridges recessed the TPTF meeting at 4:50 p.m. on Tuesday, August 26, 2008. The meeting resumed and was called to order at 8:30 a.m. on Wednesday, August 27, 2008.

MIS/CRR/NMMS CRR Map Requirements (See Key Documents)

Ms. Garza and Stacy Barry reviewed recent updates for the MIS/CRR/NMMS CRR Map Requirements. Mr. Spangler moved to approve the MIS/CRR/NMMS CRR Map Requirements v0.93 as submitted to TPTF on August 27, 2008. Mr. R. Jones seconded the motion. The motion carried by roll-call vote with 100% in favor and one abstention from the IOU Market Segment. The Consumer Market Segment was not represented fort the vote.

Texas Nodal Market Single-Entry Model Go-Live Procedure (See Key Documents)

Kalyan Sumanam discussed the Texas Nodal Market Single Entry Model (SEM) Go-Live Procedure and made additional revisions to the document as recommended by TPTF. Mr. R. Jones moved to approve the SEM Go-Live Procedure v0.08 as modified by TPTF on August 27, 2008. Mr. Jackson seconded the motion. The motion carried by unanimous roll-call vote. The Consumer Market Segment was not represented for the vote.

QRWG Update (See Key Documents)

Draft NPRR, Clarify Definition of a Generator Output Breaker in the Outage Scheduler

Anthony Alford discussed the draft NPRR, Clarify Definition of a Generator Output Breaker in the Outage Scheduler. Market Participants concurred that the draft NPRR represented a reasonable approach for distinguishing which generator output breakers to exempt from entry in the nodal Outage Scheduler. It was requested that the NPRR would be submitted to Market Rules by the sponsor and then circulated back to TPTF to receive an essentiality declaration once processed by ERCOT Market Rules. Mr. R. Jones moved to endorse the draft NPRR Clarify Definition of a Generator Output Breaker in the Outage Scheduler as discussed by TPTF on August 27, 2008, and to recommend that CenterPoint submit the draft NPRR to PRS. Mr. Spangler seconded the motion. The motion carried by roll-call vote with 100% in favor and two abstentions from the IPM Market Segment. The Consumer Market Segment was not represented for the vote.

Draft NPRR, Generation Resource Fixed Quantity Block Offer

TPTF deferred the discussion of the draft NPRR, Generation Resource Fixed Quantity Block Offer, until the September 8 – 9, 2008 TPTF meeting.

Outage Scheduler Update (See Key Documents)

Woody Rickerson discussed options to address the previous TPTF request to provide functionality for QSEs and Resources to enter their own Outages in the nodal Outage Scheduler. It was noted that more work would be needed to identify the best path forward. Take-away items from the discussion included:

- Work with the vendor to determine impacts for implementing an additional Owner/Operator user role in the nodal Outage Scheduler

- Assess how to smarten the metrics to ensure that QSE accountability for Outage entries is properly assigned whenever TSPs make proxy entries

- Consider how to revise the Nodal Protocol to clarify accountability for Outage entries

- Visit with the TRE to discuss accountability issues related to Outage entries

Adjournment of Meeting

Mr. Bridges noted that the following discussion items would be deferred to the September 8 – 9, 2008 TPTF meeting:

- NPRR143, Section 9.9.1, Invoice Recipient Payment to ERCOT for the CRR Auction, Clean-up

- Mock Credit Exposure Reports Spreadsheet

Mr. Bridges adjourned the TPTF meeting at 11:40 a.m. on Wednesday, August 27, 2008.

- Action Items:

| New Action Items Identified | Responsible Party |
| --- | --- |
| Notice all available SIG white papers for a possible vote during the September 8 – 9, 2008 TPTF meeting | S. Bridges |
| Report additional information to TPTF regarding impacts for the SIG0020 Rounding of MW Values white paper following vendor assessments in September 2008 | K. Ragsdale S. Moorty |
| Work offline with Mr. Siddiqi and Mr. Greer to align LCRA comments with the current CRR implementation | C. Yager B. Garza |
| Follow-up items for Outage Scheduler issues: - Work with the vendor to determine impacts for implementing an additional Owner/Operator user role in the nodal Outage Scheduler - Assess how to smarten the metrics to ensure that QSE accountability for Outage entries is properly assigned whenever TSPs make proxy entries - Consider how to revise the Nodal Protocol to clarify accountability for Outage entries - Visit with the TRE to discuss accountability issues related to Outage entries | W. Rickerson |

The Meeting Attendance covers all three days of the TPTF meeting, although some attendees may not have been present for the entire meeting.

The Agenda, Key Documents, and Roll-Call Votes for the August 25 – 27, 2008 TPTF meeting may be found at:

http://www.ercot.com/calendar/2008/08/20080825-TPTF.