## Slide 1: PMO Update to PRS
Troy Anderson
ERCOT Program Management Office
September 24, 2008

## Slide 2: PMO Update - Agenda
  NPRR Impact Analysis Update
  2009 Project Reforecast
  Recent Project Implementations
    August

## Slide 3: PMO Update - NPRR Impact Analysis Update
NPRR Impact Analysis is now proceeding
Based on the Board’s desire to bring a heightened awareness of changes to the Nodal project, we have added two ERCOT executive approval steps to the Impact Analysis process
  If TPTF declares an NPRR “Needed for Go-Live”…
    Approval is required by the Nodal Program Director before Nodal resources can be applied to the Impact Analysis effort
      If ERCOT disagrees with TPTF’s determination of “Needed for Go-Live”, immediate communication will be provided to TPTF and PRS
    Final approval required by CEO before Impact Analysis is posted for PRS
The new approval steps are being applied to all NPRRs from this point forward

## Slide 4: PMO Update - 2009 Project List Reassessment
ERCOT is beginning a review of the 2009 project list
  Driving factors
    Nodal delay
    Withdrawal of ERCOT fee case
Key considerations in the reassessment of 2009 project needs
  Consider what won’t be required due to the Nodal delay
  Consider what will be needed to keep Zonal systems running
  Preserve funding for key market projects (such as Advanced Metering)
  Adjust carryover funding needed by active projects
The appropriate market subcommittees will be involved
Timing of reforecast isn’t definitive but if the process goes well we will bring a draft 2009 project list to PRS in October

## Slide 5: PMO Update - YTD 2008 Project Implementations
January 2008
  IO PR-70050_01 EIS ETL Tool Implementation
February 2008
  CO PR-70044_01 MET Center Facility Analysis
  RO PR-70005_01 MO SAS70 Procedures Optimization
  IO PR-70012_01 Cyber Security Project #14
  IO PR-70037_01 OC-3 Microwave Replacement
  SO PR-70035_01 2007 REC Program Modifications
March 2008
  IO PR-60055_01 Enterprise Service Management
  IO PR-60013_01 Enhanced Digital Certificate Program
  MO PR-70038_01 ERCOT.com Infrastructure Enhancement
        (Collage Infrastructure Redesign)
  CO PR-70013_01 Corporate Document Management
  CO PR-70041_01 Taylor Control Room Display System Replacement
April 2008
  None

## Slide 6: PMO Update - YTD 2008 Project Implementations (cont’d)
May 2008
  MO PR-70048_01 MV90xi System Upgrade
  CO PR-70053_01 Video Teleconferencing
  IO PR-70055_01 Additional Production SAN Capacity
June 2008
  MO PR-60077_01 ERCOT.com Registered Area
  IO PR-70030_01 Tellabs DCCS System Replacement
  IO PR-80022_01 Additional SAN Capacity for Projects
July 2008
  RO PR-60008_01 Terms and Conditions & Performance Measures
  CO PR-70023_01 CyberSecurity Project #2
  CO PR-70047_01 Corporate Application Environment True-Up
  CO PR-80010_01 Ruby Standardization
  CO PR-60073_01 eRecruiting

## Slide 7: PMO Update - YTD 2008 Project Implementations (cont’d)
August 2008
  RO PR-60015_01 Siebel Data Model Assessment
  CO PR-80035_01 Intranet Assessment HR & Communications
  IO PR-70054_01 Blade Refresh