| NPRR Number | 146 | NPRR Title | ICCP Telemetry Information Submittals |  |
| --- | --- | --- | --- | --- |
| Timeline | Normal | Recommended Action |  | Approval |
| Date of Decision |  | September 24, 2008 |  |  |
| Nodal Protocol Section Requiring Revision |  | 3.10.1, Time Line for Network Operations Model Change Requests |  |  |
| Proposed Effective Date |  | To be determined. |  |  |
| Priority and Rank Assigned |  | To be determined. |  |  |
| Revision Description |  | This Nodal Protocol Revision Request (NPRR) changes the ICCP data object names submittal to 15 days. |  |  |
| Overall Market Benefit |  | Improve the quality of information ERCOT receives on ICCP data object names. |  |  |
| Overall Market Impact |  | Reduced burden on Transmission Service Providers (TSPs) and Qualified Scheduling Entities (QSEs) to provide needed information in a timely and correct manner. Will also prevent TSPs and ERCOT from modeling ICCP data object names that may not ever exist and then removing them at a later date. |  |  |
| Consumer Impact |  | None |  |  |
| Credit Impacts |  | To be determined. |  |  |
| Procedural History |  | - On 7/31/08, NPRR146 was posted. - On 8/8/08, ERCOT comments were posted. - On 8/21/08, PRS considered NPRR146. - On 9/2/08, Transition Plan Task Force (TPTF) comments and a TPTF voting ballot were posted. - On 9/10/08, a second set of TPTF comments and a second TPTF voting ballot were posted. - On 9/24/08, PRS again considered NPRR146. |  |  |
| PRS Decision |  | On 8/21/08, PRS unanimously voted to refer NPRR146 to TPTF. All Market Segments were present for the vote. On 9/24/08, PRS unanimously voted to recommend approval of NPRR146 as amended by TPTF comments dated September 2, 2008. All Market Segments were present for the vote. |  |  |
| Summary of PRS Discussion |  | On 8/21/08, PRS noted that TPTF had not reviewed NPRR146. On 9/24/08, PRS noted that TPTF proposed revisions to NPRR146. |  |  |

ERCOT/Market Segment Impacts and Benefits

| Assumptions | 1 | ERCOT can complete model testing for telemetry data in less than 7 days for new telemetry points. |  |
| --- | --- | --- | --- |
|  | 2 |  |  |
|  | 3 |  |  |
|  | 4 |  |  |
| Market Cost |  | Impact Area | Monetary Impact |
|  | 1 | None | No additional implementation cost |
|  | 2 |  | No additional staffing cost. Possible contractor reduction. |
|  | 3 |  |  |
|  | 4 |  |  |
| Market Benefit |  | Impact Area | Monetary Impact |
|  | 1 | Enhanced TSP and ERCOT efficiency due to not having to enter data multiple times into the NMMS. There is no reason to add data three months ahead of time and then to have to go back and change it later. | 200 man-hours per year @ $65/hour |
|  | 2 | Enhanced Market Participant efficiency | More accurate telemetry data, less likely to test incorrectly. Save 120 man-hours per year at $65/hr for settlements & billing information. |
|  | 3 | Reduced congestion cost | Potential to reduce congestion cost with more accurate telemetry data. |
|  | 4 |  |  |
| Additional Qualitative Information | 1 | Will give ERCOT shorter time period for telemetry testing from 90 to seven days. This only affects the ICCP data; all other model information will still be provided to ERCOT as required. |  |
|  | 2 | Fewer model changes for ERCOT models. Testing will be reduced due to fewer changes. |  |
|  | 3 |  |  |
|  | 4 |  |  |
| Other Comments | 1 | ERCOT systems require less changes and better modeling of telemetry information. |  |
|  | 2 | Fewer work-arounds and better telemetry information. |  |
|  | 3 |  |  |
|  | 4 |  |  |

| Comments Received |  |
| --- | --- |
| Comment Author | Comment Summary |
| ERCOT 080808 | Expresses opposition to proposed revisions; states that ERCOT system designs and business processes would require significant changes that would overshadow any perceived benefit proposed. |
| TPTF 090208 | Proposes revisions to change the proposed seven-day timeline for submitting ICCP telemetry to 15 days; proposes revisions to the NPRR cover page language. |
| TPTF 091008 | Indicates that on September 8, 2008, TPTF declared NPRR146 to be "Needed for Go-Live." |

| Original Sponsor |  |
| --- | --- |
| Name | Jim Jacoby |
| Company | American Electric Power |
| Market Segment | Investor Owned Utility (IOU) |

Proposed Protocol Language Revision

3.10.1	Time Line for Network Operations Model Change Requests

(1)	ERCOT shall perform periodic updates to the ERCOT Network Operations Model.  Market Participants may provide Network Operations Model updates to ERCOT to implement planned transmission and Resource construction one year before the required submittal date below.  TSPs and Resource Entities must timely submit Network Operations Model changes pursuant to the schedule in this Section to be included in the updates.

(2)	For a facility addition, revision, or deletion to be included in any Network Operations Model update, all technical modeling information must be submitted to ERCOT pursuant to the ERCOT NOMCR process.

(3)	TSPs and Resource Entities shall submit Network Operations Model updates at least three months prior to the physical equipment change.  ERCOT shall update the Network Operations Model according to the following table:

| Deadline to Submit Information to ERCOT Note 1 | Model Complete and Available for Test Note 2 | Updated Network Operations Model Testing Complete Note 3 | Update Network Operations Model Production Environment | Target Physical Equipment In-Service Date Note 4 |
| --- | --- | --- | --- | --- |
| Jan 1 | Feb 15 | March 15 | April 1 | Month of April |
| Feb 1 | March 15 | April 15 | May 1 | Month of May |
| March 1 | April 15 | May 15 | June 1 | Months of June–August SUMMER MODEL |
| June 1 | July 15 | August 15 | September 1 | Month of September |
| July 1 | August 15 | September 15 | October 1 | Month of October |
| August 1 | September 15 | October 15 | November 1 | Month of November |
| September 1 | October 15 | November 15 | December 1 | Month of December |
| October 1 | November 15 | December 15 | January 1 | Month of January (the next year) |
| November 1 | December 15 | January 15 | February 1 | Month of February (the next year) |
| December 1 | January 15 | February 15 | March 1 | Month of March (the next year) |

Notes:

1.	Transmission and Resource data submissions complete per ERCOT Network Operations Model Change Request process for inclusion in next update period.

2.	Network Operations Model data changes and preliminary fidelity test complete by using the Network Operations Model test facility described in Section 3.10.4(3).  The test version of the Network Operations Model will be available for market review and further testing by Market Participants.

3.	Testing of the Network Operations Model by Market Participants is complete and ERCOT begins the Energy Management System testing prior to placing the new model into the production environment.

4.	Updates include changes starting at this date and ending within the same month.

(4) 	ERCOT shall only approve energization requests when the Transmission Element is satisfactorily modeled in the Network Operations Model.

(5)	In order to allow for construction schedules, TSPs may use pseudo-breakers and switches to designate future facilities configurations such that the Network Operations Model topology may be correctly implemented as construction of new facilities is accomplished.

(6)	NOMCR submittals containing only ICCP data object names shall be provided no later than fifteen (15) days prior to the proposed Energize Date for Transmission Elements represented by the ICCP data object names and shall not be subject to IMM and PUC reporting (reference 3.10.4 ERCOT Responsibilities (5)).