## Slide 1: Texas Nodal Market Implementation: Program Update
Ron Hinsley
Notes: <number>

## Slide 2: Agenda
Program Status
  Readiness and Delivery Status
  Cost
  Schedule
  Program Controls and Transparency
Common Information Model (CIM)
  CIM – Today and Future
  CIM Activities
  EMS CIM Importer Status
Notes: <number>

## Slide 3: Program Status
`
Nodal Delivery status is:
Cost
Schedule
Scope / Quality
Nodal Delivery
Red status driven by quality, schedule, and cost impacts
Red
Red
Amber
Red*
* Final cost unknown until new schedule confirmed
Red
 | Scope | Quality | Schedule | Cost
Green | Program is aligned with current protocols | All Nodal products currently achieve quality standards | Go-Live = 12/1/2008 | Estimate at Complete =< 319M
Amber | Program is aligned to previous protocol versions | Most Nodal products currently achieve quality standards | Go-Live =< 30 days | Estimate at Complete =< 319M +10%
Red | Program is not aligned to protocols | Product quality not sufficient for Nodal launch | Go-Live =>30 days+ | Estimate at Complete => 319M +10%
ERCOT Staff Readiness status is:
Market Participant Readiness status is:
Amber status driven by limited response from entities needing to modify RARFs (MP11) and limited transaction submissions testing (MP22)
Amber status driven by ERCOT staffing, process, and training metrics (E8, 9, 1)
Amber
Amber
Notes: <number>
<number>
The program will be replacing this slide in the future with improved measures and program controls.
Current Market Participant and ERCOT Readiness status do not reflect the changes resulting from recently approved metrics. Those changes will not be seen until October.

## Slide 4
Variance
(over)/under
Cost Element
Budget
Actual
Budget
Internal Labor
$ 40.6
$ 41.0
$ (0.4)
External Labor
161.1
171.2
(10.1)
Hardware / Software
60.2
61.5
(1.3)
Travel and Other
11.2
7.0
4.2
Subtotal
$ 273.1
$ 280.7
$ (7.6)
Finance Charge
9.2
10.1
(0.9)
Total
$ 282.3
$ 290.8
$ (8.5)
Nodal Program
Cost Element Summary
($ Millions)
Through August 2008
When the integrated schedule has been finalized and the financial impact determined we will incorporate this into an updated forecast
Cost: Element Summary

## Slide 5: Schedule
The PUCT has requested completion of a new cost/benefit analysis of the nodal project (to be completed in 60-90 days), and to delay any decisions on the new schedule
TPTF has requested schedule information for the next four months in order to plan for resources within their organizations. For planning purposes, ERCOT has communicated to TPTF:
  For now, EDS will continue to do focused input testing for the state estimator and SCED
  No new functionality will be delivered to EDS in the next four months (reports, web services, MMS, etc.). In addition, EDS will not run DAM, Single-Entry Model, nor any LFC Tests (2 or 8 hr) during this time period
  EDS is committed to providing adequate lead time to market participants for preparations related to EDS activities; schedule information will be made available as soon as the information can be released
Notes: <number>

## Slide 6: Program Controls and Transparency
ERCOT is focusing efforts to provide clearer and more accurate communications to all interested parties
Implementing a set of new / improved program controls that will provide more timely reporting and accurate communications of program status
Program Status – weekly report of program–level activities, highlights, and health indicators
Project Status – comprehensive summary of core project activities, highlights, milestones, risks/issues, health indicators
Notes: <number>

## Slide 7
<number>
Texas Nodal Program Update
September 4, 2008
Common Information Model (CIM)
Notes: <number>

## Slide 8: Today: CIM Integration Development Process (Pre-Single Entry Model)
Notes: Today, ERCOT uses infrequent snapshots of data from zonal production EMS as a starting seed, and layers nodal data from various other databases to produce a CIM XML file that confirms to the CIM schema. NMMS sends the CIM XML file to both EMS and MMS, who consume the data via their respective CIM importer. The allows the systems to test their processes (i.e. DAM, HRUC, LFC, SE). Any data-related errors are sent back to the NMMS team to correct and then start testing again.
EMS and MMS both provide schema and data quality feedback (via people).

## Slide 9: Future: CIM Integration With the Single-Entry Model
Notes: In the future, nodal systems will rely on TSPs entering NOMCRs into NMMS to capture changes to the network model, rather than using zonal data merged with nodal data to produce the CIM XML file. NMMS also sends network model data to other ERCOT systems, via the integration layer.

## Slide 10: Common Information Model Activities
Delivery of a validated Common Information Model (CIM) Extensible Markup Language (XML) file that is populated with production data is the next major milestone for ERCOT
  CIM data population and validation activities are currently the main critical items for the program
  MMS and EMS are dependent on a synchronized CIM XML file
  Strong program focus is on all CIM development activities
  Completion is central to nodal functionality
Issue/Risk is the required NMMS data collection and quality
  Mitigation: eliminating dependency on zonal seed data
  Mitigation: adding more rigorous audit procedures and validation metrics
Activities / Recent Successes
  NMMS implemented and is currently processing the initial validation rule set
  A technical review of Resource Asset Registration Form (RARF) data submitted to ERCOT is in progress. "Audit Reports" will be sent to Market Participants by Sept. 30, 2008 and will continue until quality measures are achieved
  Both MMS and EMS CIM importers recently successfully consumed version 1.20 CIM XML test file
Notes: <number>
RARF Data Quality
ERCOT has begun to develop business rules (from each of the applications) and apply those rules to the data received.
ERCOT is preparing "Audit Reports" that we plan to send to each Resource Entity (RE). Once the RE has the Audit Report in front of them, ERCOT plans to work closely with them to have them resubmit RARFs as necessary.
Release of Audit Reports was moved from Sept. 19 to Sept. 30 based on feedback and changes requested by Market Participants.
<number>

## Slide 11: EMS CIM Importer Status (as of Sept. 25)
Pre-FAT in progress at ERCOT
  Started Sept. 15; goal is to complete by Oct. 10
  EMS Importer tool testing
    Cumulative current number of defects = 38 (includes one severity 2)
    10 defects ready for retest
  Database comparison in progress
    Completed three comparisons with no major issues (dynrtg, scadamom, oagmom)
    In progress with remaining four comparisons (netmom, genmom, ctgs, rasmom)
  Completed all application test validations
Next steps
  Clean pre-FAT critical defects; add product fixes
  Update test scripts; ready testing platform
  Start FAT at ERCOT (tentatively scheduled for Oct. 13)
Notes: <number>
<number>

## Slide 12
<number>
Texas Nodal Program Update
September 4, 2008
Questions?
Notes: <number>