## Slide 1: Advanced Metering TAC Update of ERCOT Activities 10/2/08

## Slide 2: ERCOT Advanced Metering Update
PUCT Project 34610 – Implementation of Advanced Metering
PUCT 34610 Sub-Project | Corresponding ERCOT Project
1. Interim Project | N/A
2. Web Portal Project | N/A
3. ERCOT Settlement Project | PR70057_01 AMIT Study for Long Term Settlement Solution PR80027_01 Advanced Metering - Market Changes for PUCT 34610 (Interim settlement solution)
4. Home Area Network (HAN) | N/A
5. Retail Interface Project | TBD
6. Customer Education | N/A

## Slide 3: ERCOT Advanced Metering Update
PR70057_01 AMIT Study for Long Term Settlement Solution
(fka ERCOT System Throughput for IDR)
Scope:
  Estimate the volume of IDR data that ERCOT systems could support with enhancements to the current systems and without system degradation. (COMPLETED 05/19 – results on next slide)
  Scale or modify existing ERCOT systems to increase capacity for IDR data. (Removed from scope at Market’s request.)
  Produce a design document (“blueprint”) that provides the future vision for ERCOT systems necessary to support up to 7 million IDR ESI IDs. EDS in partnership with Black & Veatch were selected to deliver this “blueprint” – i.e., the “AMIT Study for Long Term Settlement Solution”.
Budget Overview:
2008 PPL Budget
Original: $100 – 250K
Revised*: $250 – 500K
*Budget revised as a result of scope changes noted above and addition of outside vendor.

## Slide 4: ERCOT Advanced Metering Update
PR70057_01 AMIT Study for Long Term Settlement Solution
ERCOT IDR Threshold – Preliminary Estimates (scope item 1)

## Slide 5: ERCOT Advanced Metering Update
PR70057_01 AMIT Study for Long Term Settlement Solution
  The PUCT Advanced Metering Implementation Team (AMIT) requested that ERCOT procure a third party vendor to conduct a “study”.
Purpose of the study:
  Evaluate and provide possible long-term solutions for ERCOT systems to accommodate full settlement of the Texas electric market using 15-minute interval data from Advanced Metering Systems (AMS).
Study Output:
  Costs and benefits associated with possible long-term solutions as well as the associated timelines for implementation.

## Slide 6: ERCOT Advanced Metering Update
PR70057_01 AMIT Study for Long Term Settlement Solution
High Level Schedule
Kickoff 09/29
10/03
10/10
10/17
10/24
10/31
11/07
11/14
11/21
AMIT Study Kickoff 09/29/2008
AMIT Study Complete 11/21/2008
1 Current State
2 Requirements
3 Tech Components
4 Long Term Solution
5 Ongoing Support Plans
6 Implementation/Migration Plans
7 AMIT Presentation

## Slide 7: ERCOT Advanced Metering Update
PR80027_01 Advanced Metering_ Market Changes for PUCT 34610
(Interim Settlement Solution)
Scope:
  Modify ERCOT systems to provide for the settlement of 15-min data received from advanced meters including small distributed renewable generators. Source: PRR766, PRR756
Schedule:
Planning Phase Begins | 09/29/2008
Business Requirements Complete | 12/02/2008
Conceptual Design Complete | 01/07/2009
Detail Designs Complete | 02/09/2009
Planning Complete | 02/20/2009
Budget:
2008 PPL Budget $500k - $1M

## Slide 8
Questions?