## 2009 Recommendations
MO 2009 Project Prioritization - PUCT, Market and ERCOT Projects
Source | Committee | Prog Area | Source Doc | Project | Project No. | Current Status | Project Manager | 2009 Priority | 2009 Rank | 2009 Budget Range | 2009 Running Range | Summary Description | CBA Score (avail for those prior to 2008) | Net Benefit | Benefit Summary
ERCOT | MO | MO | PUCT 34610 | AMIT Study for Long Term Settlement (fkaERCOT System Throughput for IDR Advanced Metering) | 70057_01 | Execution | H. Day | 0 - Previously Approved | 0.1 | <$100k | <$1M | Planned carry over for closing: Provide incremental increases in IDR processing capability for ERCOT systems. | 0 | -500000 | The project improves the efficiency of ERCOT retail transaction systems. It provides incremental increases in IDR processing capability for ERCOT systems. Support market's transition to demand response-type programs.
ABOVE THIS LINE --Projects expected to carry over from 2008
ERCOT | MO | MO |  | MPIM integration with Siebel | New | Not started |  | 2 - High | 1 | <$100k | $250-$500k | Eliminate manual workaround and dual entry that can be complete after Siebel code freeze from Nodal Registration. | 0 | TBD | Reduce manual efforts.
Market/ERCOT | TPTF | MO |  | Web-enabled Registration | New | Not started |  | 2 - High | 2 | $100k-$250k | $250-$500k | Begin Planning efforts on an Interface and provide web-enabling registration forms (including RARF, NOI, interconnect, etc.) - total of around 50 forms. Will be broken into phases - 1-MP Registration and Contact UI: Registration Data Maintenance 2-Resource Registration UI: General Site and EMS/MMS resource data 3-Resource Registration UI: Network Model data 4-Resource Registration UI: Planning and Protection data | 0 | TBD | Reduce manual efforts for processing and monitoring web-enabling registration forms.
ERCOT | MO | MO |  | Information Lifecycle Management | New | Not started |  | 2 - High | 3 | $500-$750k | $500k-$1M | Implement a strategy to archive data and maintain integrity and performance. | 0 | TBD | Performance, storage, and space optimization.
BELOW THIS LINE --Projects Deferred due to Nodal Delay or cancelled
Market | COPS | MO | PRR478 PR385 | Demand Response for Settlement | 40056_01 | Defer? | 2 - High | 1 - Critical |  | $500k-$750k | $500k-$1M | Implementation resulting from PUCT projecr 34610 or related PUCT Order | 0 | TBD | 1.The time lag between approving a new profile and being able to settle ESI IDs using the new profile will be reduced. 2. New profiles are expected to be subject to significant population change as new ESI IDs are identified for inclusion in the profile; lagged-dynamic samples will accommodate these changes more quickly, accurately and efficiently than is possible with adjusted static models. 3. Use of lagged dynamic samples will allow the market to audit ESI IDs being assigned to new profiles and will create an incentive for CRs using the profile to limit the inclusion of ESI IDs to those appropriate to the profile.
Market/ERCOT | TPTF | MO | NPR 5&12 | Verifiable Cost Management System | New | Defer |  | 2 - High |  | $100k-$250k | $500k-$1M | Creation of the Verifiable Cost Management System (VCMS), the interface QSEs will use for submitting and tracking their verifiable costs requested by TPTF. | 0 | TBD | The VCMS will satisfy ERCOT’s needs for managing (submission, receipt, storage, and tracking) VC submissions and their related documentation. Reduce manual efforts for processing and monitoring verifiable cost.
ERCOT | MO | MO |  | Nodal.ercot.com Retirement | New | Defer |  | 2 - High |  | $250k-$500k | $1M-$2M | Migration of content from nodal.ercot.com website to ERCOT.com website; retirement of nodal.ercot.com website. | 0 | TBD | Anticipated efficiencies from maintaining a single repository system.
Market | COPS | MO |  | Enhancements to API for Disputes | New | Defer |  | 2 - High |  | $500k-$1M | $1M-$2M | MPs (from COPs) have requested that ERCOT enhance an API to programmatically submit disputes. The API would interface with Siebel and would be created in the integration layer. | 0 | TBD | TBD
ERCOT | TPTF | MO |  | NPRRs and Mandates | New | Defer |  | 2 - High |  | $2M-$3M | $3M-$4M | Additional post-nodal efforts - not yet defined and not covered under stabilization or operating and Maintenance. | 0 | TBD | TBD
ERCOT | MO | MO |  | COMS Extract, Report & Web Services Monitoring & Usage Statistics | 80032_01 | CXL |  | 2 - High |  | $250k-$500k | $4M-$5M | Provide research capabilities for Commercial Operations extract, report and web services data for internal business users, which include monitoring functionality and usage analysis capabilities. | 0 | TBD | Will create an infrastructure to allow access to broader information from ERCOT systems to our customers; Utilizing the standard EIS Business Intelligence layer, this offering will work to align our reporting capabilities and help to eliminate future fragmented solutions; Removal of manual processes and their inherent risks of dependency on skilled resources; Information security is guaranteed via automation methods; Information may be accessible in ways not currently available. Uses will have abilities to access and format data as needed, without the need of development resources
[8 empty] | 2009 Forecast: |  | $500k-1M