## 2009 RO Recommendations
RO 2009 Project Prioritization - PUCT, Market and ERCOT Projects
Source | Committee | Prog Area | Source Doc | Project | Project No. | Current Status | 2009 Priority | 2009 Rank | 2009 Budget Range | 2009 Running Range | Summary Description | NET Benefit | Benefit Summary
Market | RMS | RO | SCR749 | MarkeTrak Enhancements (Workflow & Reporting) | 70007_01 | Planning | 0 - Previously Approved | 0.1 | <$100k | <$100k | Carry Over Enhancements to the functionality of MarkeTrak as defined in SCR749 | 740000 | Provide efficiencies for submitting and resolution of registration disputes for Market Participants and ERCOT.
Market | RMS | RO/MO | HS3693 PUCT 34890 | Small Renewables/Distributed Generation - RMWG | 80028_01 | Execution | 0 - Previously Approved | 0.2 | <$25K | $100k-$250k | Carry Over - This project recognizes any retail transaction or settlement-type effort needed for the distributed generation/small renewables project. | TBD | TBD prior to Market Initiation
Market | RMS | RO | PUCT 34610 | Advanced Metering -Interim Solution for Settlement | 80027_01 | Execution | 0 - Previously Approved | 0.3 | $250k-$500k | $250k-$500k | Carry Over - This project to address any MKT changes resulting from Advanced Matering | TBD | TBD prior to Market Initiation
ERCOT | RO | RO |  | Data Research and Reporting (formerly ETS Transition to EDW) | 50088_01 | Planning | 0 - Previously Approved | 0.4 | $250k-$500k | $500k-$1M | Carry Over - Transition of ESIID Transaction System Reporting to a | 1200000 | Reliability - utilizing the standard EIS Business Intelligence layer, this offering will work to align our reporting capabilities and help to eliminate future fragmented solutions. Data Management - Timely report delivery. Data Management - Reliable and accurate reports. Data Management - Timely exception identification. Flexibility - Information may be accessible in ways not currently available. Users will have ability to access and format data as needed, without the need of development resources. Standard integration - Integrates with Enterprise information delivery strategic initiatives. Maintenance Costs - Maintenance of database servers - could move to an existing machine. Partition strategy. Performance of reporting. Real-time reporting instead of batch . .
ERCOT | RO | RO |  | TIBCO Siebel Integration | 80040_01 | Planning | 0-Previously Approved | 0.5 | $250k-$500k | $500k-$1M | Carry Over - This projects implements integration best practices recommended by Oracle in effort to fix partial service orders created in Siebel Customer Registration System. | 290000 | Reduced operational cost and effort for research and recovery of transactions. Improved accuracy and timeliness of transaction processing
ERCOT | RO | RO |  | EDW EAI Transition (inc. PaperFree & NAESB) | 50061_01 | On Hold | 0 - Previously Approved | 0.6 | $100k-$250k | $500k-$1M | Transition of EAI reporting from Data Archive to Enterprise Data Warehouse | 700000 | Reliability - Utilizing the standard EIS Business Intelligence layer, this offering will work to align our reporting capabilities and help to eliminate future fragmented solutions. Automation - Removal of manual processes and their inherent risks of dependency of skilled resources. Security - Information security is guaranteed via automation methods. Flexibility - Information may be accessible in ways not currently available. Users will have ability to access and format data as needed, without the need of development resources. Standard Integration - Integrates with Enterprise information delivery strategic initiatives
ABOVE THIS LINE --Projects expected to carry over from 2008
ERCOT/Market | RMS | RO/MO |  | Advance Metering Infrastructure (ERCOT Changes) | New | Not started | 1 - Critical | 1 | $1M | $1M-2M | This project will begin implementation of the approved Conceptual Design delivered as part of the 70057_01 for an entire ERCOT system change to support PUCT 34610. This project has the potential to be a phased approach across multiple years. | TBD | TBD pending direction for PUCT 34610
ERCOT | RO | RO |  | MarkeTrak Phase 3 | 80030_01 | Not started | 2 - High | 2 | $100k-$250k | $2M-3M | ERCOT requested project to expand capabilities and efficiencies of the MarkeTrak Retail Issue Resolution System that are not currently part of MarkeTrak Phase 2. | 80000 | Implement Mass Update; Automate DEV LSE Siebel changes in MarkeTrak; Add MP ability to produce market wide metrics on issues without the ability to view issue details; Automate retrieval of relevant retial information from ERCOT systems to MarkeTrak for expedidition of issue resolution; Automate generation of ERCOT Initiated Issues for Siebel Exceptions; Upgrade Serena Team Track Application; Increase reporting metrics related to MarkeTrak SLA; Increase efficiencies of Workflows and Application Adapters
ERCOT | RO | RO |  | Retail Application Upgrades | 80031_01 | Not started | 2 - High | 3 | $1M | $2M-3M | Non point upgrades, would require configuration for additional enhancements. This project is necessary to allow ERCOT to plan and implement upgrades to systems not currently within another project on the PPL to maintain compliance. In addition, the impact analysis done during planning would provide risk management of other projects/releases. | TBD | TBD - Dependent on complaince and upgrades required at time of project initation: currently Oracle, Paperfree and Siebel Upgrades anticipated
ERCOT | RO | RO |  | EDW EAI Transition (inc. PaperFree & NAESB) | 50061_02 | Not started | 2 - High | 4 | $100k-$250k | $2M-3M | This project will configure the 997 and Load Loss reports to pull from the NAESB/PFREE ODS rather than the source database. | 856900.2309 | Utilizing the standard EIS Business Intelligence layer, this offering will work to align our reporting capabilities and help to eliminate future fragmented solutions; Removal of manual processes and their inherent risks of dependency on skilled resources; Information security is guaranteed via automation methods; Information may be accessible in ways not currently available. Uses will have abilities to access and format data as needed, without the need of development resources; Integrates with Enterprise information delivery strategic initiatives
ABOVE THIS LINE --Recommended for 2009; Projects below this line unfunded for 2009
ERCOT | RMS | RO |  | TML Transition to MIS | New | Not started | 2 - High |  | $250k-$500k |  | Migration from TML to MIS of functions that support the Retail market and/or Zonal-related reporting that will continue past Nodal Go-Live. The item is not included in the approved MIS requirements. Both the Retail Market Subcommittee and ERCOT business reps have requested holding off on this effort for at least 6 months after Nodal Go-live | TBD | TBD - Anticipated benefit is to increase efficiencies by consolidating to a single system-MIS and decommission of old portal.
ERCOT | RO | RO |  | Exception Reporting / Monitoring Enhancements | 70008_01 | Below Line | 9 - Parking Lot |  | $500k-$750k |  | Automate current exception reporting to monitor protocol compliance for processing exceptions. Create new exception reports using new data available from RBP and/or EDW projects. |  | Exception reporting in Retail Customer Choice has been very manual. There are protocol requirements that may not be met due to the lack of logging after the processing occurs.
ERCOT | RO | RO |  | Systematic Exception Reprocessing Functionality | 70009_01 | Below Line | 9 - Parking Lot |  | $250k-$500k |  | Automate current exception processing to meet protocol. Create reporting features after processing occurs. |  | Exception processing in Retail Customer Choice has been very manual. There are protocol requirements that may not be met due to the manual efforts.
ERCOT | RO | RO |  | EDI Transaction logging | 60062_01 | Below Line | 9 - Parking Lot |  | $100k-$250k |  | Change the Paper Free application system to log all ANSI records to TRLOG and to log all TXSET records to a new table which will better support current and future business needs. |  | Improve performance and accessibility of data. The suggested changes in the logging details will allow users to access the data without needing a cross-reference sheet telling them what the columns are in TRLOG and what data (per transaction type) is be
ERCOT | RO | RO |  | 814 inbound XML rewrite (impacts input from portal only) | 60043_01 | Below Line | 9 - Parking Lot |  | $100k-$250k |  | Re-Write of Inbound 814 XML maps to Increase Efficiency, Reliability and Stability of ERCOT transaction data processing. |  | Our experience with splitting the inbound 814 X12 maps has shown that reducing the complexity of the map (by implementing clean flowing logic) can reap significant performance gains. The time to analyze and correct any logic errors has been decreased by
ERCOT | RO | RO |  | Commercial Apps - Calendar Consolidation | 60033_01 | Below Line | 9 - Parking Lot |  | $250k-$500k |  | Develop single business calendar for use by all retail applications |  | Reduced rework for both market and ERCOT by eliminating possibility of out of sync conditions between multiple business calendars (50 hours per year of data repair activity for CRs and TDSPs)
ERCOT | RO | RO |  | Name to DUNS conversion | 60059_01 | Below Line | 9 - Parking Lot |  | $100k-$250k |  | Change the Paper Free application system to utilize DUNS numbers as opposed to Market Participant company names. |  | Consistent naming standards within Paperfree system.
ERCOT | RO | RO |  | MP configuration Table | 60060_01 | Below Line | 9 - Parking Lot |  | $100k-$250k |  | Remove all of the MPDB.conf files in the MB/PF systems and consolidate all of the configurations into a single table. The complexity of adding new MP to the system must be reduced in order to remove the number of errors that are encountered when adding / |  | The complexity of adding new MP to the system must be reduced in order to remove the number of errors that are encountered when adding / modifying MP information.
ERCOT | RO | RO |  | Enrollment Postcard Notification Process | 80029_01 | Below Line | 9 - Parking Lot |  | $100k-$250k |  | This is an enhancement to the method for generating Enrollment Postcard Notification and Customer Objection files processing within ERCOT (starting at the point of receiving file from vendor; stopping at the point of vendor pickup). | -100000 | Improved production support (including creation of a Service Level Agreement); Improved exception handling; Education of new team members; Improve Testing capabilities
2009 Funding Forecast: $2M-$3M