|  | Texas Nodal Market Implementation Program Status Report Week Ending Oct. 3, 2008 |
| --- | --- |
| CONTENTS |  |

PROGRAM STATUS	1

CORE NODAL PROJECTS	3

Network Model Management System (NMMS)	3

Energy Management System (EMS)	5

Market Management System (MMS)	7

Outage Scheduler	10

Congestion Revenue Rights (CRR)	12

Commercial Systems (COMS)	13

Early Delivery Systems (EDS)	16

SUPPORTING NODAL PROJECTS	17

Enterprise Integration and Integrated Testing Projects (EIP and INT)	17

OTHER PROGRAM UPDATES	23

Readiness and Transition	23

APPENDIX	25

Health Indicator Measures	25

| # PROGRAM STATUS |  |
| --- | --- |
| Health Indicators |  |
| Overall; Red; Resources; Amber. Schedule; Red; Risks; Amber. Budget; Red; Issues; Amber. Scope; Amber; QC; Red. |
| Highlights |  |
| All tasks on the critical path completed on schedule NMMS conducted multi-vendor meeting and agreed to “frozen” schema changes Integrated Testing project (INT) has begun testing Integrated Release 2.0 (IR 2.0) in the integrated testing (i-Test) environment. IR 2.0 includes components from the Market Management System (MMS) and key upstream systems, as well as some of the required interfaces. INT’s testing strategy is to begin with MMS as the core system, and build out the interfaces from there EMS scheduled to complete CIM Importer Pre-FAT on Oct. 10 and begin FAT on Oct. 13 Continue to improve processes – as an example we were able to reduce the time to build and smoke test MMS4 Patch 4 from 10 days to 4 days Nodal budget – progressing as planned; presentation to Board is TBD Staffing – continue to increase participation of ERCOT staff while trending down with contractors |  |
| Milestones Planned for Next 30 Days |  |
| See milestone chart |  |
| Activities Behind Schedule |  |
| No program critical path activities are behind schedule this week |  |
| Risks or Issues |  |
| Description | Status |
| NMMS data collection and validation efforts within the timeframes | Assigned a RARF lead (Scott Middleton) and added a QA lead to the team (Dave Carty); adding more data validation and business rules; included additional time in schedule to allow for delays |
| Traceability between protocols and requirements is largely manual; not all requirements documentation has been updated to reflect NPRR changes and re-approved by TPTF | Requirements audit in process to review all project requirements documentation, approvals, and incorporation of NPRRs |
| Current schedule does not include time for additional NPRRs beyond the ones incorporated; there is a high probability that we will have additional NPRRs and change requests | Executives will need to determine the amount of additional time and budget to include; NPRRs will go to the Board for approval |
| As functionality is delivered and business owners review and test, there are changes needed. The extent of this is not fully known and is causing more rework than expected | Reviewing requirements documentation as well as reviewing business processes with project teams and business owners to identify problem areas; schedule includes time for these activities |

# CORE NODAL PROJECTS

| ## Network Model Management System (NMMS) |  |
| --- | --- |
| Health Indicators |  |
| Overall; Red; Resources; Amber. Schedule; Red; Risks; Green. Budget; Red; Issues; Green. Scope; Amber; QC; Amber. |
| Highlights |  |
| Conducted multi-vendor meeting and agreed to “frozen” schema changes Distributed all RARF Audit Reports - Current RARF Production Quality level: ~93% Completed installation of NMMS 5 |  |
| Milestones Planned for Next 30 Days |  |
| Support data requirements for AREVA CIM Importer pre-FAT Finalize schema version 1.21 |  |
| Activities Behind Schedule |  |
| No activities behind schedule |  |
| Top 3-5 Risks or Issues |  |
| Description | Status |
| Topology Processor performance | Working with Siemens to identify configuration differences |
| Need to perform data assessment | Requested Dave Carty to develop methodology and may potentially need an additional resource to assist with implementation |

| Remaining Software Releases (Siemens) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Release Number | Description | FAT Start |  | FAT Complete |  |
|  |  | Sched | Actual | Sched | Actual |
| NMMS 5 | Production Model to support business processes Auto Model Scheduler integration MIS posting folder structure Historical models and historical NOMCR tracking PTC screens to support PMCR linkage Canned reports (8) | Oct 06 08 |  |  |  |
| NMMS 6 | PTC screens and functionality for Model Coordinator screens Outage clarification Name service redesign As Built report | Jan 07 09 |  |  |  |
| NMMS 7 | Auto Model Scheduler validation |  |  |  |  |

| ## Energy Management System (EMS) |  |
| --- | --- |
| Health Indicators |  |
| Overall; Red; Resources; Green. Schedule; Red; Risks; Amber. Budget; Red; Issues; Amber. Scope; Amber; QC; Amber. |
| Highlights |  |
| Continued the unstructured CIM Importer Pre-FAT and retest of variances with no new High or Critical issues Set the benchmarks for AREVA to complete OE FAT based on the completion plan provided by them Continued the verification of Real Power OE results for a higher number of contingencies in consultation with business Technical review of OE controls with AREVA to verify Reactive Power solution Resolved the issue of remaining MTLF deliverable/SPRs with AREVA Completed the deliverables in response to Requirements Manager audit |  |
| Milestones Planned for Next 30 Days |  |
| Oct. 10 – Complete CIM Importer Pre-FAT Oct. 13 – Start EMS CIM Importer FAT Oct. 17 – EMS Release 5.1.5.x (EMS 5 OE/VSS) |  |
| Activities Behind Schedule |  |
| OE/VSS FAT affecting EMS Release 5.1.5.x. ERCOT has two technical SMEs helping test and resolve open issues. Currently a delay of 3 weeks from August 2008 schedule. Not a critical path task. EMS Release 5.1.6.x (Habitat 5.7). Low priority tasks since we have the beta version in operation. We will release when a release window opens up. Not a critical path task. |  |
| Top 3-5 Risks or Issues |  |
| Description | Status |
| OE/VSS FAT Completion | AREVA required to provide reactive power demo by 10/03 followed by ERCOT’s on site testing at AREVA 10/06-10/09 |
| Late discovery of unexpected interface issue with external programs | Mitigate by early testing. Planning to set up intra-program development system interface testing ahead of i-Test |
| Confirmation that the EMS system processors have sufficient power to run all applications simultaneously in a timely manner | Schedule an early EMS study applications performance test to validate if an issue exists |
| Scope - Pending NPRRs, SIG papers and CCB requests These include: PUN, DC Tie rework, CRR map display, EPS meter, Max shadow price, Flow gate, Time to ICCP, PSE case delivery, NPRR 102 reports and future NPRRs | These contribute to potential changes in scope |
| Delay of Habitat 5.7 upgrade | This activity had to be delayed by 3 weeks to ensure OE/VSS release is consistent with the current version of Habitat. Low priority task. Not a critical path item and will be worked in during FAT when time is available |

| Remaining Software Releases (AREVA/ERCOT) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Release Number | Description | FAT Start |  | FAT Complete |  |
|  |  | Sched | Actual | Sched | Actual |
| 5.1.5.x | Outage Evaluation functionality permits the Outage Scheduler to evaluate the impact of a requested outage Voltage support function permits the operators to address voltages issues and recommend corrective action Interfaces to MMS, CSI, EDW and CDR | July 29 08 | July 29 08 | Oct 17 08 |  |
| 5.1.6.x | Habitat 5.7 upgrade | Oct 20 08 |  | Nov 07 08 |  |
| 5.1.7.x | EMS CIM XML importer which receives data, model and configuration changes from the central master data source (NMMS) and updates the EMS applications databases | Oct 13 08 |  | Nov 17 08 |  |
| 5.1.8.x | Interfaces to down stream systems to support long-term storage and the posting of Section 8 reports | Nov 03 08 |  | Jan 13 09 |  |

| ## Market Management System (MMS) |  |
| --- | --- |
| Health Indicators |  |
| Overall; Red; Resources; Amber. Schedule; Red; Risks; Amber. Budget; Red; Issues; Amber. Scope; Amber; QC; Amber. |
| Highlights |  |
| MMS4 patch 3 FAT testing complete Started MMS4 patch 4 movement from MMS DEV to MMS FAT MMS4 patch 5 received from ABB and loading into MMS DEV started Completed review and feedback on CIM schema and CIM XML (via NMMS facilitated meeting with NMMS, EMS and MMS) Completed 3 MI-related internally developed activities Awards requirement document complete Notices requirement document complete Verbal Dispatch Instructions requirement document complete Bids and offers front-end development in progress Resource Specific Submissions front-end development in progress |  |
| Milestones Planned for Next 30 Days |  |
| Oct. 14 – Present real time process to TPTF Oct. 17 – Complete DAM operating procedure Oct. 17 – Complete UI requirements and business rules Oct. 28 – Complete MMS4 patch 4 testing in MMS FAT environment Oct. 28 – Complete MMS4 patch 5 testing in MMS Dev environment Oct. 30 – Complete bids and offers development Oct. 31 – Complete RUC operating procedure |  |
| Activities Behind Schedule |  |
| No activities behind schedule |  |
| Top 3-5 Risks or Issues |  |
| Description | Status |
| NEW ISSUE: Additional patch(es) will need to be added to the MMS4 schedule due to the delay in the start of MMS5 (dependent on a validated and synchronized CIM XML file based on v1.21 of the CIM schema) | Will work with the MMS team and ABB to determine when the patch(es) can/should be scheduled; will update the MMS schedule and notify all Nodal PMs once the patch(es) are added. |
| EXISTING ISSUE: Lost 1 DBA, 3 SMEs and 2 analysts within a two month time period | Leveraging additional internal resources to fill DBA and SME gaps; in the process of filling one analyst position |

| Remaining MMS Software Releases (ABB delivered) |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Release Number | Description |  | FAT Start |  |  | FAT Complete |  |
|  |  |  | Sched | Actual |  | Sched | Actual |
| MMS4 P3 | - Self-committed resources in DAM; resource parameters API - Load Resource modeling (SIG005); PUN modeling (SIG002); Non-Modeled generation modeling (SIG008); BLT modeling (SIG007); Partial implementation of combined cycle configuration modeling mapping of configuration to Primary/Alternate Physical generators (SIG paper) - Combined Cycle logical resource nodes (ERCOT action) - Verification of monitor/enforced flag for all branches in CIM schema (mandatory requirement) - 120+ bug fixes |  | Jul 28 08 | Jul 28 08 |  | Sep 29 08 | Sep 29 08 |
| MMS4 P4 | - Partial implementation of NPRR102, NPRR128 and JBOSS upgrade - Bug fixes |  | Aug 31 08 | Aug 27 08 |  | Oct 28 08 |  |
| MMS4 P5 | - Delivery added to ensure progress is made while waiting for validated and synchronized CIM XML file from NMMS - S&B defects, interface updates and additional workflow development and testing based on the most recent CIM schema and corresponding CIM XML test data set |  | Sep 30 08 | Sep 30 08 |  | Nov 25 08 |  |
| MMS4 P6 | - Content is being discussed with vendor |  | Dec 08 08 |  |  | Jan 02 09 |  |
| MMS4 P7 | - Last scheduled release to MMS4; Content is being discussed with vendor |  | Jan 26 09 |  |  | Feb 13 09 |  |
| MMS5 | - Last scheduled release of functionality, target delivery to ERCOT is TBD; triggered off an NMMS-delivered validated and synchronized CIM XML file ready for consumption by downstream systems - CIM XML import processing and end-to-end testing - Bug fixes - Remaining NPRR as approved (e.g., NPRR102, NPRR113), SIG paper changes (e.g., rounding) and software implementation changes based on testing (e.g., performance improvements, startup cost eligibility, SASM constraint modeling) |  |  |  |  |  |  |
| Remaining MMS “Market Manager” UI (MMS MM UI) Software Releases (ERCOT delivered) |  |  |  |  |  |  |  |
| Release Number |  | Description | FAT Start |  | FAT Complete |  |  |
|  |  |  | Sched | Actual | Sched |  | Actual |
| MMS MM UI |  | Bids and offers FAT | Nov 04 08 |  | Nov 17 08 |  |  |
| MMS MM UI |  | Resource specific submissions FAT | Nov 25 08 |  | Dec 10 08 |  |  |
| MMS MM UI |  | Schedules FAT | Dec 03 08 |  | Dec 16 08 |  |  |
| MMS MM UI |  | Self-arranged AS FAT | Dec 17 08 |  | Jan 12 09 |  |  |
| MMS MM UI |  | Trades FAT | Jan 07 09 |  | Jan 20 09 |  |  |
| MMS MM UI |  | Awards FAT | Jan 15 09 |  | Jan 28 09 |  |  |
| MMS MM UI |  | Notices FAT | Feb 20 09 |  | Feb 13 09 |  |  |
| MMS MM UI |  | Verbal dispatch instructions (VDI) FAT | Feb 16 09 |  |  |  |  |

| ## Outage Scheduler |  |
| --- | --- |
| Health Indicators |  |
| Overall; Red; Resources; Amber. Schedule; Red; Risks; Amber. Budget; Red; Issues; Amber. Scope; Green; QC; Red. |
| Highlights |  |
| FAT/regression test continues (52% complete overall, 70% pass rating, 0 Sev. 1’s, 19 Sev. 2’s) Data Conversion Test and Validate complete (Sept. 30) SPR list submitted to ABB, with priority (Oct. 3). |  |
| Milestones Planned for Next 30 Days |  |
| Oct. 24 - Opportunity Outage release to FAT Oct. 30 - Sync registration and equipment list with MMS Nov. 04 - OS Release 2.0.13.0 “Ready for Integration (i-Test)”. |  |
| Activities Behind Schedule |  |
| OS full regression test taking longer than originally planned due to application service failures and inconsistent results. ABB on-site and addressing known issues. OS application appears to be stabilizing. This activity is not on the program critical path and is still expected to complete by Nov. 4 |  |
| Top 3-5 Risks or Issues |  |
| Description | Status |
| Core OS | Market is issuing request to allow RE/QSE to submit outages against transmission equipment they own. This requires a fundamental redesign of the OS application. A SCR request is forthcoming. |

| Remaining Software Releases (ABB/Internal) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Release Number | Description | FAT Start |  | FAT Complete |  |
|  |  | Sched | Actual | Sched | Actual |
| 2.0.13.0 | Full FAT regression test of Outage Scheduler | Aug 08 08 | Aug 05 08 | Nov 04 08 |  |
|  | Regression Correction (ABB) | Nov 04 08 |  | Nov 19 08 |  |
| 2.0.14.0 | FAT Correction | Nov 19 08 |  | Jan 07 09 |  |
| OS User Interface |  |  |  |  |  |
|  | Base UI Testing | Nov 04 08 |  | Dec 04 08 |  |
|  | Opportunity Outage | Dec 04 08 |  | Jan 28 09 |  |
|  | OS Feature Pack 1 - Warnings | Dec 04 08 |  | Jan 28 09 |  |
|  | OS Feature Pack 2 - Summary Enhancements - Copy/Print/Export - Split Screen - Client-side Validation | Feb 06 09 |  | Feb 27 09 |  |

| ## Congestion Revenue Rights (CRR) |  |
| --- | --- |
| Health Indicators |  |
| Overall; Red; Resources; Green. Schedule; Red; Risks; Green. Budget; Red; Issues; Green. Scope; Amber; QC; Amber. |
| Highlights |  |
| Configured LPARs (3) plus VIO Server on new p550 box at Nexant Herakles site Provided instructions for delivering schema extract to EIP project Completed and returned Requirements artifacts to the Requirements Manager Performed and completed FAT testing for Nexant Release 1.06 (CRR4), including identification of 2 new defects Actively resolving issues related to integrated business processes w/ Credit and Settlements |  |
| Milestones Planned for Next 30 Days |  |
| Oct. 2 – Complete CRR 4 Functionality Testing and Defect Resolution Oct. 8 – Receive patch from Nexant for issues found in Release1.06 FAT testing. Oct. 20 – Obtain CRR4 (at ERCOT) sign-off Oct. 20 – Prepare CRR4 installation into i-Test Oct. 22 – Present revisions to TCR to CRR Transition plan to WMS for review Oct. 27 – Present revisions to TCR to CRR Transition plan to TPTF for review |  |
| Activities Behind Schedule |  |
| No activities behind schedule |  |
| Top 3-5 Risks or Issues |  |
| Description | Status |
| NA |  |

| Remaining Software Releases (Nexant) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Release Number | Description | FAT Start |  | FAT Complete |  |
|  |  | Sched | Actual | Sched | Actual |
| 1.06 | CRR AH Name Change functionality | Sep 26 08 | Sep 26 08 | Oct 3 08 | Oct 3 08 |
| TBD | Patch for identified defects in release 1.06 | Oct 8 08 |  |  |  |

| ## Commercial Systems (COMS) |  |
| --- | --- |
| Health Indicators |  |
| Overall; Red; Resources; Amber. Schedule; Red; Risks; Amber. Budget; Red; Issues; Amber. Scope; Amber; QC; Amber. |
| Highlights |  |
| S&B Lodestar 4.7 Upgrade - Migration to Zonal Production Sept. 27 - Deployed Framework and Metadata for Nodal DAM FAT 100% Complete RTM FAT 50% Complete Invoices FAT 50% Complete Refined timeline for implementing workaround for Lodestar product memory issue CSI Complete Release 5.4 (S&B Billing determinants) and development of Lisa test scripts Complete Release 6.1 (CMM Determinants) and development of Lisa smoke test scripts Registration Registration migration to I-test containing resolution to 14 defects (5160,3362,6768,6758,6774,6800,6783,6789,6790,6811,6715,6706,5175,4752) EIP migration to i-Test containing 3 defects for Registration S&B testing (6805,6742,6772) Registration application RARF data bulk upload files from business validation in progress. 9 issues found to date. Working with business on resolutions Create detail for Market certification of Disputes API test scripts |  |
| Milestones Planned for Next 30 Days |  |
| S&B New items which need to be added to schedule (i.e. Drop of code to nTest) CSI S&B Nov. 10 : Release 5.4 business/product testing complete Nov. 24: Release 6.1 business/product testing complete Nov. 24: Release 5.5 CSI Code Base complete CSI CMM Nov. 24: CMM Release 6.3 Code Base complete Registration and Disputes Dec. 5: FAT and Integration Testing in progress in i-Test for Registration and Disputes – 30.25% complete. Expected to be completed Financial Transfer Deploy FT to FAT Test environment (80%) Create internal roles for Finance (FTGUI users) using JBoss Plugin MMCR document submitted to release management Train Finance on GUI |  |
| Activities Behind Schedule |  |
| CSI Release 5.5 (NMMS > S&B, Remaining Determinants, and bug fixes) – Development start delay due to additional time needed for business verification of CSI Release 5.4 (MMS4, Billing Determinants, etc.). No impact to planned Integration Releases or critical path Disputes API Integration delivery to i-Test delayed due Integration rework necessary for Zonal/Nodal cross impacts. Impact: Siebel Phase 5 has been added to Integration Release 4 (scheduled to i-Test release for Jan. 09). No impact to critical path Final test scripts approvals - Working with business on completion. Approved tests begin executed in parallel. |  |
| Top 3-5 Risks or Issues For COMS |  |
| Description | Status |
| S/B - Lodestar v4.7 memory issue | Workaround has been identified and coding has been completed. Additional time added to COMS schedule for regression testing of Data Aggregation. Expect to migrate to i-Test week of 10/13/2008 |
| Data synchronization for integrated testing | Working with INT and Business teams to discuss business objectives for executing IR3.0 and assess data synchronization approach necessary to flush out all scenarios |
| NPRRs and Change Controls | Additional NPRRs and Change controls will add time and possible costs to the COMS schedule. These are being carefully evaluated through the COMS team and the Nodal CCB |

| Remaining Software Releases (Internal) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Release Number | Description | i-Test Start |  | i-Test Complete |  |
|  |  | Sched | Actual | Sched | Actual |
|  | - Siebel 4.x (current 4.1.18.6) | Aug 27 08 | Aug 27 08 | Dec 06 08 |  |
|  | - EIP - REG-S&B-MPAdapter 0.2.0.x - REG-S&B Adapter 0.4.0.x - Registration Adapter 0.4.1.x - Framework (Common) Services 0.3.0.x - Lodestar 0.2.0.x - SmartMapper Adapter 0.5.0.x * Defect patches to I-Test scheduled weekly | Aug 27 08 | Sep 18 08 | Dec 06 08 |  |
|  | - Registration / disputes integration testing begins (Siebel to Lodestar / RE&JOU bulk data load / etc) | Sep 22 08 | Sep 22 08 |  |  |
|  | - Registration Phase 4 / Disputes Phase 2 testing end | Dec 05 08 |  |  |  |
|  | - Production planning | Dec 04 08 |  |  |  |
|  | - Production migration | Dec 13 08 |  |  |  |
|  | - 12/14/Production verification | Dec 14 08 |  |  |  |
| **Reg5/Disp3 | - Refactoring complete | Jan 16 09 |  |  |  |

** Registration Phase 5 scope has not been defined at this time but will include integration data / system corrections. The scope will also deliver Disputes Phase 3 which is the remaining Dispute API integration delivery

| ## Early Delivery Systems (EDS) |  |
| --- | --- |
| Health Indicators |  |
| Overall; Red; Resources; Amber. Schedule; Red; Risks; Amber. Budget; Red; Issues; Amber. Scope; Amber; QC; NA. |
| Highlights |  |
| EDS market engagement has continued to be successful in improving telemetry quality and State Estimator convergence. - Previous group of Focused Input Tests (FIT) improved State Estimator to 96.8% (TAC approved criteria is 97%). - Next group of FIT testing to begin Oct. 21, 2008 - Updated telemetry statistics to be provided in Oct. 10, 2008 status report (previous statistics provided below). 30% of wind generation resources (WGRs) sending valid MET data vs. 7% in August. Expect to be at 100% by Oct. 31. QSE ICCP Point Issues – Status Points: 37 (vs. 91 last month), Analog: 65 (vs. 71 last month), Ownership disputes: 75 (vs. 170 last month) TSP ICCP Issues – Status Points: 545 (vs. 1,208 last month), Analog: 407 (vs. 986 last month), Ownership disputes: 0 (vs. 274 last month) Unobservable buses with Load: 41 out of ~5000. |  |
| Milestones Planned for Next 30 Days |  |
| Project Schedule Item: Focused Input Test (FIT) Testing Cycle 1 is on schedule to begin October 21, 2008 FIT Market Webex on Oct. 7, 2008 (FIT for Oct. 21, 2008 – Jan. 23, 2009) Publish results on EM09 – zonal vs. nodal constraints Publish results on EM04 and EM05 – SCED stability and quality |  |
| Activities Behind Schedule |  |
| No current activities behind schedule that potentially impact the critical path of the new schedule. Telemetry and State Estimator activities below being worked in coordination with ongoing FIT testing: - Resolution of unobservable buses - Meeting TAC-approved State Estimator criteria - Status of meteorological telemetry data to support AWS TrueWind forecasting |  |
| Top 3-5 Risks or Issues |  |
| Description | Status |
| Inability to keep MPs engaged in FIT after integrated master schedule is released | Conducting Webex to outline test objective schedule, conducting weekly calls |
| Time lapse between completion of R5.1 (SCED submissions), 6.2 (QSE by QSE LFC testing), R9.1 (DAM Submissions), and 9.2 (OS Submissions) and re-starting EDS will require these efforts to be redone to re-prime the market systems and personnel that have been suspended from DAM/RUC testing since May 30, 2008. | Add required re-work to integrated master schedule and EDS estimate, and remove only if TPTF provides feedback that it’s not needed. |
| Securing proper resource levels for EDS activities. | Initial round of resource meetings in process to improve staffing resource expectations and transitions to EDS. |

# SUPPORTING NODAL PROJECTS

| ## Enterprise Integration and Integrated Testing Projects (EIP and INT) |  |
| --- | --- |
| Health Indicators |  |
| Overall; Red; Resources; Amber. Schedule; Red; Risks; Red. Budget; Red; Issues; Red. Scope; Amber; QC; Red. |
| Highlights |  |
| Overall: Integrated Releases (IR/“Bucket List”) and interface priorities list is changing. Minor changes from Core Projects are still being received. IR 2 testing is progressing on schedule; expected to exit on schedule IR 3 planning is being finalized. IR3 testing expected to start on schedule; interface re-work is already in progress. IR 4 planning is underway. Minor interface rework is already in progress. Integrated Release 2 EIP Deliveries to i-Test - COMPLETE Core Projects Deliveries to i-Test -- COMPLETE Supporting Projects Deliveries to i-Test (EDW and CDR) -- COMPLETE Integration Testing Execution: CDR testing BEHIND SCHEDULE, expected to recover and complete on time. Integrated Release 3 EIP Deliveries to i-Test – ON SCHEDULE Core Projects Deliveries to i-Test (EMS and Siebel P4): -- BEHIND SCHEDULE Supporting Projects Deliveries to i-Test - EDW, CDR, CSI Infrastructure, EMS to OS Integration – ON SCHEDULE - MPIM Integration – AT RISK – due to environment issues. - EMS <--> MMS Integration – DELAYED – dependent on common CIM model. Defer to Integrated Release 4. Integration Testing Preparation – BEHIND SCHEDULE Integrated Release 4 EIP Deliveries to i-Test – ON SCHEDULE |  |
| Milestones Planned for Next 30 Days |  |
| Integrated Release 2 EIP Milestones-- COMPLETE Integration Testing Release 2 Complete – ON SCHEDULE (Oct. 10) Integrated Release 3 EIP - Adapters for R3 -- ON SCHEDULE (Schedule revisions are needed to accommodate Bucket List changes.) Integration Release 3 Test Planning -- BEHIND SCHEDULE |  |
| Activities Behind Schedule |  |
| Integrated Release 2 Integration Testing Execution – behind schedule due to environment and software stability issues that took a few weeks to fix; currently 4 defects remain (3 Sev 3, 1 Sev 4) which meet the exit criteria - CDR -- 60 Reports: 4 new, 56 regression Integrated Release 3 Integration Testing Preparation – behind schedule due to changes in priorities coming out of the Nodal Integrated Program Schedule and resource constraints. Mitigation: have moved additional resources over to help in the short term. This should not affect other testing preparation efforts. Planned to be complete to meet testing execution schedule - Integration Test Scenarios - Integration Test Scripts - Environment, Resources, and Data Setup |  |
| Top 3-5 Risks or Issues |  |
| Description | Status |
| Risk that Integration Release Definition/Bucket List continues to change. Impact: Integration Testing Planning, Preparation and Execution are delayed | Working with PMO to align with Integrated Program Schedule. Reviews and meetings continue to refine the list. |
| Risk that disputes API may introduce zonal/nodal dependencies earlier than expected. Impact: Cannot test the overall system | All infrastructure and software dependencies identified and mapped out. Release of API into production moved to provide time for changes to be made |
| Risk of scope changes, particularly to include business processing within the integration layer Impact: Creates an unstable architecture and failure of whole system; | Monitoring all change requests for changes such as these and so far all of the business rule implementations have been mapped into the correct systems. Currently addressing rounding of decimal data where MMS should reject incorrectly submitted decimal data and not in the integration layer. |
| Risk that integration layer performance is inadequate. Impact: System fails to function as protocols require. | Regular performance and other non-functional observations being made within the integration layer. Introducing new chunking component to support heterogeneous and large payloads. Proofs of Concept produced to verify optimal implementation have been completed for message sizes |

| Remaining Integrated Software Releases (Internal) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Release Number | Description | i-Test Start |  | i-Test Complete |  |
|  |  | Sched | Actual | Sched | Actual |
| IR 2 | Primary objectives: Run MMS daily on stable dataset Base-line all Priority 1 interfaces | Aug 12 08 | Aug 12 08 | Oct 10 08 |  |
| IR 3 | Primary objectives: Run MMS daily with key upstream interfaces Initial MMS-L* testing | Oct 13 08 |  | Dec 01 09 |  |

Metrics

Web Services Usage - The following results provide counts of success and failure for all transactions - First chart indicates volume of successfully & unsuccessfully invoked services - 2nd & 3rd charts show the most frequent successful and unsuccessful processes. - Y scale is logarithmic, X scale shows all transaction types for two graphs Transactions volumes – 249k hits by 327 entities at 91% success rate T – successful invoked transactions F – unsuccessfully invoked transactions - Overall success rate is unchanged from previous periods, but last week reached a new high of 98% success - 12 new entities in the last month - Volumes have stabilized at around 1k hits per day - Substantial increase in error rates in weeks 35 & 37 that are attributable to a handful of MPs incorrectly forming getBidSet and getAwardedAS. Both of these transactions have been successfully submitted by other MPs 30 most frequent correctly invoked processes 30 most frequent incorrectly invoked processes 30 most frequent incorrectly invoked processes in last 2 weeks Design metric – 97% Nodal has 10 major end-point systems, 36 Interfaces, 57 major integration components and around 400 Information Flows Construction metric – 87% Deployed to Testing metric – 70%

# OTHER PROGRAM UPDATES

| ## Readiness and Transition |  |
| --- | --- |
| Overall; Red; Resources; Amber. Schedule; Red; Risks; Amber. Budget; Red; Issues; Amber. Scope; Amber; QC; NA. |
| Market Participant Readiness |  |
| Highlights New Metric – MP21 – Wind Generation Resources ICCP Telemetry – was approved by TAC. Tested release 6.6 of the Nodal Scorecard in the i-Test environment Completed 3 metrics documents and finalizing 5 others. Goals for Next 30 Days Oct. 6, 2008 - Implement new MP 21 changes in production scorecard (release 6.6) – In Progress October 10, 2008 - Complete final drafts for remaining metrics documents. Update Nodal Scorecard – ongoing every Wednesday |  |
| ERCOT Readiness |  |
| Highlights ERCOT Staffing is at 97%, only 12 Nodal positions remain open. ERCOT Procedures are 89% complete, count is 444. Of 49 ERCOT Departments - 27 are now reported as “Green”; 22 reported as “Amber” for training. Updated Training Plans with staff changes and provided updated department information to LMS. Goals for Next 30 Days Oct. 6-31, 2008 – Process follow up meetings. Oct. 10, 2008 – Approval on CaseWise procedures document |  |
| Activities Behind Schedule |  |
| Procedures and training are behind schedule for several departments primarily due to system delays but will be realigned once the integrated schedule is finalized. Procedures and training are not on critical path |  |
| Top 3-5 Risks or Issues |  |
| Description | Status |
| Risk: Processes may not be in-line with the systems designs | Mitigation: Processes are vetted with directors and managers who participate in the process. There is also clear ownership for each process. The processes will be reviewed with the nodal PMs, project SMEs and business owners. |
| Issue: Metrics are ill-defined and/or unclear on the steps to ensure success (quality) | Mitigation: Documentation is being created to define the ‘as-is’ process for determining the metrics inventory definition, ownership, procedures for measuring and obtaining results, survey procedure, communications scorecard user and administrative guides. Once baselined, an analysis of the metrics can determine appropriate next steps (interim milestones, revisions needed etc.) Status: The majority of documentation has been drafted and is under review. Three documents remain to be created. Target completion is Oct. 13. |
| Metrics |  |

# APPENDIX

| ## Health Indicator Measures |  |  |  |
| --- | --- | --- | --- |
| Metric | Green | Amber | Red |
| Overall | Both core indicators are green | At least one core indicator is amber, but none are red | At least one core indicator is red |
| Schedule | All activities on the critical path are complete, or are expected to be complete, on or ahead of the planned dates | No dates have been missed, but one or more critical path activities is forecasted to complete late | At least one critical path deliverable has missed its due date. Project implementation date is in jeopardy |
| Budget (hrs) | Project forecasted to complete within the baselined hours | Project forecasted to complete up to 5% over the baselined hours | Project forecasted to complete more than 5% over the baselined hours |
| Scope | All Requirements approved; no unplanned scope changes | Pending approvals for Requirements; no unplanned scope changes | Unapproved Requirements and/or unplanned scope changes |
| Resources | All key resource positions are filled and no schedule delays are expected. | One or two key positions are not staffed and the schedule may be adversely impacted. | More than two key positions are not staffed and the schedule will be impacted. |
| Risk | All project risks have a Risk Score =< 4 | At least one project risk has a Risk Score => 5 and =< 8 | At least one project risk has an Risk Score => 9 |
| Issues | All issues are being resolved by the required due dates | Some issues are remaining open past the required due dates but none are of “critical” priority (Impact = 3 or 4) | At least one “critical” priority issue (Impact = 3 or 4) is open past the due date |
| Quality Control | Defect metrics meet all of the following: # of Severity 1 = 0 # of Severity 2 = 0 Avg. #. Days to Close Sev 1 and Sev 2 Defects < 45 % Reopen Defects < 15 | Defect metrics meet at least one of the following: #. Severity 1 = 1 to 5 #. Severity 2 = 1 to 5 Avg. # Days to Close Sev 1 and Sev 2 Defects => 45 and =< 90 % Reopen => 15 and =< 24 | Defect metrics meet at least one of the following: #. Severity 1 > 5 #. Severity 2 > 5 Avg. # Days to Close Sev 1 and Sev 2 Defects >90 % Reopen >24 |