## Sheet1
NPRR # | Source | Approval Status | Baseline | Needed for Go-Live? | Short Description | Sponsor | Schedule Impact | Cost Impact | Integrated Schedule | EMS | MMS | OS | MOTE SOTE OTS | NMMS | COMS | CRR | EDW | EIP | IDA | INF | EDS IRT | MER Training | MIS | INT | MER CDR (formerly RTR) | MPIM | Legend
77 | NPRR | Approved | Post-Baseline2 | Yes | Incorporating the ERCOT Internal Audit Department and Other Clarifications (PRR735 companion) | ERCOT Staff | None | 0 | Y | [17 empty] | Light Green = Board approved
78 | NPRR | Approved | Post-Baseline2 | Yes | Simplifying the Dispute Process | SDAWG | None | Minor to be absorbed | Y | [17 empty] | Yellow = Ready for TAC and/or Board approval
80 | NPRR | Approved | Post-Baseline2 | Yes | Revised Wording of Protocol Section 3.1.5.1 (Electrical buses as consequentially outaged transmission elements.) | Center Point | None | 0 | Y | [17 empty] | Bright Green = Tabled at TAC waiting on Nodal Go-Live date
81 | NPRR | Approved | Post-Baseline2 | Yes | Automatic Voltage Regulator (AVR) Status | ERCOT Staff | None | <$50k | Y | [17 empty] | Tan = Tabled at PRS
82 | NPRR | Approved | Post-Baseline2 | Yes | Section 8, Performance Monitoring and Compliance, Revisions to Monitoring and Qualification Tests | TPTF | None | $50k-$100k | Y | [17 empty] | Orange = Reduction in scope
83 | NPRR | Approved | Post-Baseline2 | Yes | Remove Real-Time Energy Charge for a BLT from List of Real-Time Charge Types | ERCOT Staff | None | 0 | N/A | [17 empty] | Gray = post-implementation cost savings for ERCOT
84 | NPRR | Approved | Post-Baseline2 | Yes | Creating Amendment to Standard Form Market Participant Agreement | ERCOT Staff | None | 0 | N/A | [17 empty] | No shading = Pending at TPTF or PRS
85 | NPRR | Approved | Post-Baseline2 | Yes | Revision of Digital Certificate Procedures | ERCOT Staff | None | 0 | N/A
86 | NPRR | Approved | Post-Baseline2 | Yes | Settlement Clarifications to RUC Capacity Shortfall Ratio Share Formula | TPTF | None | 0 | Y
87 | NPRR | Approved | Post-Baseline2 | Yes | Market Monitor Terminology Change | ERCOT Staff | None | 0 | Y
88 | NPRR | Approved | Post-Baseline2 | Yes | Revision to 16.11.5, Monitoring of a Counter-Party’s Creditworthiness and Credit Exposure by ERCOT | Reliant | None | 0 | N/A
89 | NPRR | Approved | Post-Baseline2 | Yes | Changing Posting Requirement of Certain Documents from MIS Secure to Public Area | ERCOT Staff | None | 0 | Y
90 | NPRR | Approved | Post-Baseline2 | Yes | Corrections of FIP-FOP in Energy Offers | TPTF | None | <$50k | Y
91 | NPRR | Tabled by TAC waiting on Nodal Go-Live date | Post-Baseline2 | Yes | Scarcity Pricing and Mitigated Offer Cap During the Period Commencing on the Nodal Market Implementation Date and Continuing for a Total of 45 Days | TPTF | None | $50k-$100k | Y | 4 | 2 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 4 | 4 | 1
92 | NPRR | Approved | Post-Baseline2 | Yes | Remove Voltage Schedules Requirement | ERCOT Staff | None | 0 | Y
94 | NPRR | Approved | Post-Baseline2 | Yes | Correct Reference to Credit Limit Determination | TPTF | None | 0 | N/A
95 | NPRR | Approved | Post-Baseline2 | Yes | Clarify Recipients of McFRIs | TPTF | None | 0 | N/A
96 | NPRR | Approved | Post-Baseline2 | Yes | Nodal Protocol Revisions to the RMR Startup Energy Payment | ERCOT Staff | None | 0 | Y
97 | NPRR | Approved | Post-Baseline2 | Yes | Changes to Section 8 to Incorporate role of TRE, the IMM, and the concept of Market Compliance | TPTF | None | $100k-$250k | Y
98 | NPRR | Approved | Post-Baseline2 | Yes | Protocols 4 and 6 Formula Clarifications | TPTF | None | 0 | Y
99 | NPRR | Approved | Post-Baseline2 | Yes | RMR Incentive Factor Payment | TPTF | None | 0 | Y
100 | NPRR | Approved | Post-Baseline2 | Yes | Removing PCRR release mechanism | TPTF | None | 0 | Y
101 | NPRR | Approved | Post-Baseline2 | Yes | Modify Time Requirements for Entry of Equipment in the Outage Scheduler | TPTF | None | 0 | N/A
102 | NPRR | TAC approved on 10/2/08 | Post-Baseline2 | Yes | PUCT 25.505 Publication of Resource and Load Information (Disclosure of market data (PRR697 / PUCT33490)) | TPTF | None | $1.5M-$2.0M | Y | 1 | 1 | 4 | 4 | 4 | 2 | 4 | 1 |  | 4 | 4 |  | 3 | 2 |  | 4
103 | NPRR | Approved | Post-Baseline2 | Yes | Settlement of Power Imported via DC Ties (Back to Back Ties) and Block Load Transfer Under Emergency Conditions | TPTF | None | 0 | Y
105 | NPRR | Approved | Post-Baseline2 | Yes | Section 23, Synchronization of Zonal Protocols | ERCOT Staff | None | 0 | N/A
106 | NPRR | Approved | Post-Baseline2 | Yes | Section 24, Synchronization of Zonal Protocols | ERCOT Staff | None | 0 | N/A
107 | NPRR | Approved | Post-Baseline2 | Yes | Emergency Interruptible Load Service | ERCOT Staff | None | <$50k | Y
108 | NPRR | Approved | Post-Baseline2 | Yes | Fuel Oil Price (FOP) Clarification | ERCOT Staff | None | 0 | Y
109 | NPRR | Approved | Post-Baseline2 | Yes | Section 18, Synchronization of Zonal Protocols | ERCOT Staff | None | 0 | N/A
110 | NPRR | Approved | Post-Baseline2 | Yes | Section 20, Synchronization of Zonal Protocols | ERCOT Staff | None | 0 | N/A
111 | NPRR | Approved | Post-Baseline2 | Yes | Timelines for Response by ERCOT to TSP Requests | ERCOT Staff | None | 0 | N/A
112 | NPRR | Approved | Post-Baseline2 | Yes | Emergency Base Point Price Revision | ERCOT Staff | None | 0 | Y
113 | NPRR | TAC approved on 10/2/08 | Post-Baseline2 | Yes | Load Resource Type Indicator for Ancillary Service (AS) Trades and Self-Arranged AS | ERCOT Staff | None | $500K- $1.0M | Y | 1 | 4 | 4 | 4 | 4 | 4 | 4 | 4 |  | 4 | 4 |  | 3 | 4 |  | 4
114 | NPRR | Approved | Post-Baseline2 | Yes | Section 11, Synchronization of Zonal Protocols | ERCOT Staff | None | 0 | N/A
117 | NPRR | Approved | Post-Baseline2 | Yes | Resource Registration Clarification | ERCOT Staff | None | 0 | N/A
118 | NPRR | Approved | Post-Baseline2 | Yes | Section 14, Synchronization of Zonal Protocols | ERCOT Staff | None | 0 | N/A
119 | NPRR | Approved | Post-Baseline2 | Yes | Resource Limit Calculator | ERCOT Staff | None | 0 | Y
120 | NPRR | Approved | Post-Baseline2 | Yes | Corrections and Clarifications for Real Time Settlements | ERCOT Staff | None | 0 | Y
122 | NPRR | Approved | Post-Baseline2 | Yes | Simplify Ancillary Services Settlement Formulas | ERCOT Staff | None | 0 | Y
123 | NPRR | Approved | Post-Baseline2 | Yes | Inadvertent Energy Account Revision | ERCOT Staff | None | 0 | N/A
124 | NPRR | TAC approved on 10/2/08 | Post-Baseline2 | Yes | Resource Node Updated Definitions | ERCOT Staff | None | $100k-$150k | Y | 4 | 1 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 |  |  | 3 | 4 |  | 4
126 | NPRR | Approved | Post-Baseline2 | Yes | Section 19, Synchronization of Zonal Protocols | ERCOT Staff | None | 0 | N/A
127 | NPRR | Approved | Post-Baseline2 | Yes | Section 22 Attachments A, I, J & M, Synchronization of Zonal Protocols | ERCOT Staff | None | 0 | N/A
128 | NPRR | Ready for PRS consideration in October | Post-Baseline2 | Yes | Combined Cycle Power Blocks with Multiple Voltage Interconnections | Calpine | None | $100k-$150k | Y |  | 1 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 |  |  | 3 | 4 |  | 4
129 | NPRR | TAC approved on 10/2/08 | Post-Baseline2 | Yes | Section 15, Synchronization of Zonal Protocols | ERCOT Staff | None | 0 | N/A | [9 empty] | 4 |  |  | 3
130 | NPRR | Approved | Post-Baseline2 | Yes | CRR Settlements Revenue Equalization | TPTF | None | $50k-$100k | Y
131 | NPRR | PRS tabled due to "Approved Post-Go-Live" status | Post-Baseline2 | Approved Post-Go-Live | Ancillary Service Trades with ERCOT | NRG Texas | TBD | TBD | N |  | 1 | 4 | 4 | 4 | 1 | 4 | 4 | 4 | 4 |  |  | 3 | 2 |  | 4
132 | NPRR | Approved | Post-Baseline2 | Yes | Outage Clarification | ERCOT Staff | None | 0 | Y
133 | NPRR | Approved | Post-Baseline2 | Yes | Addition of PSSE Format | ERCOT Staff | None | 0 | Y
134 | NPRR | PRS tabled until development of Impact Analysis | Post-Baseline2 | Yes | Section 7 Cleanup | TPTF | TBD | TBD | N |  | 1 | 4 | 4 | 4 | 1 | 2 | 4 | 1 | 4 |  |  | 3 | 4 |  | 4
135 | NPRR | PRS tabled until PRR is submitted | Post-Baseline2 | TBD | Deletion of UFE Analysis Zone Language | ERCOT Staff | TBD | TBD | N
136 | NPRR | Expected to be ready for PRS consideration in October | Post-Baseline2 | Yes | Interim Solution for 15-Minute Settlement of Advanced Meters | AEP | TBD | TBD | N
137 | NPRR | Withdrawal Pending | Post-Baseline2 | N/A | Synchronization and Update of Section 21 | ERCOT Staff | N/A | N/A | N/A
138 | NPRR | Ready for PRS consideration in October | Post-Baseline2 | Yes | Credit Monitoring and Management Reports | Credit Working Group | None | 0 | Y
139 | NPRR | Expected to be ready for PRS consideration in October | Post-Baseline2 | Yes | Available Credit Limit, Estimated Aggregate Liability, Future Credit Exposure Calculation Updates | Credit Working Group | TBD | TBD | N | [9 empty] | 4 |  |  | 3
140 | NPRR | PRS Pending Language | Post-Baseline2 | Yes | Revision to CRR Obligation Margin Adder | J. Aron | TBD | TBD | N
141 | NPRR | PRS tabled pending until PUCT decision | Post-Baseline2 | Yes | TDSP Energy Storage for Reliability | AEP | TBD | TBD | N
142 | NPRR | Ready for PRS consideration in October | Post-Baseline2 | Yes | EECP Media Appeal Change | OWG | None | 0 | N/A
143 | NPRR | Ready for PRS consideration in October | Post-Baseline2 | Yes | Section 9.9.1, Invoice Recipient Payment to ERCOT for the CRR Auction, Clean-up | ERCOT Staff | None | 0 | N/A
144 | NPRR | TAC approved on 10/2/08 | Post-Baseline2 | Yes | Five RUC Deployments Needed Before Requiring Verifiable Costs (VCWG) | VCWG | None | 0 | N/A
145 | NPRR | Expected to be ready for PRS consideration in October | Post-Baseline2 | TBD | PPAs as Resource-Specific Verifiable Costs (VCWG) | VCWG | TBD | TBD | N
146 | NPRR | Expected to be ready for PRS consideration in October | Post-Baseline2 | Yes | ICCP Telemetry Information Submittals | AEP | TBD | TBD | N
147 | NPRR | PRS Pending Language | Post-Baseline2 | TBD | DAM Short Pay Changes | WMS | TBD | TBD | N
148 | NPRR | Ready for PRS consideration in October | Post-Baseline2 | Yes | Treatment of Financial Information as Confidential | J. Aron | None | 0 | N/A
149 | NPRR | Remanded to NPRSA by PRS | Post-Baseline2 | TBD | Change the Name of Emergcney Electric Curtailment Plan (EECP) to Energy Emergency Alert (EEA) | ERCOT Staff | TBD | TBD | N
150 | NPRR | May not be ready for PRS consideration in October | Post-Baseline2 | Yes | Responsive Reserve Service Offer Floor | DSWG | TBD | TBD | N
151 | NPRR | Referred back to TPTF for review of comments | Post-Baseline2 | Yes | Clarify Definition of a Generator Output Breaker in the Outage Scheduler | Center Point | TBD | TBD | N
152 | NPRR | PRS Pending Language | Post-Baseline2 | Yes | References to Section 22 Attachments | ERCOT Staff | TBD | TBD | N
153 | NPRR | PRS Pending Language | Post-Baseline2 | Approved Post-Go-Live | Generation Resource Fixed Quantity Block Offer | TPTF | TBD | TBD | N
154 | NPRR | PRS Pending Language | Post-Baseline2 | Yes | Corrections of Entities Able to Bid for Point-To-Point Obligations in the Day-Ahead Market | TPTF | TBD | TBD | N
155 | NPRR | TPTF Pending Language | Post-Baseline2 | TBD | Clarification of Authorized Representative | ERCOT Staff | TBD | TBD | N
156 | NPRR | TPTF Pending Language | Post-Baseline2 | TBD | Transparency for PSS and Full Interconnection Studies | PSEG Texas | TBD | TBD | N
157 | NPRR | TPTF Pending Language | Post-Baseline2 | TBD | Extending Black Start Service Bid Timeline | ROS | TBD | TBD | N
158 | NPRR | TPTF Pending Language | Post-Baseline2 | TBD | EILS Self-Provision Formula Correction and Clarifications | ERCOT Staff | TBD | TBD | N
159 | NPRR | TPTF Pending Language | Post-Baseline2 | TBD | Resource Category Startup Offer Generic Cap for Wind Resources | VCWG | TBD | TBD | N
160 | NPRR | TPTF Pending Language | Post-Baseline2 | TBD | Elimination of the Non-ERCOT LSE Fee | AEP | TBD | TBD | N