## Slide 1
2009 PPL Re-Planning

## Slide 2: 2009 Project Planning Update - Background
The 2009 ERCOT fee case has been withdrawn due to the Nodal Go-Live date change. This creates a need to reforecast the 2009 PPL:
  Nodal deferred projects cannot be executed as originally planned
  Continuation of the Nodal project has resource implications for projects on the 2009 PPL
  ERCOT System Administration Fee will remain flat in 2009
    This limits our project funding
      Original project budget = $27.2M
      Revised project budget = $12.2M

## Slide 3: 2009 Project Planning Update – Re-planning Effort
DPOs asked to update 2009 PPL with the following considerations:
  For planning purposes, assume Nodal is not delivering in 2009
    When Nodal schedule is released we will revisit the revised 2009 PPL
  What won’t be required since Nodal is delayed
  What will be required to keep Zonal systems “running”
  Carryover funding needs of currently executing projects
  Critical nature of need
    Limited funding (and other resources) requires us to limit our project activity to the most critical items
    Preserve funding for key market projects
Keep 2009 Non-Nodal Projects to a minimum
  Finish what is started
  Only start “essential” projects
In 2009, we will address additional urgent needs as they arise

## Slide 4: 2009 Project Planning Update – Approval Schedule
Date |  | Activity / Event | Expected Outcome / Deliverables | Ownership
October |  | Finalize 2009 Project Lists | Revised 2009 Initiatives Lists from CARTs | DPO Managers
10/6 |  | SRT | Initial review of all Initiatives Lists | Anderson
10/6 |  | Executive Team | Initial review of all Initiatives Lists | Troxtell
10/14 |  | COPS | Review and approval of MO Initiatives List | Anderson / Parrish
10/15 |  | RMS | Review and approval of RO Initiatives List | Anderson / Parrish
10/15 |  | Final Initiatives Lists due to PMO | (SO exempt due to ROS and WMS meeting timing) | DPO Managers
10/16 |  | ROS | Review and approval of SO Initiatives List | Anderson / Lowe
Oct./Nov. |  | Leadership Approval Phase | Approved 2009 Initiatives Lists | DPO Mgrs / Anderson
10/20 |  | SRT | Final review and approval of all Initiatives Lists | Anderson
10/20 |  | Executive Team | Final review and approval of all Initiatives Lists | Troxtell
10/21 |  | Finance & Audit Committee | Initial review of 2009 prioritization process | Troxtell
10/22 |  | WMS | Review and approval of SO Initiatives List | Anderson / Lowe
10/23 |  | PRS | Final review and approval of complete Initiatives List | DPO Mgrs / Anderson
11/3 |  | SRT | Review of market subcommittee approval results | Anderson
11/3 |  | Executive Team | Review of market subcommittee approval results | Troxtell
11/6 |  | TAC | Final review and approval of all Initiatives Lists | Anderson
11/18 |  | Finance & Audit Committee | Final review and approval of all Initiatives Lists | Troxtell
11/18 |  | Board of Directors | Final review and approval of all Initiatives Lists | Karnei / Troxtell

## Slide 5: 2009 Project Planning Update – Top Risks/Constraints
Resource Contention with Nodal
Reduced Capital Project Budget
Limited Data Center Capacity
  Already at full capacity
  No relief until MET Center Disposition Project delivers more capacity
    Potentially not until 4Q2010 or 1Q2011
    Means we potentially can’t “plug-in” another server until relief is realized

## Slide 6: 2009 Project Planning Update – DRAFT Summary by CART
** CO – Met Center | $ 20,400,000 | $ 20,400,000 | $ 0
* Revised 2009 budget is $12.2M
** Met Center project is funded by a separate budget line item
CART | Initial 2009 Budget | Revised Draft 2009 Budget | Change
CO | $ 3,550,000 | $ 2,750,000 | ($ 800,000)
IO | $ 8,350,000 | $ 5,525,000 | ($ 2,825,000)
MO | $ 4,300,000 | $ 575,000 | ($ 3,725,000)
RO | $ 3,500,000 | $ 2,950,000 | ($ 550,000)
SO | $ 7,500,000 | $ 900,000 | ($ 6,600,000)
Total | $ 27,200,000 | * $ 12,700,000 | ($ 14,500,000)