|  |  |  |  | System Planning Division |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | Monthly Status Report to Reliability and Operations Subcommittee for September 2008 |  |  |
|  |  | Report Highlights |  |  |  |  |  |  |
| Item |  |  |  |  |  |  |  |  |
| 1. | - ERCOT is currently tracking 253 active generation interconnection requests totaling over 108,000 MW. This includes almost 53,000 MW of wind generation. - 152 MW of new wind generation began commercial operation bringing the currently installed total of wind power capacity to 6,023 MW. |  |  |  |  |  |  |  |
| 2. | - Regional Planning is currently reviewing proposed transmission improvements with a total cost of $548.9 Million - Transmission Projects approved in 2008 to date total $255 Million - All projects (in engineering, routing, licensing and construction) totals approximately $3.8 Billion - Transmission Projects energized in 2008 total about $375 Million - Oncor’s Nacogdoches to Lufkin 345 kV Line Project received ERCOT Board recommendation this month |  |  |  |  |  |  |  |

Table of Contents

1.	Generation Interconnection	1

1.1.	New Generation Beginning Commercial Operations	1

1.2.	New Signed Interconnection Agreements	1

1.3.	Summary of Active Generation Interconnection Requests	1

1.4.	Potential Future Generation Interconnections	2

2.	Regional Planning Group Project Reviews	4

3.	Other Notable Activities	5

# 1.	Generation Interconnection

Additional information regarding detailed generation interconnection and impact studies is contained in the “Generation Project Interconnection Information” folder in the “Operations and System Planning” area on the ERCOT website:  http://planning.ercot.com/login/login.

## New Generation Beginning Commercial Operations

# Sherbino 1 Wind Farm (06INR0012a) in Pecos County for 150 MW

# Texas State Technical College Wind (non-modeled) in Nolan County for 2 MW

## The total installed wind capacity is now 6,023 MW.

## New Signed Interconnection Agreements

Papalote Creek Wind Farm (08INR0012) in San Patricio County for 180 MW

## Summary of Active Generation Interconnection Requests

| GENERATION INTERCONNECTION REQUESTS CURRENTLY BEING PROCESSED |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Currently tracking 253 active generation interconnection or change requests As of September 30, 2008 |  |  |  |  |  |
|  |  | North | South | West | Total |
| Security Screening Study |  | 3 | 8 | 19 | 30 |
| SSS Completed |  | 6 | 15 | 19 | 41 |
| Full Interconnect Study |  | 32 | 28 | 79 | 139 |
| FIS Completed |  | 1 | 9 | 0 | 10 |
| Interconnect Agreement Completed |  | 7 | 10 | 17 | 34 |
| Capacity for Grid, MW |  | 25,938 | 37,593 | 45,120 | 108,651 |
| Wind Capacity, MW |  | 2,160 | 10,321 | 40,972 | 53,453 |

| Fuel Type | Non-Public (MW) | Public (MW) | Grand Total (MW) |
| --- | --- | --- | --- |
| Gas-CC | 23,910 | 5,519 | 29,429 |
| Gas-CT | 900 | 505 | 1,405 |
| Nuclear | 3,200 | 9,186 | 12,386 |
| Coal | 5,344 | 4,131 | 9,475 |
| Wind | 44,477 | 8,976 | 53,453 |
| Solar | 828 | 0 | 828 |
| Biomass | 50 | 145 | 195 |
| Other | 1,480 | 0 | 1,480 |
| Grand Total | 80,189 | 28,462 | 108,651 |

## Potential Future Generation Interconnections

The table below summarizes the publicly known potential future generation projects for the ERCOT region.  (IA=Interconnect Agreement, PL=Public Letter, XX= cancelled)

| Future Generation Interconnections (Public Projects) as of September 30, 2008 |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| INR | Site Name | Status | County | Region | In-Service Date | Fuel | MW Into Grid | Change from Last Report |
| 08INR0038 | M Bar Wind | PL | Andrews | West | Oct-08 | Wind | 194 | Date |
| 06INR0022a | Penascal Wind Farm 1 | IA | Kenedy | South | Oct-08 | Wind | 202 | Date |
| 08INR0050 | Victoria Power Station | IA | Victoria | South | Oct-08 | Gas | 332 |  |
| 07INR0037 | Bull Creek Wind Plant | IA | Borden | West | Oct-08 | Wind | 180 |  |
| 07INR0034 | Wolf Ridge Windfarm | IA | Cooke | North | Oct-08 | Wind | 113 |  |
| 07INR0045a | Airtricity Pyron Wind Farm | IA | Scurry | West | Nov-08 | Wind | 249 |  |
| 07INR0045b | Airtricity Inadale | IA | Scurry | West | Nov-08 | Wind | 197 |  |
| 08INR0037 | Airtricity Panther Creek 2 | IA | Howard | West | Nov-08 | Wind | 115 |  |
| 07INR0027 | S Houston Grn Pwr Exp | IA | Galveston | South | Nov-08 | Gas | 244 |  |
| 09INR0026a | Sterling Energy Center | PL | Sterling | West | Dec-08 | Wind | 200 |  |
| 08INR0059 | Gray Wind Project | PL | Borden | West | Dec-08 | Wind | 141 |  |
| 08INR0053 | Elbow Creek Wind Project | IA | Howard | West | Dec-08 | Wind | 117 |  |
| 08INR0025 | Pistol Hill Energy Center | PL | Ector | West | Dec-08 | Wind | 300 |  |
| 07INR0029 | South Trent Wind Farm | IA | Taylor | West | Dec-08 | Wind | 101 |  |
| 07INR0011 | Turkey Track Energy Center | IA | Nolan | West | Dec-08 | Wind | 170 |  |
| 04INR0011e | Hackberry Wind Farm | IA | Shackelford | West | Dec-08 | Wind | 165 |  |
| 07INR0005 | Notrees-1 | IA | Ector | West | Dec-08 | Wind | 151 |  |
| 05INR0015a | Gulf Wind 1 | IA | Kenedy | South | Dec-08 | Wind | 283 |  |
| 08INR0065 | Buffalo Gap 4 and 5 | PL | Nolan | West | Mar-09 | Wind | 465 |  |
| 08INR0046 | Bosque Expansion | IA | Bosque | North | Mar-09 | Gas | 255 |  |
| 07INR0036 | Coyote Run Windfarm | IA | Borden | West | Mar-09 | Wind | 225 |  |
| 09INR0072 | Dansby3 | PL | Brazos | North | Apr-09 | Gas | 48 |  |
| 07INR0028b | Goat Wind - phase 2 | IA | Sterling | West | Apr-09 | Wind | 70 | Date/MW |
| 09INR0060 | Stephens Wind Farm | PL | Borden | West | May-09 | Wind | 141 |  |
| 09INR0028 | V H Braunig 6 | PL | Bexar | South | May-09 | Gas | 185 |  |
| 08INR0040 | Lenorah Project | PL | Martin | West | May-09 | Wind | 350 |  |
| 08INR0012 | Papalote Creek Wind Farm | IA | San Patricio | South | May-09 | Wind | 180 | New |
| 09INR0036 | McAdoo Energy Center II | PL | Dickens | West | Jun-09 | Wind | 500 |  |
| 09INR0026 | Sterling Energy Center | PL | Sterling | West | Jun-09 | Wind | 300 |  |
| 08INR0035 | Cedar Bayou 4 | IA | Chambers | South | Jun-09 | Gas | 539 |  |
| 09INR0027 | Winchester Power Park | IA | Fayette | South | Jul-09 | Gas | 178 |  |
| 08INR0003 | Sandow 5 | IA | Milam | North | Jul-09 | Coal | 581 |  |
| 09INR0006a | Oak Grove SES 1 | IA | Robertson | North | Jul-09 | Coal | 855 |  |
| 08INR0033 | Lufkin | IA | Angelina | North | Sep-09 | Biomass | 45 |  |
| 05INR0015b | Gulf Wind 2 | PL | Kenedy | South | Sep-09 | Wind | 400 |  |
| 08INR0018 | Gunsight Mountain | IA | Howard | West | Oct-09 | Wind | 120 |  |
| 09INR0015 | Comanche Peak 1&2 Upgrade | PL | Somervell | North | Oct-09 | Nuclear | 86 |  |
| 09INR0045 | Sand Hill Peakers | PL | Travis | South | Nov-09 | Gas | 94 |  |
| 09INR0039 | Nueces Bay 7 Repowering | IA | Nueces | South | Nov-09 | Gas | 327 |  |
| 09INR0038 | Barney Davis 2 Repowering | IA | Nueces | South | Nov-09 | Gas | 360 |  |
| 09INR0034 | Gatesville Wind Farm | PL | Coryell | North | Dec-09 | Wind | 200 |  |
| 09INR0006b | Oak Grove SES 2 | IA | Robertson | North | Jan-10 | Coal | 855 |  |
| 06INR0029 | Jackson Mountain | IA | Nolan | West | Jan-10 | Wind | 90 |  |
| 09INR0037 | Scurry County Wind III | PL | Scurry | West | Mar-10 | Wind | 350 |  |
| 06INR0006 | Cobisa-Greenville | PL | Hunt | North | May-10 | Gas | 1,750 |  |
| 09INR0002 | J K Spruce 2 | IA | Bexar | South | Jun-10 | Coal | 750 |  |
| 05INR0015c | Gulf Wind 3 | PL | Kenedy | South | Sep-10 | Wind | 400 |  |
| 06INR0012b | Sherbino Mesa Wind Farm 2 | IA | Pecos | West | Oct-10 | Wind | 150 |  |
| 12INR0003 | Throckmorton Wind Farm | PL | Throckmorton | West | Dec-10 | Wind | 400 |  |
| 06INR0026 | Wild Horse Mountain | IA | Howard | West | Dec-10 | Wind | 120 |  |
| 10INR0020 | Panda Temple Power | PL | Bell | North | May-11 | Gas | 1,092 |  |
| 10INR0010 | Jack County 2 | PL | Jack | North | Jun-11 | Gas | 620 |  |
| 09INR0007 | Nacogdoches Project | PL | Nacogdoches | North | Apr-12 | Biomass | 100 |  |
| 07INR0004 | Pampa Energy Center | PL | Gray | West | May-12 | Coal | 165 |  |
| 09INR0024 | B&B Panhandle Wind | PL | Carson | West | Jun-12 | Wind | 1,001 |  |
| 09INR0001 | Sandy Creek 1 | IA | McLennan | North | Jun-12 | Coal | 925 |  |
| 12INR0004 | Fort Concho Wind Farm | PL | Tom Green | West | Jul-12 | Wind | 400 |  |
| 04INR0011c | Cottonwood Wind | IA | Shackelford | West | Jun-13 | Wind | 100 | Date |
| 04INR0011b | Mesquite Wind Phase 4 | IA | Shackelford | West | Jun-13 | Wind | 136 | Date |
| 11INR0011 | Victoria City Nuclear | PL | Victoria | South | Jan-15 | Nuclear | 3,200 |  |
| 15INR0008 | STP 3 and 4 | PL | Matagorda | South | Jan-15 | Nuclear | 2,700 |  |
| 15INR0002 | Comanche Peak 3 and 4 | PL | Somervel | North | Jan-15 | Nuclear | 3,200 |  |
|  |  |  |  |  |  | TOTAL | 28,462 |  |

# Regional Planning Group Project Reviews

# American Electric Power Service Corporation submitted a project to construct 2 new 138 kV substations, rebuild a 138 kV circuit, build  2 new 138 kV circuits, and install a new 138/69 kV autotransformer in the Abilene/San Angelo area.  The estimated cost of this project is $105.9 M.  This project is in ERCOT Independent Review.

# Luminant Energy submitted the Twin Butte – Kendall 345 kV double circuit line with series compensation.  It is a $327 million project comprised of 170 miles of 345 kV double circuits with both circuits in place, substation and breaker additions at Twin Butte and Kendall, and a 50% series compensation in each circuit.  This project is in ERCOT Independent Review.

# Luminant submitted a set of projects to reduce North to South Congestion.  It consists of several 138 kV line upgrades and series reactor installations.  The total cost for all projects is approximately $31 M. This project is in ERCOT Independent Review.

# Oncor submitted a project to add a 345 kV transmission line from Nacogdoches Southeast to Lufkin Switch with an estimated cost of $29.2 M .  This project was a result of the 2007 Five-Year Plan.  This project was endorsed by TAC on September 4, 2008 and recommended by the ERCOT Board on September 16, 2008.

# CPS Energy submitted a project to add a 138 kV line from Westover Hills to their Anderson substation to complete a new circuit from VLSI substation to Anderson substation.  The VLSI to Westover Hills 138 kV portion will be in-service in 2009 to serve new load at Westover Hills.  This project was a result of the 2007 Five-Year Plan.  The estimated cost of this project is $8.2 M with an in-service date of peak 2010.  This review of this project is complete and a RPG acceptance letter was sent on September 24, 2008.

# AEPSC submitted a project to add a 345 kV Transmission Substation at the point in Haskell County where the Oklaunion to Mulberry Creek and Tonkawa to Graham 345 kV lines cross called Clear Crossing and construct a new 345 kV transmission circuit from the existing Oklaunion Substation to the Bowman Substation.  This project was a result of the 2007 Five-Year Plan.  Clear Crossing is projected to be in service by peak 2010 with a cost of $14 M.  The Oklaunion to Bowman 345 kV line is estimated to be in service by the end of 2011 with a cost of $ 71 M.

# Other Notable Activities

- All postings referred to below can be found at http://planning.ercot.com/login/login unless otherwise indicated.

- ERCOT TPIT report for 08/01/2008 completed (3rd quarter) and posted on 08/18/2008.

- ERCOT TPIT report worksheets have been distributed to TO’s in preparation for receiving updated information for the November TPIT report.  All data is due to ERCOT no later than November 3, 2008.

- Updated SSWG 2008 Data Set A, 2008 Data Set B, and 2009 Data Set A cases have been posted.

- ERCOT Regional Planning is continuing work on the 2013 case to be used for reliability analysis and RPG analysis.  The purpose of this effort is to extend the 2007 Five-Year plan from 2012 to 2013.  Several generation units were selected for generation unavailable studies in accordance with Operations Guide 5.1.4.  Reliability projects were added to eliminate all unserved energy encountered under the various generation unavailable scenarios.  The absence of unserved energy will be confirmed with this set of projects for all selected generation unavailable.  All Reliability Projects, including those determined with all generation available, will then be “backed out” individually to confirm their need.  Subsequently, the list of Reliability projects will be sent to Transmission Owners for review.