TPIT information

Except as noted in this document, each column should be filled in for each project.

Transmission Project Information Tracking (TPIT) and Steady State Base Case updates are done quarterly.  Workbook updates are due to ERCOT on the 1st of the month or the next following business day. The case updates are due to ERCOT a week after the workbook updates.

Each quarter each TSP is e-mailed a base workbook of its projects from the previous quarter’s final TPIT workbook. Each TSP edits its workbook, makes a notation when new projects are added to the workbook, and e-mails it back to ERCOT. ERCOT combines them into one workbook.

For the projects that require Regional Planning group review, the ERCOT regional planning department updates the three columns for: Date Submitted to ERCOT for RPG review, Date RPG Review Completed, and Date ERCOT BOD Review Completed. If a project does not require RPG review, these columns will be blank.

All cancelled, completed, known and proposed transmission projects (60 kV and above) that materially affect the grid’s ability to deliver generation and control voltage shall be included in TPIT.

Cancelled projects need to be moved to cancelled tab, and then removed during the next quarter’s update.

Completed projects need to be moved to completed tab.

ERCOT assigns the TPIT project numbers to new projects.  TSP includes a notation that new projects were added to the workbook in the e-mail used to transmit the workbook back to ERCOT.

TSPs coordinate with other TSPs on combined projects.  Combined projects should only be included one time. Some projects that have multiple distinct phases with multiple TSPs constructing separate phases may be submitted as multiple projects. Notes of the related TPIT projects should be made in the ‘Other’ column.

There should not be any duplicate projects in the workbooks.

Additional data items will only be added to TPIT with approval of the TSPs who submit the data.

TSPs provide as much technical data and cost estimates as possible.  TSPs include preliminary cost estimates for all projects.  If cost estimates are part of another project please indicate in the ‘Other’ column not in the cost estimate column.  Final project cost for completed projects should be provided when available.

Units should not be in the columns with numerical data.  MVA, kV, miles, etc… are included in the headers.  All numerical data should be entered as numbers not text.

The ‘SERVICE LEVEL KV’ column for transformers should be the high voltage side of the transformer.

The two ‘Transmission Circuit Miles’ (new and rebuilt) columns should indicate the circuit miles of transmission wire and NOT the tower miles or transmission Right of Way.

The ‘Actual In-Service Date’ column should be blank in the Future tab, but filled in on the Completed tab.

Column R ‘County Location of Ending point for a Line’ should be blank for substation projects.

The ‘SSWG Base Case Related Bus Numbers’ and ‘Is the project reflected in SSWG Base Cases?’ columns may be blank. Example: some projects do not require a change to the SSWG cases. Because SSWG models are Bus-Branch models they do not reflect detailed substation design. Some projects only make substation improvements that increase reliability of the transmission system, but do not change impedance or ratings in a Bus-Branch model.  Providing bus numbers is optional.

The ‘Requested Additional Information’ and ‘Other’ columns are optional.