## Slide 1: PMO Update to PRS
Troy Anderson
ERCOT Program Management Office
October 23, 2008

## Slide 2: PMO Update - Agenda
  YTD Project Spending Update
  2009 Project Reforecast
  Recent Project Implementations
    September 2008

## Slide 3: 2008 Project Spending Update – 10/17/2008
CART | Initial Budget | Current Budget | Spending Forecast
CO | $ 8,450,000 | $ 4,986,754 | $ 5,391,064
IO | $ 6,400,000 | $ 6,900,000 | $ 6,813,833
MO | $ 1,200,000 | $ 1,394,906 | $ 1,328,567
RO | $ 6,100,000 | $ 3,830,000 | $ 2,852,746
SO | $ 50,000 | $ 1,071,795 | $ 838,918
Nodal / Zonal Interdependent | $ 5,314,000 | $ 6,715,130 | $ 6,715,130
Released but Not Reallocated | $ 0 | $ 2,615,415 | $ 0
Total | $ 27,514,000 | $ 27,514,000 | $ 23,940,258
CO – Met Center * | $ 0 | $ 6,232,880 | $ 3,007,341
* Met Center project is not funded by initial project budget allocation
Arrows indicate trend since last report (August 2008)

## Slide 4: 2009 Project Reforecast - Background
The 2009 ERCOT fee case has been withdrawn due to the Nodal Go-Live date change. This creates a need to reforecast the 2009 PPL:
  Nodal deferred projects cannot be executed as originally planned
  Continuation of the Nodal project has resource implications for projects on the 2009 PPL
  ERCOT System Administration Fee will remain flat in 2009
    This limits our project funding
      Original project budget = $27.2M
      Revised project budget = $12.2M

## Slide 5: 2009 Project Reforecast –Considerations
DPOs asked to update 2009 PPL with the following considerations:
  For planning purposes, assume Nodal is not delivering in 2009
    When Nodal schedule is released we will revisit the revised 2009 PPL
  What won’t be required since Nodal is delayed
  What will be required to keep Zonal systems “running”
  Carryover funding needs of currently executing projects
  Critical nature of need
    Limited funding (and other resources) requires us to limit our project activity to the most critical items
    Preserve funding for key market projects
Keep 2009 Non-Nodal Projects to a minimum
  Finish what is started
  Only start “essential” projects
In 2009, we will address additional urgent needs as they arise

## Slide 6: 2009 Project Reforecast – Top Risks/Constraints
Resource Contention with Nodal
Reduced Capital Project Budget
Limited Data Center Capacity
  Already at full capacity
  No relief until MET Center Disposition Project delivers more capacity
    Potentially not until 4Q2010 or 1Q2011
    Means we potentially can’t “plug-in” another server until relief is realized

## Slide 7: 2009 Project Reforecast –Schedule
2009 Project Prioritization Schedule - Overview
  Q1 2008
    2009 Initiative Lists drafted, revised and approved for inclusion in ERCOT budget request
  September 2008
    CARTs revise 2009 Initiative Lists to prepare for market review
  October 2008
    Review by market subcommittees
      MO - COPS (October 14)
      RO - RMS (October 15)
      SO - ROS, WMS (October 16 / October 22)
      CO, IO, MO, RO, SO – PRS (October 23)
  November 2008
    Review by TAC (November 6)
    Available for F&A and Board review (November 18)

## Slide 8: 2009 Project Reforecast – Approval Status
2009 Project Approval Status by Program Area
  All 5 lists have been reviewed by ERCOT Strategic Review Team (SRT) and Executive Team (ET)
  CO (Corporate Operations)
    8 projects have been deferred due to funding limitations ($1.5M impact)
  IO (IT Operations)
    No changes since ET review on 10/13/2008
  MO (Market Operations)
    Modified and approved by COPS on 10/14/2008
      Moved “Web-enabled Registration” from the Parking Lot to just below the cutline
  RO (Retail Operations)
    Modified and approved by RMS on 10/15/2008
      Added “Advanced Metering – Retail Market Interface” – (Rank 32 on the merged list)
  SO (System Operations)
    Reviewed by ROS on 10/16/2008
      ROS didn’t formally approve the list – they are concerned that additional projects should be considered in support of the current market due to the Nodal delay
        ERCOT taking steps to address this concern
      ROS is also concerned that the 2009 portion of the “Operator Training Simulator” project has been transferred to Nodal (thus changing funding sources from the System Admin Fee to the Nodal Fee)
    WMS consideration on 10/22/2008

## Slide 9: 2009 Project Reforecast – Summary by CART
** CO – Met Center | $ 20,400,000 | $ 20,400,000 | $ 0
* Revised 2009 project budget is $12.2M
** Met Center project is funded by a separate budget line item
CART | Initial 2009 Budget | Revised Draft 2009 Budget | Change
CO | $ 3,550,000 | $ 1,775,000 | ($ 1,775,000)
IO | $ 8,350,000 | $ 5,525,000 | ($ 2,825,000)
MO | $ 4,300,000 | $ 550,000 | ($ 3,750,000)
RO | $ 3,500,000 | $ 3,450,000 | ($ 50,000)
SO | $ 7,500,000 | $ 900,000 | ($ 6,600,000)
Total | $ 27,200,000 | * $ 12,200,000 | ($ 15,000,000)

## Slide 10: 2009 Project Reforecast – Project Lists
2009 Project Prioritization – Detailed Project Lists
  The Excel file provided with the presentation contains the revised 2009 project lists by Program Area (CART)
  Due to limited funding, the lists were merged to assist in determining overall priority for each effort
    As adjustments are made during the approval process, the cutline in the merged list is moved as needed
  To aid in resource prioritization, a single line item for the Nodal project was added to the merged list
    A project being ranked above Nodal simply implies that if a resource conflict arises between that project and Nodal, the higher ranked effort might be allowed to proceed, causing a potential impact to the Nodal delivery schedule – any conflict would be closely reviewed
  Summary Statistics
    39 projects are currently funded by the $12.2M budget
    9 projects were requested but are currently unfunded ($1.5M in total)
    37 projects were deferred due to the Nodal delay or for other business reasons

## Slide 11: PMO Update - YTD 2008 Project Implementations
January 2008
  IO PR-70050_01 EIS ETL Tool Implementation
February 2008
  CO PR-70044_01 MET Center Facility Analysis
  RO PR-70005_01 MO SAS70 Procedures Optimization
  IO PR-70012_01 Cyber Security Project #14
  IO PR-70037_01 OC-3 Microwave Replacement
  SO PR-70035_01 2007 REC Program Modifications
March 2008
  IO PR-60055_01 Enterprise Service Management
  IO PR-60013_01 Enhanced Digital Certificate Program
  MO PR-70038_01 ERCOT.com Infrastructure Enhancement
        (Collage Infrastructure Redesign)
  CO PR-70013_01 Corporate Document Management
  CO PR-70041_01 Taylor Control Room Display System Replacement
April 2008
  None

## Slide 12: PMO Update - YTD 2008 Project Implementations (cont’d)
May 2008
  MO PR-70048_01 MV90xi System Upgrade
  CO PR-70053_01 Video Teleconferencing
  IO PR-70055_01 Additional Production SAN Capacity
June 2008
  MO PR-60077_01 ERCOT.com Registered Area
  IO PR-70030_01 Tellabs DCCS System Replacement
  IO PR-80022_01 Additional SAN Capacity for Projects
July 2008
  RO PR-60008_01 Terms and Conditions & Performance Measures
  CO PR-70023_01 CyberSecurity Project #2
  CO PR-70047_01 Corporate Application Environment True-Up
  CO PR-80010_01 Ruby Standardization
  CO PR-60073_01 eRecruiting

## Slide 13: PMO Update - YTD 2008 Project Implementations (cont’d)
August 2008
  RO PR-60015_01 Siebel Data Model Assessment
  CO PR-80035_01 Intranet Assessment HR & Communications
  IO PR-70054_01 Blade Refresh
September 2008
  MO PR-40066_04 Lodestar 4.7 Upgrade
  SO PR-50070_01 Unit Testing Automation and Electronic Submittal – Phase 1