## Slide 1: 2009 Project Reforecast
Troy Anderson
ERCOT Program Management Office
November 6, 2008

## Slide 2: 2009 Project Reforecast - Agenda
  YTD 2008 Project Spending Update
  2009 Project Reforecast

## Slide 3: 2008 Project Spending Update – 10/30/2008
CART | Initial Budget | Current Budget | Spending Forecast
CO | $ 8,450,000 | $ 5,676,754 | $ 5,340,480
IO | $ 6,400,000 | $ 6,900,000 | $ 6,745,238
MO | $ 1,200,000 | $ 1,394,906 | $ 1,303,289
RO | $ 6,100,000 | $ 3,830,000 | $ 2,838,557
SO | $ 50,000 | $ 1,071,795 | $ 788,212
Nodal / Zonal Interdependent | $ 5,314,000 | $ 6,715,130 | $ 6,715,130
Released but Not Reallocated | $ 0 | $ 1,925,415 | $ 0
Total | $ 27,514,000 | $ 27,514,000 | $ 23,730,906
CO – Met Center * | $ 0 | $ 6,232,880 | $ 2,971,724
* Met Center project is not funded by initial project budget allocation
Arrows indicate trend since last report (August 2008)

## Slide 4: 2009 Project Reforecast - Background
The 2009 ERCOT fee case has been withdrawn due to the Nodal Go-Live date change. This creates a need to reforecast the 2009 PPL:
  Nodal deferred projects cannot be executed as originally planned
  Continuation of the Nodal project has resource implications for projects on the 2009 PPL
  ERCOT System Administration Fee will remain flat in 2009
    This limits our project funding
      Original project budget = $27.2M
      Revised project budget = $12.2M

## Slide 5: 2009 Project Reforecast –Considerations
DPOs asked to update 2009 PPL with the following considerations:
  For planning purposes, assume Nodal is not delivering in 2009
    When Nodal schedule is released we will revisit the revised 2009 PPL
  What won’t be required since Nodal is delayed
  What will be required to keep Zonal systems running
  Carryover funding needs of currently executing projects
  Critical nature of need
    Limited funding (and other resources) requires us to limit our project activity to the most critical items
    Preserve funding for key market projects
  Consider data center limitations
    No relief until MET Center Disposition Project delivers more capacity
      Potentially not until 4Q2010 or 1Q2011
      Effort underway to provide relief prior to 4Q2010
We will address additional urgent needs as they arise using our usual set of funding options

## Slide 6: 2009 Project Reforecast –Schedule
2009 Project Reforecast Schedule - Overview
  Q1 2008
    2009 Initiative Lists drafted, revised and approved for inclusion in ERCOT budget request
  September 2008
    CARTs revise 2009 Initiative Lists to prepare for market review
  October 2008
    Review by market subcommittees
      MO - COPS (October 14)
      RO - RMS (October 15)
      SO - ROS, WMS (October 16 / October 22)
      CO, IO, MO, RO, SO – PRS (October 23)
  November 2008
    Initial review by TAC (November 6)
    Reconsideration by ROS, WMS, and PRS
      Review of previous PPL items shelved due to Nodal implementation
  December 2008
    Review by TAC (December 4)
    Available for Board and F&A review (December 9)

## Slide 7: 2009 Project Reforecast – Approval Status
2009 Project Approval Status by Program Area
  All 5 lists have been reviewed by ERCOT Strategic Review Team (SRT) and Executive Team (ET)
  CO (Corporate Operations)
    8 projects fell below the cutline due to funding limitations ($1.5M total cost)
  IO (IT Operations)
    No changes since ET review on 10/13/2008
  MO (Market Operations)
    Modified and approved by COPS on 10/14/2008
      Moved “Web-enabled Registration” from the Parking Lot to just below the cutline
  RO (Retail Operations)
    Modified and approved by RMS on 10/15/2008
      Added “Advanced Metering – Retail Market Interface” (Rank 32 on the merged list)
  SO (System Operations)
    Reviewed by ROS on 10/16/2008
      ROS didn’t formally approve the list – they are concerned that additional projects should be considered in support of the current market due to the Nodal delay
        ERCOT is taking steps to address this concern
      ROS is also concerned that the 2009 portion of the “Operator Training Simulator” project has been transferred to Nodal (thus changing funding sources from the System Admin Fee to the Nodal Fee)
    WMS consideration on 10/22/2008 had a similar result as ROS

## Slide 8: 2009 Project Reforecast – Summary by CART
** CO – Met Center | $ 20,400,000 | $ 20,400,000 | $ 0
* Revised 2009 project budget is $12.2M
** Met Center project is funded by a separate budget line item
CART | Initial 2009 Budget | Revised Draft 2009 Budget | Change
CO | $ 3,550,000 | $ 1,775,000 | ($ 1,775,000)
IO | $ 8,350,000 | $ 5,525,000 | ($ 2,825,000)
MO | $ 4,300,000 | $ 550,000 | ($ 3,750,000)
RO | $ 3,500,000 | $ 3,450,000 | ($ 50,000)
SO | $ 7,500,000 | $ 900,000 | ($ 6,600,000)
Total | $ 27,200,000 | * $ 12,200,000 | ($ 15,000,000)

## Slide 9: 2009 Project Reforecast – Project Lists
2009 Project Prioritization – Detailed Project Lists
  The Excel file provided with the presentation contains the revised 2009 project lists by Program Area (CART)
  Due to 2009 funding constraints, the lists were merged to assist in determining overall priority for each effort
    As adjustments are made during the approval process (and ongoing), the cutline in the merged list is moved as needed
  To aid in resource prioritization, a single line item for the Nodal project was added to the merged list
    A project being ranked above Nodal simply implies that if a resource conflict arises between that project and Nodal, the higher ranked effort might be allowed to proceed, causing a potential impact to the Nodal delivery schedule – any conflict would be closely reviewed
  NEW DEVELOPMENT
    The Executive Team (at the request of the SRT) authorized a 10% “capability” allowance to provide more flexibility in maximizing project delivery in 2009

## Slide 10: 2009 Project Reforecast – Project Lists
2009 Project Prioritization – Detailed Project Lists
  Summary Statistics
    38 projects are currently funded by the $12.2M budget
    8 projects were requested that are below the $12.2M cutline but fall within the 10% capability area ($1.2M in total)
      These projects can be initiated but will be monitored closely to ensure that we stay within our total budget allocation
    1 project was requested that is currently unfunded ($0.3M)
    38 projects were moved to the Parking Lot for various reasons
      16 were deferred due to the Nodal delay
      11 were deferred for other business reasons
      3 were cancelled or being considered for cancellation
      2 were completed in 2008
      3 post-Nodal projects are being delivered by Nodal
        They are marked “Complete” on the SO PPL
      2 post-Nodal projects are being partially delivered by Nodal
        They are marked “Partial Complete” on the SO PPL
      1 was transferred to Nodal (OTS)