## Slide 1: Texas Nodal Program Implementation: Program Update
Ron Hinsley

## Slide 2: Agenda
Health Indicators
Highlights
Critical Path through Feb. 2009
Top Risks / Issues
Cost
Notes: <number>
<footer>
<header>
<date/time>
<number>

## Slide 3: Health Indicators
Indicator | Status | Explanation
Overall | Red | Overall status remains red, driven by schedule and budget indicators
Schedule | Red | Schedule remains red until the integrated schedule is approved
Budget | Red | Budget remains red until new budget is finalized and approved
Scope | Amber | Requirements review still underway
Resources | Amber | Majority of projects reporting amber status
Risks | Amber | Program addressing risks detailed on subsequent slide
Issues | Amber | Program addressing issues detailed on subsequent slide
Quality Control | Red | Status driven by number of Sev 1 and 2 defects and lengthy defect turn-around time
ERCOT Readiness | Amber | Status quo until the schedule is released
Market Participant Readiness | Amber | Status quo until the schedule is released
Note: health indicator measures are located in the appendix

## Slide 4: Highlights
The program is now posting a weekly status report to the nodal website: http://nodal.ercot.com/docs/po/index.html
No tasks on the program critical path are currently behind schedule
EMS CIM Importer has completed Pre-FAT and started FAT. All critical defects have been resolved. FAT is scheduled to complete by Nov. 14
The finalized nodal program schedule will not include additional time for future unforeseen changes that might affect the program’s schedule. Instead, any program changes that arise will be addressed on a case-by-case basis
Defect update
  The number of severity 1, 2, and 3 active defects has remained relatively constant
  We expect a significant increase in numbers as more components enter i-Test

## Slide 5: Highlights – Nodal Reporting Structure
Program Mgmt Office
Janet Ply
Early Delivery Systems/ MP Readiness
Matt Mereness
ERCOT
Readiness
Murray Nixon
Infrastructure
David Forfia
Executive Sponsor*
Ron Hinsley
Quality Assurance: Joyce Statz Testing Czarina: Eileen Hall
TPTF Chair: Joel Mickey
IT Governance
Network Model Mgmt System
Linda Clarke
Congestion Revenue Rights System
Rachelle Zani
Energy Management System
Manuel Atanacio
MIS Portal
Brett Economides
Current Day Reports
Naresh Chunduri
Enterprise Data Whse
Shawna Jirasek
Executive Program Director
Ron Hinsley
Market Systems
Murray Nixon
Nodal Program Controller
Aaron Smallwood
* Accountable for program schedule and budget
MMS
Jeff Robinson
OS Sankara Krishnaswamy
IMM
TBD
Commercial Systems & CMM
Hope Parrish
S&B and CSI
Justin Rasberry
FT
Phyllis Encinias
Reg/Disputes
Clay Katskee
Nodal Integration Systems
Mike Bianco
Integration Svcs
Brian Brandaw
Integration Testing
TBD
Operational Readiness
TBD
E2E Integration Management
Ken Kasparian
Notes: Nodal staffing changes
  ERT efforts have been redistributed to Murray Nixon, the project manager of Market Systems. In her new role, Nixon will structure a team to address nodal business processes and procedures. Nixon will retain her leadership role over the Market Management System (MMS), the Outage Scheduler (OS), and Independent Market Monitoring (IMM) projects
  Jeff Robinson will take on more day-to-day project management activities for the MMS project
  Sankara “Krish” Krishnaswamy, formerly Enterprise Data Warehouse (EDW) Project Manager, is moving into the Outage Scheduler PM role
  Shawna Jirasek is transitioning into the EDW PM role
  Daryl Cote will be leaving the nodal program on Oct. 31. Matt Mereness will replace him as Early Delivery System (EDS) PM, with Richard Howard responsible for system environment readiness
  Stephen Kerr will be leaving the nodal program on Oct. 31, to be replaced by Brian Brandaw as PM for the Enterprise Integration Project (EIP)
  Dr. Joyce Statz joined the nodal program on Oct. 28 as Quality

## Slide 6: Highlights – Staffing
Staffing for nodal continues to trend down for contractors while holding fairly steady for ERCOT employees
Notes: Stats for Sept / Oct:
Group Aug-08 Sep-08 Diff
Employee Hrs 23984 22938 1046
Contractor Hrs 32315 27989 4327
Employee FTEs 143 137 6
Contractor FTEs 192 167 26

## Slide 7: Critical Path through Feb. 2009
NMMS activities to deliver a validated CIM XML file are the critical path activities from now through early 2009.

## Slide 8: Top Risks / Issues
Description | Status
Information Lifecycle Management (ILM) strategy for ERCOT is behind schedule. Problem: Current processes do not adequately address archival and storage requirements for Nodal; Existing Data Center constraints limit new storage growth Without ILM in place and executed, the nodal program go-live date could be delayed because of insufficient storage | Assigning a PM to manage a project to develop an ILM strategy and implement the strategy Project funds have been identified Project to be managed by Business, IT and Nodal
Nodal business process work is incomplete. Without the business process foundation in place, requirements traceability, functional testing, nodal procedures, and training work cannot be completed. | Murray Nixon has been assigned as the PM to lead this effort. Staffing needs and an associated budget have been developed Project schedule development is in progress TPTF agreed with strategy to review top level business processes for clarity and transparency; will leverage work performed in 2006-2008 for as starting point
Traceability between protocols and requirements is largely manual; not all requirements documentation has been updated to reflect NPRR changes and re-approved by TPTF | Requirements review in process to review all project requirements documentation, approvals, and incorporation of NPRRs TPTF input provided on Oct. 27; requested that backlog for Requirements and Conceptual Design Document approvals be packaged for processing ERCOT will implement quarterly cycle for TPTF reviews/approvals

## Slide 9
Cost: Element Summary
When the integrated schedule has been finalized and the financial impact determined we will incorporate this into an updated forecast
Variance
(over)/under
Cost Element
Budget
Actual
Budget
Internal Labor
$ 42.4
$ 42.8
$ (0.4)
External Labor
167.1
177.1
(10.0)
Hardware / Software
60.5
61.6
(1.1)
Travel and Other
11.2
7.2
4.0
Subtotal
$ 281.2
$ 288.7
$ (7.5)
Finance Charge
9.6
10.6
(1.0)
Total
$ 290.8
$ 299.3
$ (8.5)
Nodal Program
Cost Element Summary
($ Millions)
Through September 2008

## Slide 10
Appendix

## Slide 11: Health Indicator Measures
Metric | Green | Amber | Red
Overall | Both core indicators are green | At least one core indicator is amber, but none are red | At least one core indicator is red
Schedule | All activities on the critical path are complete, or are expected to be complete, on or ahead of the planned dates | No dates have been missed, but one or more critical path activities is forecasted to complete late | At least one critical path deliverable has missed its due date. Project implementation date is in jeopardy
Budget (hrs) | Project forecasted to complete within the baselined hours | Project forecasted to complete up to 5% over the baselined hours | Project forecasted to complete more than 5% over the baselined hours
Scope | All Requirements approved; no unplanned scope changes | Pending approvals for Requirements; no unplanned scope changes | Unapproved Requirements and/or unplanned scope changes
Resources | All key resource positions are filled and no schedule delays are expected. | One or two key positions are not staffed and the schedule may be adversely impacted. | More than two key positions are not staffed and the schedule will be impacted.
Risk | All project risks have a Risk Score =< 4 | At least one project risk has a Risk Score => 5 and =< 8 | At least one project risk has an Risk Score => 9
Issues | All issues are being resolved by the required due dates | Some issues are remaining open past the required due dates but none are of “critical” priority (Impact = 3 or 4) | At least one “critical” priority issue (Impact = 3 or 4) is open past the due date
Quality Control | Defect metrics meet all of the following: # of Severity 1 = 0 # of Severity 2 = 0 Avg. #. Days to Close Sev 1 and Sev 2 Defects < 45 % Reopen Defects < 15 | Defect metrics meet at least one of the following: # of Severity 1 = 1 to 5 # of Severity 2 = 1 to 5 Avg. # Days to Close Sev 1 and Sev 2 Defects => 45 and =< 90 % Reopen => 15 and =< 24 | Defect metrics meet at least one of the following: # of Severity 1 > 5 # of Severity 2 > 5 Avg. # Days to Close Sev 1 and Sev 2 Defects >90 % Reopen >24

## Slide 12
Questions?