|  | Texas Nodal Market Implementation Program Status Report Week Ending Oct. 31, 2008 |
| --- | --- |
| CONTENTS |  |

PROGRAM STATUS	1

CORE NODAL PROJECTS	3

Network Model Management System (NMMS)	3

Energy Management System (EMS)	5

Market Management System (MMS)	7

Outage Scheduler (OS)	10

Congestion Revenue Rights (CRR)	12

Commercial Systems (COMS)	14

Early Delivery Systems (EDS)	17

OTHER PROJECT UPDATES	18

Systems Integration	18

APPENDIX	21

Staffing Trends	21

Quality Center Dashboard (posted on Nodal website)	21

Nodal Org Chart	21

| # PROGRAM STATUS |  |
| --- | --- |
| Health Indicators |  |
| Overall; Red; Resources; Amber. Schedule; Red; Risks; Amber. Budget; Red; Issues; Amber. Scope; Amber; QC; Red. |
| Highlights |  |
| Defect update The number of severity 1 and 2 active defects has remained relatively constant. The number of severity 3 active defects has increased by only 5% over the last 60 days; however we expect a significant increase as more components enter i-Test. The defect turnaround time for all vendors has risen in the last 3 months. Staffing update Nodal staffing changes: See Appendix for link to org chart - Adjusted nodal organization to reflect reassignments of work for EDS, ERT and INT to Matt Mereness, Murray Nixon and Mike Bianco. Staffing Trends See Appendix Budget Actual spend through Sept. 2008 is $299.3 million. Budgeted spend was $290.8 million, causing a variance of $(8.5) million |  |
| Milestones Planned for Next 30 Days |  |
| See individual projects |  |
| Activities Behind Schedule |  |
| - Nodal business process work is not as far along as originally thought; currently in process of developing the project schedule – Nodal PM assigned, Murray Nixon, who is determining scope, developing a budget, and staffing the team. This will be removed after this week. - Information Life Cycle Management (ILM) strategy for ERCOT has not been developed. This could likely impact nodal go-live date if this is not in place in time to accommodate the data needs for Nodal. Meeting scheduled on Oct. 15 to better understand needs and impact. ERCOT is meeting to assign a PM and possibly develop an RFP for this work. The PMO will continue to monitor progress to ensure that there is no impact. This will be removed after this week. - No tasks on the program critical path are behind schedule this week. |  |
| Risks or Issues |  |
| Description | Status |
| (Risk: Oct. 17) ILM strategy for ERCOT is behind schedule. Without this in place and executed, the nodal program go-live date could be delayed because of insufficient storage. | Need to assign a PM to manage this project, working closely with the business owners and IT. (See above – will be removed after this week) |
| (Risk: Oct. 17) Nodal business process work is incomplete. Without the business process foundation in place, requirements traceability, functional testing, nodal procedures, and training work cannot be completed. | Murray Nixon has been assigned as the PM to lead this effort. Staffing needs and an associated budget have been developed. Development of a project schedule is in progress. (See above – will be removed after this week) |
| Traceability between protocols and requirements is largely manual; not all requirements documentation has been updated to reflect NPRR changes and re-approved by TPTF | Requirements review in process to review all project requirements documentation, approvals, incorporation of NPRRs; presented findings to TPTF on Oct. 27; ERCOT will schedule project-level documentation reviews with TPTF for comments and approval |

# CORE NODAL PROJECTS

| ## Network Model Management System (NMMS) |  |
| --- | --- |
| Health Indicators |  |
| Overall; Red; Resources; Green. Schedule; Red; Risks; Green. Budget; Red; Issues; Green. Scope; Red; QC; Amber. |
| Highlights |  |
| - NMMS Validation Rules Set 1 Implemented and Error Resolved - Implemented final business into RARF Audit Reporting process - Developed Zonal Seed Model Checklist - Established NMMS Data Quality Assurance process; developing task sheets for each major model component - Finalized MP10 database (resource mapping to resource nodes and resource mapping to EPS meter) for incorporation into the Nodal model following zonal seed |  |
| Milestones Planned for Next 30 Days |  |
| - Nov 13 90% Quality Achieved for RARF Data |  |
| Activities Behind Schedule |  |
| None |  |
| Top 3-5 Risks or Issues |  |
| Description | Status |
| (Oct. 23) Two Loads Acting As Resources (LAARs) have not submitted RARFs, but are in the zonal model and therefore are not modeled in the nodal model | Client services has contacted both market participants and working with them to submit their RARFs. Meetings on conducted on Oct. 28 to step through RARF data submittal process |
| (Aug. 1) Topology Processor performance is not acceptable to CRR business owner | Oct. 28 test resulted in process time at ERCOT of 36 minutes and processing time of 38 minutes at Siemens. (CRR business needs are 30 minutes). Differences in output log are being analyzed by Siemens. |

| Remaining Software Releases (Siemens) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Release Number | Description | FAT Start |  | FAT Complete |  |
|  |  | Sched | Actual | Sched | Actual |
| NMMS 5 | Production Model to support business processes Auto Model Scheduler integration MIS posting folder structure Historical models and historical NOMCR tracking Project Tracking Coordinator (PTC) screens to support Planning Model Change Request (PMCR) linkage Canned reports (8) | Oct 06 08 | Oct 17 08 |  |  |
| NMMS 6 | PTC screens and functionality for Model Coordinator screens Outage clarification Name service redesign As Built report | Jan 09 09 |  |  |  |
| NMMS 7 | Auto Model Scheduler validation | Mar 20 09 |  |  |  |

| ## Energy Management System (EMS) |  |
| --- | --- |
| Health Indicators |  |
| Overall; Red; Resources; Green. Schedule; Red; Risks; Green. Budget; Red; Issues; Amber. Scope; Amber; QC; Amber. |
| Highlights |  |
| - CIM Importer Functional Acceptance Test (FAT) on data model 1.20 is in progress and it is on schedule to complete earlier than Nov. 17 - Continue with FAT for the Outage Evaluation (OE), Voltage Support (VSS), Interfaces, Displays, etc. - CCB approved the change requests for Market Analyst Interface (listed as risk by Operations) and EPS meters. The change request for the CRR Map is still in progress. |  |
| Milestones Planned for Next 30 Days |  |
| Nov 17 –EMS CIM Importer FAT completed (aggressive internal team target is Oct. 31 and it may exit FAT early next week) Nov 14 –EMS FAT Release 5.1.5.x (EMS 5 OE/VSS) completed |  |
| Activities Behind Schedule |  |
| EMS Release 5.1.5.x (FAT release for Outage Evaluation, voltage support, interfaces, etc.) has slipped with the late closure of severity 1 defects and the need to rerun the full test suite with the goal to finish by Nov. 14 |  |
| Top 3-5 Risks or Issues |  |
| Description | Status |
| (Issue: Oct. 20) EMS CIM Importer Performance | The time to complete the business process to import a new model is longer than expected. Project team is working with the vendor to improve the through-put time. Plan to retest performance as part of a future FAT for the EMS CIM Importer on data model 1.21 |

| Remaining Software Releases (AREVA/ERCOT) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Release Number | Description | FAT Start |  | FAT Complete |  |
|  |  | Sched | Actual | Sched | Actual |
| 5.1.5.x | - Outage Evaluation functionality permits the Outage Scheduler to evaluate the impact of a requested outage - Voltage support function permits the operators to address voltages issues and recommend corrective action - Interfaces to MMS, CSI, EDW and CDR | July 29 08 | July 29 08 | Nov 14 08 |  |
| 5.1.6.x | Habitat 5.7 upgrade from beta to the release version | Nov 24 08 |  | Dec 12 08 |  |
| 5.1.7.x | EMS CIM XML importer which receives data, model and configuration changes from the central master data source (NMMS) and updates the EMS applications databases | Oct 13 08 | Oct 14 08 | Nov 17 08 |  |

| ## Market Management System (MMS) |  |
| --- | --- |
| Health Indicators |  |
| Overall; Red; Resources; Green. Schedule; Red; Risks; Amber. Budget; Red; Issues; Green. Scope; Amber; QC; Amber. |
| Highlights |  |
| - MMS4 patch 4 FAT testing completed on schedule - Real time process presented to TPTF on schedule - Market Manager - Bids and Offers front-end/back-end development in progress - Market Manager - All “query” front-end development work in progress - Market Manager - Resource-Specific Submissions front-end development in progress - All approved post baseline 2 changes have been addressed with the vendor and included in the new MMS schedule; - MMS synced with OS |  |
| Milestones Planned for Next 30 Days |  |
| Nov. 04 – Market Manager Bids and Offers migrated to FAT/i-Test Nov. 05 – Four internal development activities (e.g., eTAG, DB procedures, MI indexes) completed Nov. 12 – RUC operating procedures v1 procedure completed (moved from Oct. 31 to Dec. 15 to Nov. 12 per TPTF direction) Nov. 18 – Bids & offers FAT completed Nov. 21 – MMS4 patch 6 delivered by ABB Nov. 24 – Adjustment period v1 procedure completed Nov. 25 – MMS4 patch 5 FAT completed Nov. 25 – Resource Specific Submissions released to FAT/i-Test (smoke test) |  |
| Activities Behind Schedule |  |
| None |  |
| Top 3-5 Risks or Issues |  |
| Description | Status |
| (Risk: Oct. 17) Availability of EIP web services for the new MMS market manager user interface (MM UI) | V1.17 of the EIP web services specification for the MMS UI is targeted for i-Test release in mid-December. Testing of the Market Manager for bids and offers, resource specific submissions, schedules and self-arranged AS will be delayed until the web services is made available in the i-Test environment. |

| Remaining MMS Software Releases (ABB delivered) |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Release Number | Description |  | FAT Start |  |  | FAT Complete |  |
|  |  |  | Sched | Actual |  | Sched | Actual |
| MMS4 P3 | - Self-committed resources in DAM; resource parameters API - Load Resource modeling (SIG005); Private Use Networks modeling (SIG002); Non-Modeled generation modeling (SIG008); Block Load Transfer modeling (SIG007); Partial implementation of combined cycle configuration modeling mapping of configuration to Primary/Alternate Physical generators (SIG paper) - Combined Cycle logical resource nodes (ERCOT action) - Verification of monitor/enforced flag for all branches in CIM schema (mandatory requirement) - 120+ bug fixes |  | Jul 28 08 | Jul 28 08 |  | Sep 29 08 | Sep 29 08 |
| MMS4 P 4 | - Partial implementation of NPRR102, NPRR128 and JBOSS upgrade - Bug fixes |  | Aug 31 08 | Aug 27 08 |  | Oct 28 08 | Oct 28 08 |
| MMS4 P 5 | - Delivery added to ensure progress is made while waiting for validated and synchronized CIM XML file from NMMS - S&B defects, interface updates and additional workflow development and testing based on the most recent CIM schema and corresponding CIM XML test data set |  | Sep 30 08 | Sep 30 08 |  | Nov 25 08 |  |
| MMS4 P6 | Content is being discussed with vendor |  | Nov 14 08 Nov 21 08 |  |  | Jan 06 09 Jan 13 09 |  |
| MMS4 P7 | Last scheduled release to MMS4; Content is being discussed with vendor |  | Jan 06 09 Jan 09 09 |  |  | Feb 17 09 Feb 20 09 |  |
| MMS5 | - Last scheduled release of functionality, target delivery to ERCOT is TBD; triggered off an NMMS-delivered validated and synchronized CIM XML file ready for consumption by downstream systems - CIM XML import processing and end-to-end testing - Bug fixes - Remaining NPRR as approved (e.g., NPRR102, NPRR113), SIG paper changes (e.g., rounding) and software implementation changes based on testing (e.g., performance improvements, startup cost eligibility, SASM constraint modeling) |  |  |  |  |  |  |
| Remaining MMS “Market Manager” UI (MMS MM UI) Software Releases (ERCOT delivered) |  |  |  |  |  |  |  |
| Release Number |  | Description | FAT Start |  | FAT Complete |  |  |
|  |  |  | Sched | Actual | Sched |  | Actual |
| MMS MM UI |  | Bids and offers FAT | Nov 05 08 |  | Nov 18 08 |  |  |
| MMS MM UI |  | Resource specific submissions FAT | Dec 01 08 |  | Dec 12 08 |  |  |
| MMS MM UI |  | Schedules FAT | Dec 11 08 |  | Jan 07 09 |  |  |
| MMS MM UI |  | Self-arranged AS FAT | Dec 18 08 |  | Jan 14 09 |  |  |
| MMS MM UI |  | Trades FAT | Jan 19 09 |  | Jan 30 09 |  |  |
| MMS MM UI |  | Awards FAT | Jan 27 09 |  | Feb 09 09 |  |  |
| MMS MM UI |  | Notices FAT | Feb 04 09 |  | Feb 17 09 |  |  |
| MMS MM UI |  | Verbal dispatch instructions (VDI) FAT | Feb 17 09 |  | Mar 02 09 |  |  |

| ## Outage Scheduler (OS) |  |
| --- | --- |
| Health Indicators |  |
| Overall; Red; Resources; Green. Schedule; Red; Risks; Amber. Budget; Red; Issues; Amber. Scope; Green; QC; Red. |
| Highlights |  |
| - OS FAT/Regression test continues (91% complete overall, 74% pass rating, 0 sev. 1’s, 25 sev. 2’s) - OSUI Opportunity Outage (Transmission/Resource) in progress - Registration and equipment list synced with MMS - Transition for new PM in progress. |  |
| Milestones Planned for Next 30 Days |  |
| Nov. 4 – OS 2.0.13.0 FAT/regression test completed Nov. 4 – OS source environment delivered for EDW replication Nov. 21 – OS 2.1.0.0 patch received from ABB delayed from Nov. 19 (Due to ABB’s decision to bundle with MMS release) Nov. 25 – OSUI Opportunity Outages development and migration to FAT/i-Test completed |  |
| Activities Behind Schedule |  |
| None |  |
| Top 3-5 Risks or Issues |  |
| Description | Status |
| (Risk: Oct. 3) Core OS | Market is issuing request to allow RE/QSE to submit outages against transmission equipment they own. A draft SCR is being issued to TPTF for review. Will alert vendor of a potential change once the SCR has been reviewed and approved by TPTF. |
| (Risk: Oct. 17) availability of EIP web services for the new OS user interface (OS UI) | V1.17 of the EIP web services specification for the OS UI is targeted for i-Test release in mid-December. Testing of the Outage Scheduler for transmission and resource outage submissions, queries and other features will be delayed until the web services is made available in the i-Test environment. |

| Remaining Software Releases (ABB/Internal) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Release Number | Description | FAT Start |  | FAT Complete |  |
|  |  | Sched | Actual | Sched | Actual |
| 2.0.13.0 | OS Full FAT regression test | Aug 08 08 | Aug 05 08 | Nov 04 08 |  |
| 2.1.0.0 | OS FAT/Regression Installation and Test | Nov 19 08 Nov 21 08 |  | Jan 08 09 Jan 09 09 |  |
| OS User Interface |  |  |  |  |  |
|  | Base UI Testing | Dec 01 08 |  | Jan 09 09 |  |
|  | - OS Feature Pack 1 - Group Outages - Opportunity Outages - Warnings | Jan 19 09 |  | Feb 18 09 |  |
|  | - OS Feature Pack 2 - Summary Enhancements - Copy/Print/Export - Split Screen - Client-side Validation | Feb 27 09 |  | Mar 19 09 |  |

| ## Congestion Revenue Rights (CRR) |  |
| --- | --- |
| Health Indicators |  |
| Overall; Red; Resources; Green. Schedule; Red; Risks; Green. Budget; Red; Issues; Green. Scope; Green; QC; Amber. |
| Highlights |  |
| - Continued testing/analysis in CRR staging tables and Nexant code. Four new defects found. - Met with EIP and MMS re: MCFRI allocation in DAM - CMM End-to-End Business Process meeting – CRR and Credit - TCR to CRR Transition Plan presented to TPTF - NPRR 154 passed on to MMS - Updated CRR project documentation as required, and revised Nexant MUI Download Mapping Document - Met with Settlements to discuss the updates needed to settlements calculation for refunding TCR/PCRs upon Texas Nodal implementation. - Continued working on getting NOIEs ready for 2009 PCR allocation - Continued work on getting non-certified CRR AH certified - Revisited contractor needs for 2009 - Reviewed completion of VIO updates on DEV environment and verified that application is now working with proxy/policy configuration |  |
| Milestones Planned for Next 30 Days |  |
| Nov 6 –TAC approval for TCR to CRR Transition plan received Nov. 20 –CRR4 (at ERCOT) sign-off completed Nov. 21 – CRR4 Preparation for Migration to i-Test completed |  |
| Activities Behind Schedule |  |
| TAC approval for the TCR to CRR Transition Plan will not occur on Nov. 6 based on comments received at the Oct. 28 TPTF meeting. |  |
| Top 3-5 Risks or Issues |  |
| Description | Status |

| Remaining Software Releases (Nexant) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Release Number | Description | FAT Start |  | FAT Complete |  |
|  |  | Sched | Actual | Sched | Actual |
| 1.07 | Patch for identified defects in release 1.06 | Oct 31 08 |  |  |  |

| ## Commercial Systems (COMS) |  |
| --- | --- |
| Health Indicators |  |
| Overall; Red; Resources; Amber. Schedule; Red; Risks; Green. Budget; Red; Issues; Green. Scope; Amber; QC; Amber. |
| Highlights |  |
| S&B - Completed FAT Testing – All Core Lodestar Settlements and Billing in p-Test. Ready for migration to IR3 - Completed FAT Testing - Data Aggregation in p-Test. Ready for migration to IR3 CSI and CMM - CSI 5.4 (NMMS, S/B Determinants) Ready for connectivity testing in IR3 - CSI 6.1 (CMM Interfaces) Ready for connectivity testing in IR3 Registration - REG4 Dispute2 FAT = 86%, INT = 53%, Regression = 8% CMM - Oct. 24 Release 4.1 Credit Scoring Training Demo Complete Internally |  |
| Milestones Planned for Next 30 Days |  |
| CSI S&B Oct 27 FAT Testing - Statements and Invoices p-Test (FAT) completed Oct 27 – Settlements and Billing ”Initial” Build p-Test (FAT) completed Oct 31 – S&B i-Test Environment Setup completed Oct 31 – Settlements and Billing Environment Setup completed Oct 31 – Settlements and Billing Migration Preparation completed (Initial S&B 5) Oct 31 – Data Aggregation i-Test Environment Setup completed Oct 31 – Appworx Migration Preparation completed (Appworx 1) Nov 10 – Settlement and Billing p-Test (FAT) completed (Final Build to i-Test) Nov 19 – Data Aggregation p-Test (FAT) completed CMM Oct 31 – CMM Requirement Details(Use Cases, technical specifications) Approved Internally Nov 11 – “As Built” Design for CMM Release 4.1 (Custom Management) Approved Internally |  |
| Activities Behind Schedule |  |
| Settlements and Billing p-Test (FAT) completed (Final Build to i-Test) - This date is changing from Oct. 27 to Nov. 10 to accommodate ongoing FAT testing with additional data, however it does not impact the overall schedule because S&B has been approved for release to i-Test and will run in parallel with IR3 Data Aggregation p-Test (FAT) completed (Final Build to i-Test) - Baselined date of Nov. 19 is changing to Dec. 19. Need to verify 15 day baseline runs which require more manual work than previously planned and require business validation tool updates. This does not impact the schedule as Data Aggregation has been approved for release to i-Test and will run in parallel with IR3. |  |
| Top 3-5 Risks or Issues For COMS |  |
| Description | Status |
| (Risk: Aug. 1) Data synchronization for integrated testing | Defined business objectives for executing IR3.0 and assessed data synchronization approach. Data czar to work with INT team to define baseline data in the IR bucket list. |
| (Issue: Aug. 1) Data requirements expectations issues encountered during testing integrated interfaces from Registration | Ongoing meetings with teams representing other systems. Documenting differences and adding to list for change requests with estimates for impact assessment. |

| Remaining Software Releases (Internal) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Release Number | Description | i-Test Start |  | i-Test Complete |  |
|  |  | Sched | Actual | Sched | Actual |
| Registration Phase 4 / Disputes Phase 2 | - COMS REG 4/DISP 2: Calendar for Dispute Calculations - COMS REG 4/DISP 2: Bulk Upload process for RE/JOU creation - COMS REG 4/DISP 2: Deferred Phase 1, Phase 2, Phase 3 – High severity defects - COMS REG 4/DISP 2: Invoice Disputes - COMS REG 4/DISP 2: Siebel Interface for Dispute API Integration - COMS REG 4/DISP 2: Siebel To Lodestar (Reg SNB) interface replacement. | Aug 27 08 | Aug 27 08 | Dec 06 08 |  |
| Registration Phase 5 / Disputes Phase 3 | - COMS REG 5/DISP 3: Siebel Refactoring Changes for MMS Integration - COMS REG 5/DISP 3: Siebel Refactoring Changes for MPIM Role Configuration for Disputes API - COMS REG 5/DISP 3: Siebel Refactoring Changes for Integration-FINAL delivery phase of Registration - COMS REG 5/DISP 3: Changes to Push Contacts to MPIM from Siebel (no more dual entry) - COMS REG 5/DISP 3: Additional Refactoring Change needs for Integration with Synch Systems - Defects for Rework - COMS REG 5/DISP 3: Submit Refactoring Business Requirements Document for Approval | Jan 21 09 |  | Feb 17 09 |  |
| S/B Core | - Lodestar Bundle for Settlement and Invoicing of DAM, RTM, RUC | Oct 31 08 |  | Dec 10 08 |  |
| Data Agg Core | - Lodestar Bundle for Data Aggregation Re-Write (Initial) | Oct 31 08 |  | Dec 10 08 |  |
| Appworx | - Appworx Bundle for Nodal and Zonal Optimization | Oct 31 08 |  |  |  |
| CSI5.4 | - MMS4, Outbound Interfaces | Oct 17 08 |  |  |  |
| CSI5.5 | - MMS5 Initial, Remaining Determinants | Dec 19 08 |  |  |  |
| CSI6.1 | - CMM – DAM, RTM, Determinants | Oct 17 08 |  |  |  |
| CSI6.3 | - CMM – CRR UDAA, Remaining Determinants, CMM Loaders | Dec 19 08 |  |  |  |
| CSI7.0 | - S&B/CMM Long Day-Short Day | Mar 26 09 |  |  |  |
| S/B Source Reports | - CODIA, S&B, WCS, Data Agg Reports from Source Systems (Lodestar and Siebel) | Feb 17 09 |  |  |  |
| CMM4.1 | - CMM - 4.1 External Reports - CMM - 4.1 Credit Exposure Component Adjustment - CMM - 4.1 Credit Scoring - CMM - 4.1 ACL Screen and Adjustment - CMM - 4.1 Bilateral Trade | Dec 04 08 |  |  |  |
| CMM4.2 | - CMM - 4.2 Bug Fixes - CMM - 4.2 Run Exposure Calc - CMM - 4.2 Request Collateral | Feb 04 09 |  |  |  |
| CMM4.3 | - Bug Fix | Mar 04 09 |  |  |  |
| FTGUI | - Internal Financial Transfer GUI |  |  |  |  |

| ## Early Delivery Systems (EDS) |  |
| --- | --- |
| Health Indicators |  |
| Overall; Red; Resources; Amber. Schedule; Red; Risks; Amber. Budget; Red; Issues; Amber. Scope; Green; QC; N/A. |
| Highlights |  |
| Focus Input Testing (FIT) this week reflected the importance of continuing ERCOT and market telemetry testing and support. After a 6-week break from FIT activities, there was decay in the quality of telemetry data and performance of the State Estimator (final numbers still being compiled). The next FIT iteration is scheduled for Nov 4-6, 2008. Ongoing status is summarized below: - Wind generation resources (WGRs) sending 65% valid meteorological data (vs. 30% 4 weeks ago). Still targeting to be at 100% by Oct. 31. - Unobservable buses with Load: 21 out of ~5000 (vs. 41 three weeks ago). - QSE ICCP Point Issues – Status Points: 4 (vs. 91 last month), Analog: 52 (vs. 71 last month), Ownership disputes: 0 (vs. 170 last month) - TSP ICCP Issues – Status Points: 528 (vs. 1,208 last month), Analog: 454 (vs. 986 last month), Ownership disputes: 0 (vs. 274 last month) |  |
| Milestones Planned for Next 30 Days |  |
| - Oct. 31 – FIT results published - Nov. 2 – FIT Cycle 2 began (ongoing activity through Jan 23, 2009) - Nov. 5 – Measurement of MP21- Wind Meteorological telemetry began - Dec. 1 – Nodal implementation of the System Operations Test Environment (SOTE), which is part of the Market Operation (MOTE) project, completed. |  |
| Activities Behind Schedule |  |
| - No current activities behind schedule that potentially impact the critical path of the new schedule. - Telemetry and State Estimator activities below being worked in coordination with ongoing FIT testing: - Resolution of unobservable buses - Meeting TAC-approved State Estimator criteria - Status of meteorological telemetry data to support AWS TrueWind forecasting |  |
| Top 3-5 Risks or Issues |  |
| Description | Status |
| (Risk: Oct. 10) Inability to keep MPs engaged in FIT after integrated master schedule is released. This would adversely impact improvements made in telemetry and state estimator. | Escalating issue- at least one MP looking to discontinue EDS testing support. |

# OTHER PROJECT UPDATES

| ## Systems Integration |  |
| --- | --- |
| Health Indicators |  |
| Overall; Red; Resources; Red. Schedule; Red; Risks; Green. Budget; Red; Issues; Amber. Scope; Green; Quality Control; Amber. |
| Highlights |  |
| Overall - Announced new Systems Integration Team structure this week. Team Management transitions underway. - Working on updating the Integrated Release Plan (Bucket List) against the new Nodal schedule baseline. - IR 3 deployments and testing are on track. All EIP interfaces have been deployed on schedule for IR 3. - IR 4 test plan and test case development is underway and on track. Integrated Release 3 Interface Readiness; Int Test Plng (Next Level); Integration Test Execution; Comments. Interfaces; Dplyd i-Test; Test Cases; Test Scrpts; L1; L2; L3; L4; L5. MP to MMS (EWS1.16); ; ; ; ; ; ; ; Resource skill set limitation; working with MMS Team to complete.. Platts to MMS; ; ; ; ; ; . CRR to MMS; ; ; ; ; . CMM to MMS; ; ; ; ; . Reg to MMS; ; ; ; ; ; Siebel environment build/access issues; expect to resolve by 11/10.. Reg to CMM; ; ; ; ; ; Siebel environment build/access issues; expect to resolve by 11/10.. Reg to CRR; ; ; ; ; ; Siebel environment build/access issues; expect to resolve by 11/10.. REG to S&B; ; ; ; ; ; ; . CMM to CRR (ACL); ; ; ; ; . CRR to CMM (ACL); ; ; ; ; . CMM to CRR (BT); ; ; ; ; . CRR to CMM (BT); ; ; ; ; . S&B to MMS (CF); ; ; ; ; . S&B to MMS (LRS); ; ; ; ; . S&B to MMS (VC); ; ; ; ; . S&B to MMS (RMR); ; ; ; ; . MMS to CSI5.4 (only); ; ; ; ; . Deployment into i-Test to start on Nov. 10. MP to OS (EWS1.16); ; . Platts to S&B; ; . S&B to CRR; ; . MP to Reg (EWS1.16); ; . CMM to Reg; ; . Legend; ; Completed; ; In progress; ; In jeopardy; Blank white; Not started; Blank grey; Not scheduled for this release. Release 4 EIP and INT Status Tracking matrix to be finalized next week. Operational Readiness Test (ORT) Planning (Security, Performance, Failover, Monitoring, DST) - Operational Readiness scope review planned for ERCOT IT Stakeholders next week. - Meetings with security architects and project teams to be scheduled the second week of November for follow up on compliance to ERCOT security requirements. - Application-level monitoring template in process. Plan to circulate to the project teams for review and completion next week. - Working on aligning ORT milestones with integrated schedule. - Working through non-functional requirement review and gap analysis. Plan to complete next week. |
| Milestones Planned for Next 30 Days |  |
| - Dec. 1 IR 3 completed (at risk of slipping due to product release dates on new schedule baseline). - Dec. 1 IR 4 deployments started (at risk of slipping due to product release dates on new schedule baseline). |  |
| Activities Behind Schedule |  |
| Integrated Release 3 - EMS deployment in i-Test (proposing to slip to IR 4) - Siebel environment build and access issues Integrated Release 4 - Integration Test Cases and Scripts – resource skill set limitation; reaching out to Project Teams to support Level 3 and 4 test planning. |  |
| Top 3-5 Risks or Issues |  |
| Description | Status |
| (Risk: Oct. 3) Integration Release Definition/Bucket List continues to change. Impact: Integration Testing Planning, Preparation and Execution are delayed | Working with PMO to align with Integrated Program Schedule. Reviews and meetings continue to refine the list. |
| (Risk: Sept. 26) Scope changes, particularly to include business processing within the integration layer Impact: Creates an unstable architecture and failure of whole system | Monitoring all change requests for changes such as these and so far all of the business rule implementations have been mapped into the correct systems. |
| (Risk: Sept. 26) Integration layer performance is inadequate. Impact: System fails to function as protocols require. | - Regular performance and other non-functional observations being made within the integration layer. - Introducing new chunking component to support heterogeneous and large payloads. - Proofs of Concept produced to verify optimal implementation have been completed for message sizes - Oct 16: Testing in development environments has shown optimum design parameters but not yet tested in i-Test |
| (Risk: Oct. 17) Non-functional requirements will not be readily available impacting both INT and project resources to establish requirements for the Operational Readiness Testing activities. | Working with projects and PMO to define the correct process and evaluation methodology to collect and define traceability for these requirements. |

| Remaining Integrated Software Releases (Internal) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Release Number | Description | i-Test Start |  | i-Test Complete |  |
|  |  | Sched | Actual | Sched | Actual |
| IR 3 | Primary objectives: Run Market Management System daily with key Integration inputs Initial Market Management System to Lodestar testing | Oct 13 08 | Oct 09 08 | Dec 01 08 |  |
| IR 4 | IR4 TC1 – Installation Window | Dec 01 08 |  | Dec 31 08 |  |
|  | IR4 TC1 – Testing Window | Jan 05 09 |  | Feb 06 09 |  |
|  | IR4 TC2 – Installation Window | Feb 09 09 |  | Feb 14 09 |  |
|  | IR4 TC3 – Installation Window | Feb 16 09 |  | Mar 31 09 |  |
|  | IR4 TC2 – Testing Window | TBD |  | TBD |  |
|  | IR4 TC3 – Testing Window | TBD |  | TBD |  |
| IR 5 | Details TBD |  |  |  |  |

# APPENDIX

## Staffing Trends

## Quality Center Dashboard (posted on Nodal website)

http://nodal.ercot.com/readiness/qc/index.html

## Nodal Org Chart

http://cpwp004j/sites/pmo/default.aspx

| Health Indicator Measures |  |  |  |
| --- | --- | --- | --- |
| Metric | Green | Amber | Red |
| Overall | Both core indicators are green | At least one core indicator is amber, but none are red | At least one core indicator is red |
| Schedule | All activities on the critical path are complete, or are expected to be complete, on or ahead of the planned dates | No dates have been missed, but one or more critical path activities is forecasted to complete late | At least one critical path deliverable has missed its due date. Project implementation date is in jeopardy |
| Budget (hrs) | Project forecasted to complete within the baselined hours | Project forecasted to complete up to 5% over the baselined hours | Project forecasted to complete more than 5% over the baselined hours |
| Scope | All requirements approved; no unplanned scope changes | Pending approvals for requirements; no unplanned scope changes | Unapproved requirements and/or unplanned scope changes |
| Resources | All key resource positions are filled and no schedule delays are expected. | One or two key positions are not staffed and the schedule may be adversely impacted. | More than two key positions are not staffed and the schedule will be impacted. |
| Risk | All project risks have a Risk Score =< 4 | At least one project risk has a Risk Score => 5 and =< 8 | At least one project risk has an Risk Score => 9 |
| Issues | All issues are being resolved by the required due dates | Some issues are remaining open past the required due dates but none are of “critical” priority (Impact = 3 or 4) | At least one “critical” priority issue (Impact = 3 or 4) is open past the due date |
| Quality Control | Defect metrics meet all of the following: # of Severity 1 = 0 # of Severity 2 = 0 Avg. #. Days to Close Sev 1 and Sev 2 Defects < 45 % Reopen Defects < 15 | Defect metrics meet at least one of the following: # of Severity 1 = 1 to 5 # of Severity 2 = 1 to 5 Avg. # Days to Close Sev 1 and Sev 2 Defects => 45 and =< 90 % Reopen => 15 and =< 24 | Defect metrics meet at least one of the following: # of Severity 1 > 5 # of Severity 2 > 5 Avg. # Days to Close Sev 1 and Sev 2 Defects >90 % Reopen >24 |