|  |  |  |  | System Planning Division |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | Monthly Status Report to Reliability and Operations Subcommittee for October 2008 |  |  |
|  |  | Report Highlights |  |  |  |  |  |  |
| Item |  |  |  |  |  |  |  |  |
| 1. | - ERCOT is currently tracking 260 active generation interconnection requests totaling over 110,000 MW. This includes almost 54,000 MW of wind generation. - 211 MW of new wind generation began commercial operation bringing the currently installed total of wind power capacity to 6,234 MW. |  |  |  |  |  |  |  |
| 2. | - Regional Planning is currently reviewing proposed transmission improvements with a total cost of $470.9 Million - Transmission Projects approved in 2008 to date total $255 Million - All projects (in engineering, routing, licensing and construction) totals approximately $3.8 Billion - Transmission Projects energized in 2008 total about $375 Million - Oncor’s Nacogdoches to Lufkin 345 kV Line Project received ERCOT Board recommendation this month |  |  |  |  |  |  |  |

Table of Contents

1.	Generation Interconnection	1

1.1.	New Generation Beginning Commercial Operations	1

1.2.	New Signed Interconnection Agreements	1

1.3.	Summary of Active Generation Interconnection Requests	1

1.4.	Potential Future Generation Interconnections	2

2.	Regional Planning Group Project Reviews	4

3.	Other Notable Activities	5

# 1.	Generation Interconnection

Additional information regarding detailed generation interconnection and impact studies is contained in the “Generation Project Interconnection Information” folder in the “Operations and System Planning” area on the ERCOT website:  http://planning.ercot.com/login/login.

## New Generation Beginning Commercial Operations

# Wolf Ridge Wind Farm (07INR0034) in Cooke County for 113 MW

# South Trent Wind Farm (07INR0029) in Taylor County for 98 MW

## The total installed wind capacity in ERCOT is now 6,234 MW.

## Summary of Active Generation Interconnection Requests

| GENERATION INTERCONNECTION REQUESTS CURRENTLY BEING PROCESSED |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Currently tracking 260 active generation interconnection or change requests As of October 31, 2008 |  |  |  |  |  |
|  |  | North | South | West | Total |
| Security Screening Study |  | 3 | 11 | 14 | 28 |
| SSS Completed |  | 5 | 15 | 26 | 46 |
| Full Interconnect Study |  | 36 | 28 | 80 | 144 |
| FIS Completed |  | 1 | 9 | 0 | 10 |
| Interconnect Agreement Completed |  | 6 | 10 | 16 | 32 |
| Capacity for Grid, MW |  | 25,996 | 38,527 | 45,620 | 110,143 |
| Wind Capacity, MW |  | 2,047 | 10,395 | 41,437 | 53,879 |

| Fuel Type | Non-Public (MW) | Public (MW) | Grand Total (MW) |
| --- | --- | --- | --- |
| Gas-CC | 24,760 | 5,519 | 30,279 |
| Gas-CT | 1,050 | 505 | 1,555 |
| Nuclear | 3,200 | 9,186 | 12,386 |
| Coal | 5,375 | 4,131 | 9,506 |
| Wind | 45,117 | 8,762 | 53,879 |
| Solar | 863 | 0 | 863 |
| Biomass | 50 | 145 | 195 |
| Other | 1,480 | 0 | 1,480 |
| Grand Total | 81,895 | 28,248 | 110,143 |

## Potential Future Generation Interconnections

The table below summarizes the publicly known potential future generation projects for the ERCOT region.  (IA=Interconnect Agreement, PL=Public Letter, XX= cancelled)

| Future Generation Interconnections (Public Projects) as of October 31, 2008 |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| INR | SiteName | Status | County | Region | COD | Fuel | MW For Grid | Change from Last Report |
| 08INR0050 | Victoria Power Station | IA | Victoria | South | Nov-08 | Gas-CC | 332 | Date |
| 06INR0022a | Penascal Wind Farm 1 | IA | Kenedy | South | Nov-08 | Wind | 202 | Date |
| 05INR0015a | Gulf Wind 1 | IA | Kenedy | South | Nov-08 | Wind | 283 | Date |
| 07INR0045b | Inadale | IA | Scurry | West | Nov-08 | Wind | 197 |  |
| 08INR0037 | Panther Creek 2 | IA | Howard | West | Nov-08 | Wind | 115 |  |
| 07INR0045a | Pyron Wind Farm | IA | Scurry | West | Nov-08 | Wind | 249 |  |
| 07INR0011 | Turkey Track Energy Center | IA | Nolan | West | Nov-08 | Wind | 170 | Date |
| 08INR0053 | Elbow Creek Wind Project | IA | Howard | West | Nov-08 | Wind | 117 | Date |
| 07INR0037 | Bull Creek Wind Plant | IA | Borden | West | Nov-08 | Wind | 180 | Date |
| 09INR0026a | Sterling Energy Center | PL | Sterling | West | Dec-08 | Wind | 200 |  |
| 08INR0059 | Gray Wind Project | PL | Borden | West | Dec-08 | Wind | 141 |  |
| 08INR0025 | Pistol Hill Energy Center | PL | Ector | West | Dec-08 | Wind | 300 |  |
| 07INR0005 | Notrees-1 | IA | Ector | West | Dec-08 | Wind | 151 |  |
| 04INR0011e | Hackberry Wind Farm | IA | Shackelford | West | Dec-08 | Wind | 165 |  |
| 08INR0065 | Buffalo Gap 4 and 5 | PL | Nolan | West | Mar-09 | Wind | 465 |  |
| 08INR0046 | Bosque Expansion | IA | Bosque | North | Mar-09 | Gas-CC | 255 |  |
| 07INR0036 | Coyote Run Windfarm | IA | Borden | West | Mar-09 | Wind | 225 |  |
| 09INR0072 | Dansby3 | PL | Brazos | North | Apr-09 | Gas-CT | 48 |  |
| 07INR0028b | Goat Wind - phase 2 | IA | Sterling | West | Apr-09 | Wind | 70 |  |
| 07INR0027 | S Houston Green Power Exp | IA | Galveston | South | Apr-09 | Gas-CC | 244 | Date |
| 09INR0060 | Stephens Wind Farm | PL | Borden | West | May-09 | Wind | 141 |  |
| 08INR0040 | Lenorah Project | PL | Martin | West | May-09 | Wind | 350 |  |
| 08INR0012 | Papalote Creek Wind Farm | IA | San Patricio | South | May-09 | Wind | 180 |  |
| 09INR0036 | McAdoo Energy Center II | PL | Dickens | West | Jun-09 | Wind | 500 |  |
| 09INR0026 | Sterling Energy Center | PL | Sterling | West | Jun-09 | Wind | 300 |  |
| 08INR0035 | Cedar Bayou 4 | IA | Chambers | South | Jun-09 | Gas-CC | 539 |  |
| 09INR0027 | Winchester Power Park | IA | Fayette | South | Jul-09 | Gas-CT | 178 |  |
| 08INR0003 | Sandow 5 | IA | Milam | North | Jul-09 | Coal | 581 |  |
| 09INR0006a | Oak Grove SES 1 | IA | Robertson | North | Jul-09 | Coal | 855 |  |
| 08INR0033 | Lufkin | IA | Angelina | North | Sep-09 | Biomass | 45 |  |
| 05INR0015b | Gulf Wind 2 | PL | Kenedy | South | Sep-09 | Wind | 400 |  |
| 09INR0028 | V H Braunig 6 | PL | Bexar | South | Oct-09 | Gas-CT | 185 | Date |
| 08INR0018 | Gunsight Mountain | IA | Howard | West | Oct-09 | Wind | 120 |  |
| 09INR0015 | Comanche Peak Upgrade | PL | Somervell | North | Oct-09 | Nuclear | 86 |  |
| 09INR0045 | Sand Hill Peakers | PL | Travis | South | Nov-09 | Gas-CT | 94 |  |
| 09INR0039 | Nueces Bay 7 Repowering | IA | Nueces | South | Nov-09 | Gas-CC | 327 |  |
| 09INR0038 | Barney Davis 2 Repowering | IA | Nueces | South | Nov-09 | Gas-CC | 360 |  |
| 09INR0034 | Gatesville Wind Farm | PL | Coryell | North | Dec-09 | Wind | 200 |  |
| 08INR0038 | M Bar Wind | PL | Andrews | West | Dec-09 | Wind | 194 | Date |
| 09INR0006b | Oak Grove SES 2 | IA | Robertson | North | Jan-10 | Coal | 855 |  |
| 06INR0029 | Jackson Mountain | IA | Nolan | West | Jan-10 | Wind | 90 |  |
| 09INR0037 | Scurry County Wind III | PL | Scurry | West | Mar-10 | Wind | 350 |  |
| 06INR0006 | Cobisa-Greenville | PL | Hunt | North | May-10 | Gas-CC | 1,750 |  |
| 09INR0002 | J K Spruce 2 | IA | Bexar | South | Jun-10 | Coal | 750 |  |
| 05INR0015c | Gulf Wind 3 | PL | Kenedy | South | Sep-10 | Wind | 400 |  |
| 06INR0012b | Sherbino Mesa Wind Farm 2 | IA | Pecos | West | Oct-10 | Wind | 150 |  |
| 12INR0003 | Throckmorton Wind Farm | PL | Throckmorton | West | Dec-10 | Wind | 400 |  |
| 06INR0026 | Wild Horse Mountain | IA | Howard | West | Dec-10 | Wind | 120 |  |
| 10INR0020 | Panda Temple Power | PL | Bell | North | May-11 | Gas-CC | 1,092 |  |
| 10INR0010 | Jack County 2 | PL | Jack | North | Jun-11 | Gas-CC | 620 |  |
| 09INR0007 | Nacogdoches Project | PL | Nacogdoches | North | Apr-12 | Biomass | 100 |  |
| 07INR0004 | Pampa Energy Center | PL | Gray | West | May-12 | Coal | 165 |  |
| 09INR0024 | B&B Panhandle Wind | PL | Carson | West | Jun-12 | Wind | 1,001 |  |
| 09INR0001 | Sandy Creek 1 | IA | McLennan | North | Jun-12 | Coal | 925 |  |
| 12INR0004 | Fort Concho Wind Farm | PL | Tom Green | West | Jul-12 | Wind | 400 |  |
| 04INR0011b | Mesquite Wind Phase 4 | IA | Shackelford | West | Jun-13 | Wind | 136 |  |
| 04INR0011c | Cottonwood Wind | IA | Shackelford | West | Jun-13 | Wind | 100 |  |
| 11INR0011 | Victoria City Nuclear | PL | Victoria | South | Jan-15 | Nuclear | 3,200 |  |
| 15INR0008 | STP 3 and 4 | PL | Matagorda | South | Jan-15 | Nuclear | 2,700 |  |
| 15INR0002 | Comanche Peak 3 and 4 | PL | Somervel | North | Jan-15 | Nuclear | 3,200 |  |
|  |  |  |  |  |  |  | 28,248 |  |

# Regional Planning Group Project Reviews

# American Electric Power Service Corporation submitted a project to construct 2 new 138 kV substations, rebuild a 138 kV circuit, build  2 new 138 kV circuits, and install a new 138/69 kV autotransformer in the Abilene/San Angelo area.  The estimated cost of this project is $105.9 M.  This project is in ERCOT Independent Review.

# Luminant Energy submitted the Twin Butte – Kendall 345 kV double circuit line with series compensation.  It is a $327 million project comprised of 170 miles of 345 kV double circuits with both circuits in place, substation and breaker additions at Twin Butte and Kendall, and a 50% series compensation in each circuit.  The need for this project has been established by the PUC Docket 33672.  Determination of the builder of this project will be decided in PUC Docket 35665.  RPG Review can not continue.

# Luminant submitted a set of projects to reduce North to South Congestion.  It consists of several 138 kV line upgrades and series reactor installations.  The total cost for all projects is approximately $31 M. This project is in ERCOT Independent Review.

# AEPSC submitted a project to add a 345 kV Transmission Substation at the point in Haskell County where the Oklaunion to Mulberry Creek and Tonkawa to Graham 345 kV lines cross called Clear Crossing and construct a new 345 kV transmission circuit from the existing Oklaunion Substation to the Bowman Substation.  This project was a result of the 2007 Five-Year Plan.  Clear Crossing is projected to be in service by peak 2010 with a cost of $14 M.  The Oklaunion to Bowman 345 kV line is estimated to be in service by the end of 2011 with a cost of $ 71 M.  The need for the Oklaunion to Bowman part of the project has been established by the PUC Docket 33672.  Determination of the builder of this project will be decided in PUC Docket 35665.  RPG Review of this part of the project can not continue.  RPG review of the Clear Crossing part of this project is in ERCOT Independent Review.

# Oncor submitted a project to install an additional 300 MVar of dynamic reactive at Renner station.  The estimated cost of this project is $ 35 M with an in-service of 2010.  This project is in the Comment Period.

# Oncor submitted a project to relieve congestion related to new wind units in the Lamesa area.  The project will upgrade the Lamesa to Bluff Creek 138 kV line, rebuild the Bluff Creek to China Grove 138 kV line, rebuild the Lamesa to Ackerly Vealmoor 69 kV line to 138/69 kV double circuit, rebuild the Lamesa 138 kV switching station, build a new 138 kV Ackerly Vealmoor station, add second circuits to all rebuilt lines and include station upgrades at China Grove and Big Spring.  The cost of this project is $ 80.8 M.  This project will be reviewed to ensure that the improvements fit into the likely CREZ transmission solution for the area.  This project is in the Comment Period.

# Oncor submitted a project to add several 345 kV circuits to support the addition of Comanche Peak units 3 and 4 in 2015 at an estimated cost of $ 133 M.    These upgrades include a new 345 kV double circuit line with one circuit in place from Comanche to Whitney, a new 345 kV line from Comanche to Johnson Switch, a new circuit on existing structures from Johnson Switch to Everman, a new 345 kV double circuit with one circuit in place from Comanche to DeCordova, and a new 345 kV line on existing structures from Comanche to Parker Switch.  This project is in the Comment Period.

# Other Notable Activities

- All postings referred to below can be found at http://planning.ercot.com/login/login unless otherwise indicated.

- ERCOT TPIT report worksheets have been distributed to TO’s in preparation for receiving updated information for the November TPIT report.  All data is due to ERCOT no later than November 3, 2008.

- SSWG 2009 Data Set B cases were posted.

- ERCOT Regional Planning is continuing work on the 2013 case to be used for reliability analysis and RPG analysis.  The purpose of this effort is to extend the 2007 Five-Year plan from 2012 to 2013.  Several generation units were selected for generation unavailable studies in accordance with Operations Guide 5.1.4.  Reliability projects were added to eliminate all unserved energy encountered under the various generation unavailable scenarios.  This list of Reliability projects was sent to Transmission Owners for review with a respond-by of November 7, 2008.