## -- SO --
2009 Initiatives by CART
CART | Rank | Revised Position | Percent of 2009 Budget Needed | Project Name / Type | Original 2009 Budget | Original Budget Range | Revised 2009 Budget | Revised Budget Range | Reforecast Comments | Candidate Projects / Additional Details
SO | 1 | New | 100 | Reliability Assessment Tool | 0 | 0 | 150000 | $100k-$250k | Carry Over-Production Migration | Develop a reliability assessment tool to evaluate the reliability risk level of wind penetration in a quantitative way using probabilistic methods. This tool will assist system operators when maintaining adequate system reliability.
SO | 2 | New | 100 | Large Wind Power Production Ramp Forecasting | 0 | 0 | 135000 | $100k-$250k | Carry Over-Pre-Fat, FAT & migration to production. | Develop a large ramp forecast product and make it available for SO engineers and operators.
SO | 3 | Continue As Planned | 100 | Mid-Term Load Forecast Phase II | 0 |  | 30000 | <$50k | No Change | Integrated results from AREVA LF and alternate source and enable operator capability to select which Load Forecast will be used by EMS.
SO | 4 | Continue As Planned | 100 | Improvements to VSA/DSA (TSAT/VSAT) - Phase II | 0 |  | 569000 | $500k-$1M |  | Provide additional user functionality to make TSAT minimally viable as a real-time operations tool, and to significantly improve the usefulness of VSAT to operations.
SO | 5 | Transfer to Nodal | 0 | OTS (Operator Training Simulator) | 1700000 | $1M-$2M | 0 | 0 |  | AREVA components – Base OTS functions, Power System Modeling changes, QSE model revamp and implementation and Time Synch ABB components – Case development, Operational market data feed to OTS, Interface with simulation engine, Instructor control functions. In-flight Nodal project completing in 2009 needed for Operator training.
SO | 6 | Defer | 0 | MMS Multiple Network Models | 70000 | $50k-$100k | 0 | 0 | Post Nodal | Ability to provide separate models for DAM & RUC. Functionality currently being developed by Nodal per requirements
SO | 7 | Complete | 0 | MMS Dynamically scheduled resource incremental and decremental energy offer curves. | 60000 | $50k-$100k | 0 | 0 | Completed by Nodal | ERCOT implemented functionality based on their original interpretation; further discussion yielded a new interpretation for ERCOT that will require a change to the requirements and design. Part of Nodal requirements delivery.
SO | 8 | Complete | 0 | MMS S&B Information only calculations | 30000 | <$50k | 0 | 0 | Completed by Nodal | S&B information only calculations DAOPTPRINFO & RTOPTPRINFO will not be available until after go-live. Part of Nodal requirements delivery.
SO | 9 | Defer | 0 | NPRRs & Mandates | 1000000 | $1M-$2M | 0 | 0 |  | In flight & new NPRRs. Legislative or PUCT mandates.
SO | 10 | Defer | 0 | IMM & ERCOT Market Operations Support Study Tools | 1500000 | $1M-$2M | 0 | 0 |  | Enhancements to the ABB base product to improve functionality as a study tool. This is required by the IMM to monitor the Nodal Market. At this time it is expected that both the IMM and ERCOT Market Operations Support will benefit from these enhancements. If the needs of the IMM and ERCOT are determined to be significantly different a separate project may be necessary. This budget estimate includes the cost of hardware for the IMM as well as the study tool enhancements.
SO | 11 | Defer | 0 | ERCOT System Operations User Interfaces & Alarm Improvements | 750000 | $500k-$1M | 0 | 0 | Post Nodal | Improve EMS & MMS User Interfaces (UI's) for enhanced ERCOT Operator situational awareness. Improve Alarm Handling/Presentation – Control Room/EMS. Operators will be able to use delivered interfaces.
SO | 12 | Defer | 0 | CRR API | 500000 | $500k-$1M | 0 | 0 | Post Nodal | System to system interactions for the uploading and downloading of data between ERCOT and Market Participants without manual intervention. Nomination submittals (upload), Auction bid/offer submittals (upload), CRR Network Model files (download), CRR ownership records (download), CRR Auction results (download) Market Participants will be able to access CRR without API.
SO | 13 | Defer | 0 | NMMS API | 750000 | $500k-$1M | 0 | 0 | Post Nodal | System to system interactions for the uploading and possible future downloading of data between ERCOT and Market Participants with minimal manual intervention. NOMCR submittals (upload) including data submittals, one-line submittals and CIM XML submittal. Various other submittals such as Rating Methodologies, SPS documents, etc. Market Participants will be able to submit NOMCRs without API.
SO | 14 | Defer | 0 | MMS A/S Deliverability Evaluation Function (DEF) Enhancements | 260000 | $250k-$500k | 0 | 0 | Post Nodal | This tool is used by ERCOT operators to determine if there is a situation where Ancillary Service (AS) over a given time horizon is undeliverable. During MMS 2 pre-FAT where this tool was tested, certain enhancements in the scenarios simulated and results presented were proposed. ERCOT still has work to do to evaluate the proposed enhancements. There is a concern that it will take to long for the Operator to set and run once an hour.
SO | 15 | Partial Complete | 0 | MMS Weekly RUC Enhancements | 78000 | $50k-$100k | 0 | 0 | Partially delivered by Nodal | Provide enhanced configurability of WRUC study periods. Needed for daily run to support PASA
SO | 16 | Complete | 0 | Implemention of "shelf-ready" functionality for co-optimizing energy and A/S for self-committed resources in DAM | 400000 | $250k-$500k | 0 | 0 | Completed by Nodal | Need approved NPRR and requirements (NOTE: This is a preliminary estimate. A TPTF sub-group is still defining the requirements. Once protocol and requirement changes are approved, MMS will work with ABB to estimate the work. Design and implementation details may also alter the estimate.
SO | 17 | Defer | 0 | MMS Save Case Format Enhancement | 65000 | $50k-$100k | 0 | 0 | Post Nodal | All major processes (SCED, DAM, RUC) inputs/outputs are archived (referred to as save cases). These save cases can be reloaded into MMS for future analysis. To aid in analysis it was considered beneficial if the binary files in the save case could be stored in a ASCII file format. Workaround is available as data in binary file is still accessible after loading into MMS
SO | 18 | Defer | 0 | MMS CCT Data Enhancement | 20000 | <$50k | 0 | 0 | Post Nodal | Provide additional data in the database for monthly and annual CCTs for further analysis (Congestion management group) Workaround is available as raw data will be available in files
SO | 19 | Partial Complete | 0 | MMS Credit Check Performance Enhancement | 85000 | $50k-$100k | 0 | 0 | Partially delivered by Nodal | Improve the performance of Phase 2 validation for the credit limit check component. At present it is not known whether further performance improvements are needed
SO | 20 | Defer | 0 | Outage Scheduler Enhancements | 250000 | $100k-$250k | 0 | 0 | Post Nodal | Provide enhancements to the Outage Scheduler
[5 empty] | 7518000 | 7500000 | 884000 | 900000