## Merged
2009 Initiatives by CART
CART | Merged Rank | Revised Position | Percent of 2009 Budget Needed | Project Name / Type | Project Number | Original Budget Range | Revised Budget Range | Running Range | Reforecast Comments | Candidate Projects / Additional Details |  | Source | Non-Discretionary / Discretionary | Nodal | Add'l Sort | Full Doc?
MO | 1 | Continue As Planned | 100 | ERCOT System Throughput for IDR (Advanced Metering) | 70057_01 | <$50k | <$50k | <$1M | PUC Study only | Planned carryover for closing: Provide incremental increases in IDR processing capability for ERCOT systems. | ERCO | ERCOT / Carryover | Non-Discretionary | N | ERCOT Non-Nodal Non-Disc | Y
RO | 2 | Continue As Planned | 100 | Small Renewables/Distributed Generation - RMWG | 80028_01 | <$50k | <$50k | <$1M | Carryover for stabilization - iTEST constraints | Legislature / PUCT project | PUCT | PUCT / Carryover | Non-Discretionary | N | PUCT | Y
SO | 3 | New | 100 | Reliability Assessment Tool | 90001_01 | 0 | $100k-$250k | <$1M | Carry Over-Production Migration | Develop a reliability assessment tool to evaluate the reliability risk level of wind penetration in a quantitative way using probabilistic methods. This tool will assist system operators when maintaining adequate system reliability. | ERCO | ERCOT | Discretionary | N | ERCOT Non-Nodal Disc | Y
SO | 4 | New | 100 | Large Wind Power Production Ramp Forecasting | 90002_01 | 0 | $100k-$250k | <$1M | Carry Over-Pre-Fat, FAT & migration to production. | Develop a large ramp forecast product and make it available for SO engineers and operators. | ERCO | ERCOT | Discretionary | N | ERCOT Non-Nodal Disc | Y
RO | 5 | Continue As Planned | 100 | Advanced Metering - Mkt Changes for PUCT 34610 (fka RMWG/TX SET) | 80027_01 | $250k-$500k | $250k-$500k | <$1M | Carryover - Constraints: iTEST, Bus., Dev., system resource, market apporval of requirements | PUCT Project | PUCT | PUCT / Carryover | Non-Discretionary | N | PUCT | Y
RO | 6 | Continue As Planned | 100 | MarkeTrak Enhancements (Workflow & Reporting) | 70007_01 | $50k-$100k | $50k-$100k | <$1M | Carryover - Constraints: iTEST, Integration resources | Planned Enhancements to the functionality of MarkeTrak per SCR749 | Mark | Market / Carryover | Non-Discretionary | N | Mkt Non-Nodal | Y
IO | 7 | New | 100 | Spectel Server Replacement | 90003_01 | 0 | $500k-$1M | $1M-$2M | Aging equipment - fell below 2008 funding line |  | ERCO | ERCOT | Discretionary | N | ERCOT Non-Nodal Disc | Y
IO | 8 | Partial Execution | 50 | Data Storage | 90004_01 | $3M-$4M | $1M-$2M | $3M-$4M | Some capacity required to handle production growth and some required to implement an ILM strategy to mitigate growth to ensure we fit in the current data center | Storage Requirements for all environments to support data virtualization and ensure adequate capacity for ongoing operations and growth | ERCO | ERCOT | Discretionary | N | ERCOT Non-Nodal Disc | N
RO | 9 | Continue As Planned | 100 | Website Enhancements for ERCOT Outages PhII | 70006_02 | 0 | <$50k | $3M-$4M | Carry Over for Closing only
RO | 10 | Defer | 0 | ERCOT Outage Evaluation PhII(SCR745) | 60006_01 | 0 | 0 | $3M-$4M | Must get approval from TDTWG and Board to close as is.
RO | 11 | New | 100 | TIBCO_Siebel Integration | 80040_01 | 0 | $250k-$500k | $3M-$4M | Carryover - constraints: iTEST, physical resources | Implement integration best practices regarding TIBCO adapter including common services deployment for TIBCO replacing current framework services in effort to resolve ‘Half-Order’ issues. Siebel to expose thin “Service Order” interface service to TIBCO integration component. | ERCO | ERCOT | Non-Discretionary | N | ERCOT Non-Nodal Non-Disc | Y
RO | 12 | Continue As Planned | 100 | EDW EAI Transition Phase 1 (inc. PaperFree & NAESB) | 50061_01 | $50k-$100k | $50k-$100k | $3M-$4M | Carryover - constraints: iTEST, physical resources | Phase 1 will transition Paperfree and NAESB data from the Data Archive to Operational Data Store and begin replication. Necessary to decommission outdated DA hardware. | ERCO | ERCOT / Carryover | Non-Discretionary | N | ERCOT Non-Nodal Non-Disc | Y
MO | 13 | Continue As Planned | 100 | MPIM integration with Siebel | 90005_01 | $50k-$100k | $50k-$100k | $3M-$4M | Constraints - iTEST, physical resurces | Eliminate manual workaround and dual entry (2009 deferral necessary due to Siebel freeze) | ERCO | ERCOT | Discretionary | Y | ERCOT Nodal Specific Disc | N
MO | 14 | New | 100 | Information Lifecycle Management (Comm Ops Systems) | 90006_01 | 0 | $250k-$500k | $4M-$5M | New project to plan for data management of COMS data |  | ERCO | ERCOT | Discretionary | N | ERCOT Non-Nodal Disc | Y
Nodal | 15
RO | 16 | Continue As Planned | 100 | Data Research and Reporting (formerly ETS Transition to EDW) | 50088_01 | $100k-$250k | $250k-$500k | $4M-$5M | Carryover - Constraints: iTEST, Infrastructure | Deliver a data research and reporting tool for ERCOT Commercial Operations. | ERCO | ERCOT / Carryover | Non-Discretionary | N | ERCOT Non-Nodal Non-Disc | Y
RO | 17 | Continue As Planned | 100 | Advanced Metering – Long-Term Settlement Solution | 90007_01 | $1M-$2M | $1M-$2M | $5M-$6M | Planning - Constraints: physical resources | This project will begin implementation of the approved CSD from PR70057 for a system wide enhancement of data throughput for Market Operations. MKT Project is PUCT 34610. This project expected to be a phased approach across multiple years. Supports outcome of PUCT 34610 for ERCOT changes. | PUCT | PUCT | Non-Discretionary | N | PUCT | N
CO | 18 | New | 100 | Taylor Reconfiguration | 90008_01 | 0 | $250k-$500k | $5M-$6M | Large % of purchase could occur in 2008 - $750,000 |  | ERCO | ERCOT | Discretionary | N | ERCOT Non-Nodal Disc | Y
CO | 19 | Continue As Planned | 100 | MET Center Disposition | 80001_01 | >$5M | >$5M | Separate funding line item |  | Project to deliver: 1) Austin Control Center & Data Center; 2) Taylor Data Center Expansion; 3) Executive and Administrative Staff Office Lease Space | ERCO | ERCOT / Carryover | Non-Discretionary | N | ERCOT Non-Nodal Non-Disc | Y
IO | 20 | Continue As Planned | 100 | Minor Capital | TBD | $1M-$2M | $1M-$2M | $7M-$8M | Average minor cap expenditure over the last 3 years is $1.75m/y | Average minor capital expenditure (not budget) over the last 3 years is $2M. | ERCO | ERCOT | Non-Discretionary | N | ERCOT Non-Nodal Non-Disc | N
SO | 21 | Continue As Planned | 100 | Mid-Term Load Forecast Phase II | 60084_02 | 0 | <$50k | $7M-$8M | No Change | Integrated results from AREVA LF and alternate source and enable operator capability to select which Load Forecast will be used by EMS. |  | ERCOT / Carryover
SO | 22 | Continue As Planned | 100 | Improvements to VSA/DSA (TSAT/VSAT) - Phase II | 50029_01 | 0 | $500k-$1M | $8M-$9M |  | Provide additional user functionality to make TSAT minimally viable as a real-time operations tool, and to significantly improve the usefulness of VSAT to operations. |  | ERCOT / Carryover
RO | 23 | Continue As Planned | 100 | MarkeTrak Phase 3 | 80030_01 | $100k-$250k | $100k-$250k | $8M-$9M | iTEST, integration resources | Additional efficiencies not limited to a version upgrade. Will include Market requests. Required to maintain vendor support of application. | ERCO | ERCOT | Non-Discretionary | N | ERCOT Non-Nodal Non-Disc | Y
RO | 24 | Continue As Planned | 100 | Retail Application Upgrades | 80031_01 | $1M-$2M | $500k-$1M | $8M-$9M | iTest, physical resurces, integration resources | Version upgrades of retail applications and infrastructure components that will introduce new functionality. Required to maintain vendor support of applications.
IO | 25 | Continue As Planned | 100 | Infrastructure Monitoring Enhancement Project (Remedy Phase 3) | 90009_01 | $500k-$1M | $500k-$1M | $9M-$10M | Enhance asset tracking for desktops, implementation of SLA tracking and BPM to items within CMDB, inclusion of IDM integration enhancements | System enhancement to the existing Remedy and OpenView systems
CO | 26 | Continue As Planned | 100 | Cyber Security Project #1 | 60075_01 | $100k-$250k | $100k-$250k | $9M-$10M |  |  | ERCO | ERCOT / Carryover | Non-Discretionary | N | ERCOT Non-Nodal Non-Disc | Y
CO | 27 | Continue As Planned | 100 | Employee Performance Management | 80003_01 | 0 | <$50k | $9M-$10M | 2009 training effort (carryover) |  | ERCO | ERCOT / Carryover | Non-Discretionary | N | ERCOT Non-Nodal Non-Disc | Y
CO | 28 | Continue As Planned | 100 | Vendor Contract Management (Phase 2) | 70034_01 | $50k-$100k | $50k-$100k | $9M-$10M |  | Automate and link Hummingbird's contract approval process with the contract and vendor database. | ERCO | ERCOT / Carryover | Non-Discretionary | N | ERCOT Non-Nodal Non-Disc | Y
CO | 29 | Continue As Planned | 100 | Microsoft Project Server Upgrade | 60058_01 | $250k-$500k | $100k-$250k | $9M-$10M | Anticipating the majority of the work completes in 2008 and minimal carryover would be required…mainly for Closing activities. | Upgrade or replace the current Enterprise Project Management (EPM) tool and to implement portfolio management & reporting processes by streamlining management, access, and availability to project and portfolio data ultimately automating project dashboard reporting thereby reducing the effort required by PMs, BAs, project resources, etc. utilizing manual tools. | ERCO | ERCOT / Carryover | Non-Discretionary | N | ERCOT Non-Nodal Non-Disc | Y
IO | 30 | Continue As Planned | 100 | Monitoring & Reporting Tools | 90010_01 | $250k-$500k | $500k-$1M | $10M-$11M | Improved reporting on SAN capacity and stability for better business decisions. Eliminate future project delays and avoid production issues. | TBD | ERCO | ERCOT | Non-Discretionary | N | ERCOT Non-Nodal Non-Disc | N
RO | 31 | Continue As Planned | 100 | EDW EAI Transition Phase 2 (including PaperFree & NAESB) | 50061_02 | $100k-$250k | $100k-$250k | $10M-$11M | Carryover - constraints: iTEST, physical resources | Phase 2 will build reporting from the Paperfree and NAESB Data Archive into the Operational Data Store. Critical infrastructure project. | ERCO | ERCOT | Non-Discretionary | N | ERCOT Non-Nodal Non-Disc | Y
RO | 32 | New | 100 | Advanced Metering - Retail Market Interface | 90011_01 | 0 | $500k-$1M | $11M-$12M | Carryover - constraints: iTEST, physical resources | Phase 2 will build reporting from the Paperfree and NAESB Data Archive into the Operational Data Store. Critical infrastructure project. | ERCO | ERCOT | Non-Discretionary | N | ERCOT Non-Nodal Non-Disc | Y
CO | 33 | Continue As Planned | 100 | Cyber Security Project #2 | 70046_01 | $100k-$250k | $100k-$250k | $11M-$12M |  |  | ERCO | ERCOT / Carryover | Non-Discretionary | N | ERCOT Non-Nodal Non-Disc | Y
CO | 34 | Continue As Planned | 100 | Cyber Security Project #3 | 80008_01 | $250k-$500k | $100k-$250k | $11M-$12M |  |  | ERCO | ERCOT / Carryover | Non-Discretionary | N | ERCOT Non-Nodal Non-Disc | Y
CO | 35 | Continue As Planned | 100 | Cyber Security Project #6 | 90012_01 | $250k-$500k | $100k-$250k | $12M-$13M |  |  | ERCO | ERCOT | Non-Discretionary | Y | ERCOT Nodal Specific Non-Disc | Y
CO | 36 | Continue As Planned | 100 | Cyber Security Project #4 | 80016_01 | $250k-$500k | $100k-$250k | $11M-$12M |  |  | ERCO | ERCOT | Non-Discretionary | N | ERCOT Non-Nodal Non-Disc | Y
CO | 37 | Continue As Planned | 100 | Physical Security Project #1 | 70014_01 | $50k-$100k | $50k-$100k | $11M-$12M |  |  | ERCO | ERCOT / Carryover | Non-Discretionary | N | ERCOT Non-Nodal Non-Disc | Y
CO | 38 | Continue As Planned | 100 | Corporate Document Management (ENTERPRISE) | 60029_01 | $250k-$500k | $250k-$500k | $12M-$13M |  | Develop a strategy for ERCOT organization document management in 2008 and implement the strategy in 2009 to accomplish the following: Managed Security of Records and Information; Statutory and Regulatory Compliance (new rules of civil procedure: eDiscovery); Improved efficiency and productivity. | ERCO | ERCOT / Carryover | Non-Discretionary | N | MET Center | Y
CO | 39 | New | 100 | Blue Building Evacuation Route | 90013_01 | 0 | $100k-$250k | $12M-$13M |  |  | ERCO | ERCOT | Non-Discretionary | N | ERCOT Non-Nodal Non-Disc | Y
SO | 40 | New | 100 | Additional Zonal Projects Requested After Determination of New Nodal Go-Live Date | 90019_01 | 0 | $500k-$1M | $12M-$13M | Candidate projects include PRR776 and other items previously shelved due to expected 12/2008 Nodal Go-Live |  | ERCO | ERCOT | Non-Discretionary | N | ERCOT Non-Nodal Non-Disc | Y
Cutline - $12,700,000
CO | 41 | Continue As Planned | 100 | Cyber Security Project #7 | 90014_01 | $250k-$500k | $250k-$500k | $13M-$14M
CO | 42 | Continue As Planned | 100 | Procurement Process Flows | 80007_01 | <$50k | $100k-$250k | $13M-$14M |  | Programs developed with the Lawson Process Flow toolset which automates the flow of information during various steps to business processes. The number, type, and requirements will be determined as part of the overall Procurement business process review. | ERCO | ERCOT / Carryover | Non-Discretionary | N | ERCOT Non-Nodal Non-Disc | Y
CO | 43 | Continue As Planned | 100 | Process Flows - HR | 70020_01 | <$50k | $100k-$250k | $13M-$14M |  | Automate and provide auditable checkpoints for the hiring and termination of ERCOT employees | ERCO | ERCOT / Carryover | Non-Discretionary | N | ERCOT Non-Nodal Non-Disc | Y
CO | 44 | Continue As Planned | 100 | Finance Process Flows | 80013_01 | <$50k | $100k-$250k | $13M-$14M |  | Programs developed with the Lawson Process Flow toolset which automates the flow of information during various steps to business processes. The number, type, and requirements will be determined as part of the overall Finance business process review | ERCO | ERCOT / Carryover | Non-Discretionary | N | ERCOT Non-Nodal Non-Disc | Y
MO | 45 | Partial Execution | 10 | Web-enabled Registration | 90015_01 | $100k-$250k | <$50k | $13M-$14M | Begin planning | Create an interface and provide web-enabled registration forms (including RARF, NOI, interconnect, etc.) - total of around 50 forms. Nodal Go-live manual process. | Mark | Market | Non-Discretionary | Y | Mkt Nodal Specific Non-Disc | N
CO | 46 | Complete | 100 | Cyber Security Project #5 | N/A | 0 | 0 | $13M-$14M | Planned for delivery in 2008 - approved by CCB on 11/3/2008 |  | ERCO | ERCOT / Carryover | Non-Discretionary | N | ERCOT Non-Nodal Non-Disc | Y
CO | 47 | Continue As Planned | 100 | Physical Security Project #2 | 60094_01 | 0 | <$50k | $13M-$14M
CO | 48 | Partial Execution | 50 | Physical Security Project #3 | 80002_01 | <$50k | $100k-$250k | $13M-$14M |  |  | ERCO | ERCOT | Discretionary | N | ERCOT Non-Nodal Disc | Y
Capability Line - Additional 10% - Projects in this area are authorized to begin to help maximize 2009 project delivery (Ranks 41-48)
CO | 49 | New | 100 | Intranet Replacement | 90016_01 | 0 | $250k-$500k | $13M-$14M
MO | 50 | New | 100 | Serena Collage Upgrade | 90017_01 | 0 | $250k-$500k | $14M-$15M
Parking Lot Items Below This Line - Total Unfunded Not in Parking Lot = $640,000 (Rank 48-49)
CO | 97 | Defer | 0 | Lawson Security | 70015_01 | 0 | 0 |  | $50k - Candidate project if funding becomes available |  | ERCO | ERCOT / Carryover | Non-Discretionary | N | ERCOT Non-Nodal Non-Disc | Y
CO | 97 | Defer | 0 | VCM Replacement | 80004_01 | 0 | 0 |  | Candidate project if funding becomes available
SO | 98 | Transfer to Nodal | 0 | OTS (Operator Training Simulator) |  | $1M-$2M | 0 |  |  | AREVA components – Base OTS functions, Power System Modeling changes, QSE model revamp and implementation and Time Synch ABB components – Case development, Operational market data feed to OTS, Interface with simulation engine, Instructor control functions. In-flight Nodal project completing in 2009 needed for Operator training. | ERCO | ERCOT / Carryover | Non-Discretionary | Y | ERCOT Nodal Specific Non-Disc | Y
MO | 99 | Defer | 0 | Demand Response for Settlement |  | $500k-$1M | 0 |  | Possible Cancel | Implementation resulting from PUCT project 34610 or related PUCT order | Mark | Market | Non-Discretionary | N | Mkt Non-Nodal | Y
MO | 99 | Defer | 0 | Verifiable Cost Management System |  | $100k-$250k | 0 |  | Post Nodal | Creation of the Verifiable Cost Management System (VCMS), the interface QSEs will use for submitting and tracking their verifiable costs requested by TPTF. | Mark | Market | Non-Discretionary | Y | Mkt Nodal Specific Non-Disc | N
MO | 99 | Defer | 0 | Nodal.ercot.com Retirement |  | $250k-$500k | 0 |  | Post Nodal | Migration of content from nodal.ercot.com website to ERCOT.com website; retirement of nodal.ercot.com website. | ERCO | ERCOT | Discretionary | Y | ERCOT Nodal Specific Disc | N
MO | 99 | Defer | 0 | Enhancements to API for Disputes |  | $500k-$1M | 0 |  | Post Nodal | MPs (from COPs) have requested that ERCOT enhance an API to programmatically submit disputes. The API would interface with Siebel and would be created in the integration layer. | Mark | Market | Discretionary | Y | Mkt Nodal Specific Disc | N
MO | 99 | Defer | 0 | NPRRs & Mandates |  | $2M-$3M | 0 |  | Post Nodal | Additional post-nodal efforts - not yet defined and not covered under stabilization or Operations and Maintenance. | Mark | Market | Non-Discretionary | Y | Mkt Nodal Placehldr | N
MO | 99 | Cancel | 0 | COMS Extract, Report & Web Services Monitoring & Usage Statistics |  | $250k-$500k | 0 |  | Cancel | Provide research capabilities for Commercial Operations extract, report and web services data for internal business users, which include monitoring functionality and usage analysis capabilities. | ERCO | ERCOT | Discretionary | N | ERCOT Non-Nodal Disc | Y
CO | 99 | Delete | 0 | Corporate Document Management |  | $250k-$500k | 0 |  | Completed in 2008 with reduced scope | Implement Corporate Document Management strategy in the following departments: HR, Finance, Procurement, Security | ERCO | ERCOT / Carryover | Non-Discretionary | N | ERCOT Non-Nodal Non-Disc | Y
CO | 99 | New | 0 | Cyber Security Project #8 |  | 0 | 0 |  |  |  | ERCO | ERCOT / Carryover | Non-Discretionary | N | ERCOT Non-Nodal Non-Disc | Y
CO | 99 | Cancel | 100 | Intranet Assessment POC |  | 0 | 0 |  |  |  | ERCO | ERCOT | Discretionary | N | ERCOT Non-Nodal Disc | Y
CO | 99 | Defer | 0 | Cyber Security Project #9 |  | <$50k | 0
CO | 99 | Defer | 0 | Credit NPRRs |  | $250k-$500k | 0 |  | Deferred due to Nodal Go-Live delay | Placeholder to respond to NPRRs and mandates
CO | 99 | Defer | 0 | E-Procurement |  | <$50k | 0 |  |  | Included in Lawson’s Requisition Self Service is the E-Procurement application. E-Procurement allows for designated individuals to shop for goods from pre-approved outside vendors within the Requisition Self Service screens. Vendors establish and maintain
CO | 99 | Defer | 0 | Asset Management Integration (Altiris, Remedy, Lawson) |  | $100k-$250k | 0 |  |  | ERCOT currently has several Asset Management tools including Altiris, Aperture, Remedy and Lawson. Each of these tools provide a unique purpose and data. Integration between the systems is necessary to eliminate errors resulting from duplicate data.
CO | 99 | Defer | 0 | SharePoint Hosting |  | $250k-$500k | 0 |  |  | Potential hosting of SharePoint at an external site | ERCO | ERCOT | Discretionary | N | ERCOT Non-Nodal Disc | N
IO | 99 | Defer | 0 | Network - Switches |  | $250k-$500k | 0 |  | Replaced every 5 years | Replaced every 5 years. | ERCO | ERCOT | Discretionary | N | ERCOT Non-Nodal Disc | N
IO | 99 | Defer | 0 | Computing Hardware - Desktops |  | $250k-$500k | 0 |  | Replaced every 3 years | Replaced every 3 years | ERCO | ERCOT | Discretionary | N | ERCOT Non-Nodal Disc | N
IO | 99 | Defer | 0 | Network - Firewalls |  | $100k-$250k | 0 |  | Done in 2008 | Replaced every 4-5 years. | ERCO | ERCOT | Discretionary | N | ERCOT Non-Nodal Disc | N
IO | 99 | Defer | 0 | Computing Hardware - X-series Replacement |  | $1M-$2M | 0 |  | Defered until data center capacity is available | Replaced every 3-4 years. | ERCO | ERCOT | Discretionary | N | ERCOT Non-Nodal Disc | N
IO | 99 | Defer | 0 | Storage - Misc. |  | $250k-$500k | 0 |  | Defered until data center capacity is available | Allotment for additional storage projects for supporting equipment - SAN directors & switches, eg. to allow implementation of storage equipment | ERCO | ERCOT | Non-Discretionary | N | ERCOT Non-Nodal Non-Disc | N
RO | 99 | Defer | 0 | TML Transition to MIS |  | $500k-$1M | 0 |  | Post Nodal | Migration from TML to MIS of functions that support the Retail market and/or Zonal-related reporting that will continue past Nodal Go-Live. Will maintain 2 systems until this transition occurs. | ERCO | ERCOT | Discretionary | Y | ERCOT Nodal Specific Disc | N
SO | 99 | Defer | 0 | MMS Multiple Network Models |  | $50k-$100k | 0 |  | Post Nodal | Ability to provide separate models for DAM & RUC. Functionality currently being developed by Nodal per requirements | Mark | Market / Carryover | Non-Discretionary | Y | Mkt Nodal Specific Non-Disc | Y
SO | 99 | Complete | 0 | MMS Dynamically scheduled resource incremental and decremental energy offer curves. |  | $50k-$100k | 0 |  | Completed by Nodal | ERCOT implemented functionality based on their original interpretation; further discussion yielded a new interpretation for ERCOT that will require a change to the requirements and design. Part of Nodal requirements delivery. | Mark | Market / Carryover | Non-Discretionary | Y | Mkt Nodal Specific Non-Disc | Y
SO | 99 | Complete | 0 | MMS S&B Information only calculations |  | <$50k | 0 |  | Completed by Nodal | S&B information only calculations DAOPTPRINFO & RTOPTPRINFO will not be available until after go-live. Part of Nodal requirements delivery. | Mark | Market / Carryover | Non-Discretionary | Y | Mkt Nodal Specific Non-Disc | Y
SO | 99 | Defer | 0 | NPRRs & Mandates |  | $1M-$2M | 0 |  |  | In flight & new NPRRs. Legislative or PUCT mandates. | Mark | Market | Non-Discretionary | Y | Mkt Nodal Placehldr | N
SO | 99 | Defer | 0 | IMM & ERCOT Market Operations Support Study Tools |  | $1M-$2M | 0 |  |  | Enhancements to the ABB base product to improve functionality as a study tool. This is required by the IMM to monitor the Nodal Market. At this time it is expected that both the IMM and ERCOT Market Operations Support will benefit from these enhancements. If the needs of the IMM and ERCOT are determined to be significantly different a separate project may be necessary. This budget estimate includes the cost of hardware for the IMM as well as the study tool enhancements. | IMM | IMM | Non-Discretionary | Y | IMM | N
SO | 99 | Defer | 0 | ERCOT System Operations User Interfaces & Alarm Improvements |  | $500k-$1M | 0 |  | Post Nodal | Improve EMS & MMS User Interfaces (UI's) for enhanced ERCOT Operator situational awareness. Improve Alarm Handling/Presentation – Control Room/EMS. Operators will be able to use delivered interfaces. | ERCO | ERCOT | Discretionary | Y | ERCOT Nodal Specific Disc | N
SO | 99 | Defer | 0 | CRR API |  | $500k-$1M | 0 |  | Post Nodal | System to system interactions for the uploading and downloading of data between ERCOT and Market Participants without manual intervention. Nomination submittals (upload), Auction bid/offer submittals (upload), CRR Network Model files (download), CRR ownership records (download), CRR Auction results (download) Market Participants will be able to access CRR without API. | Mark | Market | Discretionary | Y | Mkt Nodal Specific Disc | Y
SO | 99 | Defer | 0 | NMMS API |  | $500k-$1M | 0 |  | Post Nodal | System to system interactions for the uploading and possible future downloading of data between ERCOT and Market Participants with minimal manual intervention. NOMCR submittals (upload) including data submittals, one-line submittals and CIM XML submittal. Various other submittals such as Rating Methodologies, SPS documents, etc. Market Participants will be able to submit NOMCRs without API. | Mark | Market | Discretionary | Y | Mkt Nodal Specific Disc | N
SO | 99 | Defer | 0 | MMS A/S Deliverability Evaluation Function (DEF) Enhancements |  | $250k-$500k | 0 |  | Post Nodal | This tool is used by ERCOT operators to determine if there is a situation where Ancillary Service (AS) over a given time horizon is undeliverable. During MMS 2 pre-FAT where this tool was tested, certain enhancements in the scenarios simulated and results presented were proposed. ERCOT still has work to do to evaluate the proposed enhancements. There is a concern that it will take to long for the Operator to set and run once an hour. | ERCO | ERCOT | Discretionary | Y | ERCOT Nodal Specific Disc | N
SO | 99 | Partial Complete | 50 | MMS Weekly RUC Enhancements |  | $50k-$100k | 0 |  | Partially delivered by Nodal | Provide enhanced configurability of WRUC study periods. Needed for daily run to support PASA | ERCO | ERCOT | Discretionary | Y | ERCOT Nodal Specific Disc | N
SO | 99 | Complete | 0 | Implemention of "shelf-ready" functionality for co-optimizing energy and A/S for self-committed resources in DAM |  | $250k-$500k | 0 |  | Completed by Nodal | Need approved NPRR and requirements (NOTE: This is a preliminary estimate. A TPTF sub-group is still defining the requirements. Once protocol and requirement changes are approved, MMS will work with ABB to estimate the work. Design and implementation details may also alter the estimate. | Mark | Market | Discretionary | Y | Mkt Nodal Specific Disc | N
SO | 99 | Defer | 0 | MMS Save Case Format Enhancement |  | $50k-$100k | 0 |  | Post Nodal | All major processes (SCED, DAM, RUC) inputs/outputs are archived (referred to as save cases). These save cases can be reloaded into MMS for future analysis. To aid in analysis it was considered beneficial if the binary files in the save case could be stored in a ASCII file format. Workaround is available as data in binary file is still accessible after loading into MMS | ERCO | ERCOT | Discretionary | Y | ERCOT Nodal Specific Disc | N
SO | 99 | Defer | 0 | MMS CCT Data Enhancement |  | <$50k | 0 |  | Post Nodal | Provide additional data in the database for monthly and annual CCTs for further analysis (Congestion management group) Workaround is available as raw data will be available in files | ERCO | ERCOT | Discretionary | Y | ERCOT Nodal Specific Disc | N
SO | 99 | Partial Complete | 50 | MMS Credit Check Performance Enhancement |  | $50k-$100k | 0 |  | Partially delivered by Nodal | Improve the performance of Phase 2 validation for the credit limit check component. At present it is not known whether further performance improvements are needed | ERCO | ERCOT | Discretionary | Y | ERCOT Nodal Specific Disc | N
SO | 99 | Defer | 0 | Outage Scheduler Enhancements |  | $100k-$250k | 0 |  | Post Nodal | Provide enhancements to the Outage Scheduler | Mark | Market / ERCOT | Discretionary | Y | Mkt Nodal Specific Disc | N
CO | 31
IO | 10
MO | 11
RO | 14
SO | 21
87

## -- CO --
2009 Initiatives by CART
CART | CO Rank | Revised Position | Percent of 2009 Budget Needed | Project Name / Type | Project Number | Original Budget Range | Revised Budget Range | Reforecast Comments | Candidate Projects / Additional Details
CO | 1 | New | 100 | Taylor Reconfiguration | 90008_01 | 0 | $250k-$500k
CO | 2 | Continue As Planned | 100 | MET Center Disposition | 80001_01 | >$5M | >$5M |  | Project to deliver: 1) Austin Control Center & Data Center; 2) Taylor Data Center Expansion; 3) Executive and Administrative Staff Office Lease Space
CO | 3 | Continue As Planned | 100 | Cyber Security Project #1 | 60075_01 | $100k-$250k | $100k-$250k
CO | 4 | Continue As Planned | 100 | Employee Performance Management | 80003_01 | 0 | $100k-$250k | 2009 training effort (carryover)
CO | 5 | Continue As Planned | 100 | Vendor Contract Management (Phase 2) | 70034_01 | $50k-$100k | $50k-$100k |  | Automate and link Hummingbird's contract approval process with the contract and vendor database.
CO | 6 | Continue As Planned | 100 | Microsoft Project Server Upgrade | 60058_01 | $250k-$500k | $100k-$250k | Anticipating the majority of the work completes in 2008 and minimal carryover would be required…mainly for Closing activities. | Upgrade or replace the current Enterprise Project Management (EPM) tool and to implement portfolio management & reporting processes by streamlining management, access, and availability to project and portfolio data ultimately automating project dashboard reporting thereby reducing the effort required by PMs, BAs, project resources, etc. utilizing manual tools.
CO | 7 | Continue As Planned | 100 | Cyber Security Project #2 | 70046_01 | $100k-$250k | $100k-$250k
CO | 8 | Continue As Planned | 100 | Cyber Security Project #3 | 80008_01 | $250k-$500k | $250k-$500k
CO | 9 | Continue As Planned | 100 | Cyber Security Project #6 | 90012_01 | $250k-$500k | $250k-$500k
CO | 10 | Continue As Planned | 100 | Cyber Security Project #4 | 80016_01 | $250k-$500k | $250k-$500k
CO | 11 | Continue As Planned | 100 | Physical Security Project #1 | 70014_01 | $50k-$100k | $50k-$100k
CO | 12 | Continue As Planned | 100 | Corporate Document Management (ENTERPRISE) | 60029_01 | $250k-$500k | $250k-$500k | Adjust 2009 budget, "transfer" funds from Corporate to Enterprise. | Develop a strategy for ERCOT organization document management in 2008 and implement the strategy in 2009 to accomplish the following: Managed Security of Records and Information; Statutory and Regulatory Compliance (new rules of civil procedure: eDiscovery); Improved efficiency and productivity.
CO | 13 | Continue As Planned | 100 | Procurement Process Flows | 90013_01 | <$50k | <$50k |  | Programs developed with the Lawson Process Flow toolset which automates the flow of information during various steps to business processes. The number, type, and requirements will be determined as part of the overall Procurement business process review.
CO | 14 | Continue As Planned | 100 | Process Flows - HR | 90014_01 | <$50k | <$50k |  | Automate and provide auditable checkpoints for the hiring and termination of ERCOT employees
CO | 15 | Continue As Planned | 100 | Finance Process Flows | 80007_01 | <$50k | <$50k |  | Programs developed with the Lawson Process Flow toolset which automates the flow of information during various steps to business processes. The number, type, and requirements will be determined as part of the overall Finance business process review
CO | 16 | Complete | 0 | Cyber Security Project #5 | 70020_01 | 0 | 0 | Planned for delivery in 2008 - approved by CCB on 11/3/2008
CO | 17 | New | 100 | Blue Building Evacuation Route | 80013_01 | 0 | $250k-$500k
CO | 18 | Continue As Planned | 100 | Physical Security Project #2 | N/A | 0 | <$50k
CO | 19 | Partial Execution | 50 | Physical Security Project #3 | 60094_01 | <$50k | <$50k
CO | 20 | Continue As Planned | 100 | Cyber Security Project #7 | 80002_01 | $250k-$500k | $250k-$500k
CO | 21 | New | 100 | Intranet Replacement | 90016_01 |  | $250k-$500k | Initiating in 2008
CO | 22 | Continue As Planned | 100 | Lawson Security | 70015_01 | 0 | $50k-$100k
CO | 23 | Defer | 0 | VCM Replacement | 80004_01 |  | 0 | Candidate project if funding becomes available
CO | 24 | Delete | 0 | Corporate Document Management |  | $100k-$250k | 0 | Completed in 2008 with reduced scope | Implement Corporate Document Management strategy in the following departments: HR, Finance, Procurement, Security
CO | 25 | New | 0 | Cyber Security Project #8 |  | 0 | 0
CO | 26 | New | 100 | Intranet Assessment POC |  | 0 | $50k-$100k
CO | 27 | Defer | 0 | Cyber Security Project #9 |  | <$50k | <$50k
CO | 28 | Defer | 0 | Credit NPRRs |  | <$50k | <$50k | Deferred due to Nodal Go-Live delay | Placeholder to respond to NPRRs and mandates
CO | 29 | Defer | 0 | E-Procurement |  | <$50k | <$50k |  | Included in Lawson’s Requisition Self Service is the E-Procurement application. E-Procurement allows for designated individuals to shop for goods from pre-approved outside vendors within the Requisition Self Service screens. Vendors establish and maintain
CO | 30 | Defer | 0 | Asset Management Integration (Altiris, Remedy, Lawson) |  | $100k-$250k | 0 |  | ERCOT currently has several Asset Management tools including Altiris, Aperture, Remedy and Lawson. Each of these tools provide a unique purpose and data. Integration between the systems is necessary to eliminate errors resulting from duplicate data.
CO | 31 | Defer | 0 | SharePoint Hosting |  | $250k-$500k | 0 |  | Potential hosting of SharePoint at an external site
|  |  |  | Subtotal |  | 23950000 | 22175000
|  |  |  | Less: Met Center |  | 20400000 | 20400000
|  |  |  | CO Total |  | 3550000 | 1775000

## -- IO --
2009 Initiatives by CART
CART | IO Rank | Revised Position | Percent of 2009 Budget Needed | Project Name / Type | Project Number | Original Budget Range | Revised Budget Range | Reforecast Comments | Candidate Projects / Additional Details
IO | 1 | New | 100 | Spectel Server Replacement | 90003_01 | 0 | $500k-$1M | Aging equipment - fell below 2008 funding line
IO | 2 | Partial Execution | 50 | Data Storage | 90004_01 | $3M-$4M | $1M-$2M | Some capacity required to handle production growth and some required to implement an ILM strategy to mitigate growth to ensure we fit in the current data center | Storage Requirements for all environments to support data virtualization and ensure adequate capacity for ongoing operations and growth
IO | 3 | Continue As Planned | 100 | Infrastructure Monitoring Enhancement Project (Remedy Phase 3) | TBD | $500k-$1M | $500k-$1M | Enhance asset tracking for desktops, implementation of SLA tracking and BPM to items within CMDB, inclusion of IDM integration enhancements | System enhancement to the existing Remedy and OpenView systems
IO | 4 | Continue As Planned | 100 | Monitoring & Reporting Tools | 90009_01 | $250k-$500k | $500k-$1M | Improved reporting on SAN capacity and stability for better business decisions. Eliminate future project delays and avoid production issues. | TBD
IO | 5 | Continue As Planned | 100 | Minor Capital | 90010_01 | $1M-$2M | $1M-$2M | Average minor cap expenditure over the last 3 years is $1.75m/y | Average minor capital expenditure (not budget) over the last 3 years is $2M.
IO | 6 | Defer | 0 | Network - Switches |  | $250k-$500k | 0 | Replaced every 5 years | Replaced every 5 years.
IO | 7 | Defer | 0 | Computing Hardware - Desktops |  | $250k-$500k | 0 | Replaced every 3 years | Replaced every 3 years
IO | 8 | Defer | 0 | Network - Firewalls |  | $100k-$250k | 0 | Done in 2008 | Replaced every 4-5 years.
IO | 9 | Defer | 0 | Computing Hardware - X-series Replacement |  | $1M-$2M | 0 | Deferred until data center capacity is available | Replaced every 3-4 years.
IO | 10 | Defer | 0 | Storage - Misc. |  | $250k-$500k | 0 | Deferred until data center capacity is available | Allotment for additional storage projects for supporting equipment - SAN directors & switches, eg. to allow implementation of storage equipment
|  |  |  | Subtotal |  | 8350000 | 5525000

## -- MO --
2009 Initiatives by CART
CART | MO Rank | Revised Position | Percent of 2009 Budget Needed | Project Name / Type | Project Number | Original Budget Range | Revised Budget Range | Reforecast Comments | Candidate Projects / Additional Details
MO | 1 | Continue As Planned | 100 | Study for Advanced Metering Long Term Solution of Settlement (fka ERCOT System Throughput for IDR (Advanced Metering) | 70057_01 | <$50k | <$50k | PUC Study only | Planned carryover for closing: Provide incremental increases in IDR processing capability for ERCOT systems.
MO | 2 | Continue As Planned | 100 | MPIM integration with Siebel | 90005_01 | $100k-$250k | $50k-$100k | Constraints - iTEST, physical resurces | Eliminate manual workaround and dual entry (2009 deferral necessary due to Siebel freeze)
MO | 3 | New | 50 | Information Lifecycle Management (Comm Ops Systems) | 90006_01 | $250k-$500k | $500k-$1M | New project still being estimated as of 10/3/08
MO | 4 | Partial Execution | 10 | Web-enabled Registration | 90015_01 | $100k-$250k | <$50k | Begin planning | Create an interface and provide web-enabled registration forms (including RARF, NOI, interconnect, etc.) - total of around 50 forms. Nodal Go-live manual process.
MO | 5 | New | 100 | ERCOT.com CMS Replacement | 90017_01 | 0 | $250k-$500k
MO | 6 | Defer | 0 | Demand Response for Settlement |  | $500k-$1M | 0 | Possible Cancel | Implementation resulting from PUCT project 34610 or related PUCT order
MO | 7 | Defer | 0 | Verifiable Cost Management System |  | $100k-$250k | 0 | Post Nodal | Creation of the Verifiable Cost Management System (VCMS), the interface QSEs will use for submitting and tracking their verifiable costs requested by TPTF.
MO | 8 | Defer | 0 | Nodal.ercot.com Retirement |  | $250k-$500k | 0 | Post Nodal | Migration of content from nodal.ercot.com website to ERCOT.com website; retirement of nodal.ercot.com website.
MO | 9 | Defer | 0 | Enhancements to API for Disputes |  | $500k-$1M | 0 | Post Nodal | MPs (from COPs) have requested that ERCOT enhance an API to programmatically submit disputes. The API would interface with Siebel and would be created in the integration layer.
MO | 10 | Defer | 0 | NPRRs & Mandates |  | $2M-$3M | 0 | Post Nodal | Additional post-nodal efforts - not yet defined and not covered under stabilization or Operations and Maintenance.
MO | 11 | Defer | 0 | COMS Extract, Report & Web Services Monitoring & Usage Statistics |  | $250k-$500k | 0 | Cancel | Provide research capabilities for Commercial Operations extract, report and web services data for internal business users, which include monitoring functionality and usage analysis capabilities.
|  |  |  | Subtotal |  | 4300000 | 550000

## -- RO --
2009 Initiatives by CART
CART | RO Rank | Revised Position | Percent of 2009 Budget Needed | Project Name / Type | Project Number | Original Budget Range | Revised Budget Range | Reforecast Comments | Candidate Projects / Additional Details
RO | 1 | Continue As Planned | 100 | Small Renewables/Distributed Generation - RMWG | 80028_01 | <$50k | <$50k | Carry Over for stabilization - iTEST constraints | Legislature / PUCT project
RO | 2 | Continue As Planned | 100 | Advanced Metering - Mkt Changes for PUCT 34610 (fka RMWG/TX SET) | 80027_01 | $250k-$500k | $250k-$500k | Carry Over - Constraints: iTEST, Bus., Dev., system resource, market apporval of requirements | PUCT Project
RO | 3 | Continue As Planned | 100 | MarkeTrak Enhancements (Workflow & Reporting) | 70007_01 | $50k-$100k | $50k-$100k | Carry Over - Constraints: iTEST, Integration resources | Planned Enhancements to the functionality of MarkeTrak per SCR749
RO | 4 | Continue As Planned | 100 | Website Enhancements for ERCOT Outages Phase 2 | 70006_02 | 0 | <$50k |  | PUCT Project
RO | 5 | Continue As Planned | 100 | ERCOT Outage Evaluation Phase 2 | 60006_01 | 0 | 0 |  | PUCT Project
RO | 6 | New | 100 | TIBCO_Siebel Integration | 80040_01 | 0 | $250k-$500k | Carry Over - constraints: iTEST, physical resources | Implement integration best practices regarding TIBCO adapter including common services deployment for TIBCO replacing current framework services in effort to resolve ‘Half-Order’ issues. Siebel to expose thin “Service Order” interface service to TIBCO integration component.
RO | 7 | Continue As Planned | 100 | EDW EAI Transition Phase 1(inc. PaperFree & NAESB) | 50061_01 | $50k-$100k | $50k-$100k | Carry Over - constraints: iTEST, physical resources | Phase 1 will transition Paperfree and NAESB data from the Data Archive to Operational Data Store and begin replication. Necessary to decommission outdated DA hardware.
RO | 8 | Continue As Planned | 100 | Data Research and Reporting (formerly ETS Transition to EDW) | 50088_01 | $100k-$250k | $250k-$500k | Carry Over - Constraints: iTEST, Infrastructure | Deliver a data research and reporting tool for ERCOT Commercial Operations.
RO | 9 | Continue As Planned | 100 | Advanced Metering – Long-Term Settlement Solution | 90007_01 | $1M-$2M | $1M-$2M | Planning - Constraints: physical resources | This project will begin implementation of the approved CSD from PR70057 for a system wide enhancement of data throughput for Market Operations. MKT Project is PUCT 34610. This project expected to be a phased approach across multiple years. Supports outcome of PUCT 34610 for ERCOT changes.
RO | 10 | Continue As Planned | 100 | MarkeTrak Phase 3 | 80030_01 | $100k-$250k | $100k-$250k | iTEST, integration resources | Additional efficiencies not limited to a version upgrade. Will include Market requests. Required to maintain vendor support of application.
RO | 11 | Continue As Planned | 100 | Retail Application Upgrades | 80031_01 | $1M-$2M | $500k-$1M | itest, physical resurces, integration resources | Version upgrades of retail applications and infrastructure components that will introduce new functionality. Required to maintain vendor support of applications.
RO | 12 | Continue As Planned | 100 | EDW EAI Transition Phase 2 (including PaperFree & NAESB) | 50061_02 | $100k-$250k | $100k-$250k | Carry Over - constraints: iTEST, physical resources | Phase 2 will build reporting from the Paperfree and NAESB Data Archive into the Operational Data Store. Critical infrastructure project.
RO | 13 | New | 100 | Advanced Metering - Retail Market Interface | 90011_01 | 0 | $500k-$1M | Carry Over - constraints: iTEST, physical resources | Phase 2 will build reporting from the Paperfree and NAESB Data Archive into the Operational Data Store. Critical infrastructure project.
RO | 14 | Defer | 0 | TML Transition to MIS |  | $500k-$1M | 0 | Post Nodal | Migration from TML to MIS of functions that support the Retail market and/or Zonal-related reporting that will continue past Nodal Go-Live. Will maintain 2 systems until this transition occurs.
|  |  |  | Subtotal |  | 3500000 | 3450000

## -- SO --
2009 Initiatives by CART
CART | SO Rank | Revised Position | Percent of 2009 Budget Needed | Project Name / Type | Project Number | Original Budget Range | Revised Budget Range | Reforecast Comments | Candidate Projects / Additional Details
SO | 1 | New | 100 | Reliability Assessment Tool | 90001_01 | 0 | $100k-$250k | Carry Over-Production Migration | Develop a reliability assessment tool to evaluate the reliability risk level of wind penetration in a quantitative way using probabilistic methods. This tool will assist system operators when maintaining adequate system reliability.
SO | 2 | New | 100 | Large Wind Power Production Ramp Forecasting | 90002_01 | 0 | $100k-$250k | Carry Over-Pre-Fat, FAT & migration to production. | Develop a large ramp forecast product and make it available for SO engineers and operators.
SO | 3 | Continue As Planned | 100 | Mid-Term Load Forecast Phase II | 60084_02 |  | <$50k | No Change | Integrated results from AREVA LF and alternate source and enable operator capability to select which Load Forecast will be used by EMS.
SO | 4 | Continue As Planned | 100 | Improvements to VSA/DSA (TSAT/VSAT) - Phase II | 50029_01 |  | $500k-$1M |  | Provide additional user functionality to make TSAT minimally viable as a real-time operations tool, and to significantly improve the usefulness of VSAT to operations.
SO | 5 | New | 100 | Additional Zonal Projects Requested After Determination of New Nodal Go-Live Date | 90019_01 | 0 | $500k-$1M | Candidate projects include PRR776 and other items previously shelved due to expected 12/2008 Nodal Go-Live
SO | 6 | Transfer to Nodal | 0 | OTS (Operator Training Simulator) |  | $1M-$2M | 0 |  | AREVA components – Base OTS functions, Power System Modeling changes, QSE model revamp and implementation and Time Synch ABB components – Case development, Operational market data feed to OTS, Interface with simulation engine, Instructor control functions. In-flight Nodal project completing in 2009 needed for Operator training.
SO | 7 | Defer | 0 | MMS Multiple Network Models |  | $50k-$100k | 0 | Post Nodal | Ability to provide separate models for DAM & RUC. Functionality currently being developed by Nodal per requirements
SO | 8 | Complete | 0 | MMS Dynamically scheduled resource incremental and decremental energy offer curves. |  | $50k-$100k | 0 | Completed by Nodal | ERCOT implemented functionality based on their original interpretation; further discussion yielded a new interpretation for ERCOT that will require a change to the requirements and design. Part of Nodal requirements delivery.
SO | 9 | Complete | 0 | MMS S&B Information only calculations |  | <$50k | 0 | Completed by Nodal | S&B information only calculations DAOPTPRINFO & RTOPTPRINFO will not be available until after go-live. Part of Nodal requirements delivery.
SO | 10 | Defer | 0 | NPRRs & Mandates |  | $1M-$2M | 0 |  | In flight & new NPRRs. Legislative or PUCT mandates.
SO | 11 | Defer | 0 | IMM & ERCOT Market Operations Support Study Tools |  | $1M-$2M | 0 |  | Enhancements to the ABB base product to improve functionality as a study tool. This is required by the IMM to monitor the Nodal Market. At this time it is expected that both the IMM and ERCOT Market Operations Support will benefit from these enhancements. If the needs of the IMM and ERCOT are determined to be significantly different a separate project may be necessary. This budget estimate includes the cost of hardware for the IMM as well as the study tool enhancements.
SO | 12 | Defer | 0 | ERCOT System Operations User Interfaces & Alarm Improvements |  | $500k-$1M | 0 | Post Nodal | Improve EMS & MMS User Interfaces (UI's) for enhanced ERCOT Operator situational awareness. Improve Alarm Handling/Presentation – Control Room/EMS. Operators will be able to use delivered interfaces.
SO | 13 | Defer | 0 | CRR API |  | $500k-$1M | 0 | Post Nodal | System to system interactions for the uploading and downloading of data between ERCOT and Market Participants without manual intervention. Nomination submittals (upload), Auction bid/offer submittals (upload), CRR Network Model files (download), CRR ownership records (download), CRR Auction results (download) Market Participants will be able to access CRR without API.
SO | 14 | Defer | 0 | NMMS API |  | $500k-$1M | 0 | Post Nodal | System to system interactions for the uploading and possible future downloading of data between ERCOT and Market Participants with minimal manual intervention. NOMCR submittals (upload) including data submittals, one-line submittals and CIM XML submittal. Various other submittals such as Rating Methodologies, SPS documents, etc. Market Participants will be able to submit NOMCRs without API.
SO | 15 | Defer | 0 | MMS A/S Deliverability Evaluation Function (DEF) Enhancements |  | $250k-$500k | 0 | Post Nodal | This tool is used by ERCOT operators to determine if there is a situation where Ancillary Service (AS) over a given time horizon is undeliverable. During MMS 2 pre-FAT where this tool was tested, certain enhancements in the scenarios simulated and results presented were proposed. ERCOT still has work to do to evaluate the proposed enhancements. There is a concern that it will take to long for the Operator to set and run once an hour.
SO | 16 | Partial Complete | 0 | MMS Weekly RUC Enhancements |  | $50k-$100k | 0 | Partially delivered by Nodal | Provide enhanced configurability of WRUC study periods. Needed for daily run to support PASA
SO | 17 | Complete | 0 | Implemention of "shelf-ready" functionality for co-optimizing energy and A/S for self-committed resources in DAM |  | $250k-$500k | 0 | Completed by Nodal | Need approved NPRR and requirements (NOTE: This is a preliminary estimate. A TPTF sub-group is still defining the requirements. Once protocol and requirement changes are approved, MMS will work with ABB to estimate the work. Design and implementation details may also alter the estimate.
SO | 18 | Defer | 0 | MMS Save Case Format Enhancement |  | $50k-$100k | 0 | Post Nodal | All major processes (SCED, DAM, RUC) inputs/outputs are archived (referred to as save cases). These save cases can be reloaded into MMS for future analysis. To aid in analysis it was considered beneficial if the binary files in the save case could be stored in a ASCII file format. Workaround is available as data in binary file is still accessible after loading into MMS
SO | 19 | Defer | 0 | MMS CCT Data Enhancement |  | <$50k | 0 | Post Nodal | Provide additional data in the database for monthly and annual CCTs for further analysis (Congestion management group) Workaround is available as raw data will be available in files
SO | 20 | Partial Complete | 0 | MMS Credit Check Performance Enhancement |  | $50k-$100k | 0 | Partially delivered by Nodal | Improve the performance of Phase 2 validation for the credit limit check component. At present it is not known whether further performance improvements are needed
SO | 21 | Defer | 0 | Outage Scheduler Enhancements |  | $100k-$250k | 0 | Post Nodal | Provide enhancements to the Outage Scheduler
[6 empty] | 7500000 | 900000