## Market Design
ERCOT
Renewable Technology Working Group (RTWG)
List of Market Design Issues
Issue Category | Issue No. | Description | Assigned to: | Priority | Revision Mechanism | Status | Other REF No.
MD | 1 | Options to ancillary services allocations: Cost allocation | CATF
MD | 2 | Options to ancillary services allocations: Procurement Optimization | QMWG
MD | 3 | Non-Spin requirements
MD | 4 | Consideration of new ancillary service products
MD | 5 | Storage technologies benefits (e.g., flywheels) to the integration of wind and provision of necessary ancillary services (regulation, responsive reserves)
MD | 6 | Ancillary Service procurement methodology (Increase RGS, RRS, NSRS during high risk periods) | WOTF |  |  |  | WOTF 3c
MD | 7 | Protocol changes to allow wind resources to provide ancillary services |  |  | PRR
MD | 8 | Review Protocol re: reactive and voltage requirements which are unclear, confusing, ambiguous |  |  | PRR |  | WOTF 1a
MD | 9 | Review nodal protocols for proper treatment of wind generation re: dispatch response |  |  | NPRR
MD | 10 | Review nodal protocols for proper treatment of wind generation re: performance metrics with negative pricing |  |  | NPRR
MD | 11 | Review nodal protocols for proper treatment of wind generation re: base point deviaton charges as applicable to wind generation |  |  | NPRR
MD | 12 | WGR LSL as % of HSL | QMWG |  | PRR 773 | Approved by TAC | WOTF 2a
MD | 13 | Mandate use of AWST 80% forecast in wind Resource Plans |  | N/A | PRR 763 | COMPLETE | WOTF 3b

## System Ops
ERCOT
Renewable Technology Working Group (RTWG)
List of System Operations Issues
Issue Category | System Ops Issue No. | Description | Assigned to: | Priority | Revision Mechanism | Status | Other Ref No.
SO | 1 | Update forms used by ERCOT to gather generator data so that WGRs can provide accurate information |  |  |  |  | WOTF 1d
SO | 2 | Identifying nodal tools to more effectively integrate wind into the grid
SO | 3 | Response to down balancing instructions (QMWG); SCE issues, clarity on expected following instructions, requirements
SO | 4 | Smart grid and demand response implications on market design and integration of renewable resources
SO | 5 | Impact of plug-in hybrid vehicles on storage and use of renewable resources
SO | 6 | Qualification testing of reactive capability for wind generation
SO | 7 | High frequency: Develop alternate solutions | WOTF |  |  |  | WOTF 5
SO | 8 | System Inertia/Governor Generator Response | PDCWG |  |  |  | WOTF 1e
SO | 9 | Better defined SCADA control on generation breakers | WOTF |  |  |  | WOTF 1b
SO | 10 | ERCOT/TSP/Generator voltage management practices | WOTF |  |  |  | WOTF 1c
SO | 11 | Review Operating Guide re: reactive and voltage requirements which are unclear, confusing, ambiguous |  |  | OGRR
SO | 12 | Low Voltage Ride-Through (LVRT) for WGRs |  |  | OGRR 208
SO | 13 | Performance metrics for wind
SO | 14 | Evaluate transmission line and wind power production criteria | WOTF |  |  |  | WOTF 3e
SO | 15 | 24/7 communication must be available for TSP to reach wind generators. | WOTF |  | OGRR |  | WOTF 2a
SO | 16 | Wind generation ramp rate limitations | ROS |  | PRR 771 | Approved by TAC | WOTF 3a
SO | 17 | Mid Term and Short Term Load Forecast weather sensitivity | WOTF | N/A |  | COMPLETE | WOTF 3b
SO | 18 | Evaluate transmission line and wind power production outage criteria | WOTF/CWMG |  |  |  | WOTF 3e
SO | 19 | Run multiple CSC limit studies | WOTF | N/A | N/A | COMPLETE | WOTF 3f
SO | 20 | Dynamic line ratings | WOTF | N/A | N/A | COMPLETE | WOTF 3g
SO | 21 | Reexamine EECP Steps | OWG |  | PRR 769 NPRR 142 | Approved by TAC | WOTF 3h
SO | 22 | Operational studies (ramp rate, load low situations, forecasting)

## System Planning
ERCOT
Renewable Technology Working Group (RTWG)
List of System Planning Issues
Issue Category | Issue No. | Description | Assigned to: | Priority | Revision Mechanism | Status | Other Ref. No.
SP | 1 | Verify technical data (installed technology)
SP | 2 | Verify computer models for wind generation
SP | 3 | Planning criteria studies (stability, fault, steady-state)
SP | 4 | ERCOT Stability Study

## WT
ERCOT
Renewable Technology Working Group (RTWG)
List of Workshop/Training Opportunities
Issue Category | Issue No. | Description | Assigned to: | Priority | Revision Mechanism | Status | Other Ref. No.
WT | 1 | WGR QSE Resource Plan and Energy Schedule Update Process
WT | 2 | ERCOT Wind Workshop III - Spring 2009
WT | 3 | WGR Operator Training

## Summary
ERCOT
Renewable Technology Working Group (RTWG)
List of Issues
No. | Issue Category | Issue No. | Description | Assigned to: | Priority | Revision Mechanism | Status
1 | MD | 1 | Options to ancillary services allocations: Cost allocation | CATF | 0 | 0 | 0
2 | MD | 2 | Options to ancillary services allocations: Procurement Optimization | QMWG | 0 | 0 | 0
3 | MD | 3 | Non-Spin requirements | 0 | 0 | 0 | 0
4 | MD | 4 | Consideration of new ancillary service products | 0 | 0 | 0 | 0
5 | MD | 5 | Storage technologies benefits (e.g., flywheels) to the integration of wind and provision of necessary ancillary services (regulation, responsive reserves) | 0 | 0 | 0 | 0
6 | MD | 6 | Ancillary Service procurement methodology (Increase RGS, RRS, NSRS during high risk periods) | WOTF | 0 | 0 | 0
7 | MD | 7 | Protocol changes to allow wind resources to provide ancillary services | 0 | 0 | PRR | 0
8 | MD | 8 | Review Protocol re: reactive and voltage requirements which are unclear, confusing, ambiguous | 0 | 0 | PRR | 0
9 | MD | 9 | Review nodal protocols for proper treatment of wind generation re: dispatch response | 0 | 0 | NPRR | 0
10 | MD | 10 | Review nodal protocols for proper treatment of wind generation re: performance metrics with negative pricing | 0 | 0 | NPRR | 0
11 | MD | 11 | Review nodal protocols for proper treatment of wind generation re: base point deviaton charges as applicable to wind generation | 0 | 0 | NPRR | 0
12 | MD | 12 | WGR LSL as % of HSL | QMWG | 0 | PRR 773 | Approved by TAC
13 | MD | 13 | Mandate use of AWST 80% forecast in wind Resource Plans | 0 | N/A | PRR 763 | COMPLETE
14 | SO | 1 | Update forms used by ERCOT to gather generator data so that WGRs can provide accurate information | 0 | 0 | 0 | 0
15 | SO | 2 | Identifying nodal tools to more effectively integrate wind into the grid | 0 | 0 | 0 | 0
16 | SO | 3 | Response to down balancing instructions (QMWG); SCE issues, clarity on expected following instructions, requirements | 0 | 0 | 0 | 0
17 | SO | 4 | Smart grid and demand response implications on market design and integration of renewable resources | 0 | 0 | 0 | 0
18 | SO | 5 | Impact of plug-in hybrid vehicles on storage and use of renewable resources | 0 | 0 | 0 | 0
19 | SO | 6 | Qualification testing of reactive capability for wind generation | 0 | 0 | 0 | 0
20 | SO | 7 | High frequency: Develop alternate solutions | WOTF | 0 | 0 | 0
21 | SO | 8 | System Inertia/Governor Generator Response | PDCWG | 0 | 0 | 0
22 | SO | 9 | Better defined SCADA control on generation breakers | WOTF | 0 | 0 | 0
23 | SO | 10 | ERCOT/TSP/Generator voltage management practices | WOTF | 0 | 0 | 0
24 | SO | 11 | Review Operating Guide re: reactive and voltage requirements which are unclear, confusing, ambiguous | 0 | 0 | OGRR | 0
25 | SO | 12 | Low Voltage Ride-Through (LVRT) for WGRs | 0 | 0 | OGRR 208 | 0
26 | SO | 13 | Performance metrics for wind | 0 | 0 | 0 | 0
27 | SO | 14 | Evaluate transmission line and wind power production criteria | WOTF | 0 | 0 | 0
28 | SO | 15 | 24/7 communication must be available for TSP to reach wind generators. | WOTF | 0 | OGRR | 0
29 | SO | 16 | Wind generation ramp rate limitations | ROS | 0 | PRR 771 | Approved by TAC
30 | SO | 17 | Mid Term and Short Term Load Forecast weather sensitivity | WOTF | N/A | 0 | COMPLETE
31 | SO | 18 | Evaluate transmission line and wind power production outage criteria | WOTF/CWMG | 0 | 0 | 0
32 | SO | 19 | Run multiple CSC limit studies | WOTF | N/A | N/A | COMPLETE
33 | SO | 20 | Dynamic line ratings | WOTF | N/A | N/A | COMPLETE
34 | SO | 21 | Reexamine EECP Steps | OWG | 0 | PRR 769 NPRR 142 | Approved by TAC
35 | SO | 22 | Operational studies (ramp rate, load low situations, forecasting) | 0 | 0 | 0 | 0
36 | SP | 1 | Verify technical data (installed technology) | 0 | 0 | 0 | 0
37 | SP | 2 | Verify computer models for wind generation | 0 | 0 | 0 | 0
38 | SP | 3 | Planning criteria studies (stability, fault, steady-state) | 0 | 0 | 0 | 0
39 | SP | 4 | ERCOT Stability Study | 0 | 0 | 0 | 0
40 | WT | 1 | WGR QSE Resource Plan and Energy Schedule Update Process | 0 | 0 | 0 | 0
41 | WT | 2 | ERCOT Wind Workshop III - Spring 2009 | 0 | 0 | 0 | 0
42 | WT | 3 | WGR Operator Training | 0 | 0 | 0 | 0
MD = Market Design
SO = System Operations
SP = System Planning
WT = Workshop/Training