## Slide 1: Texas Nodal Program Implementation: Program Update
Ron Hinsley

## Slide 2: Agenda
Health Indicators
Highlights
Steps to Finalize Schedule and Budget
Preliminary Schedule
Preliminary Budget
Top Risks / Issues
Notes: <number>
<footer>
<header>
<date/time>
<number>

## Slide 3: Health Indicators
Indicator | Status | Explanation
Overall | Red | Overall status remains red, driven by schedule and budget indicators
Schedule | Red | Schedule remains red until the integrated schedule is approved
Budget | Red | Budget remains red until new budget is finalized and approved
Scope | Amber | Requirements review still underway
Resources | Green | Majority of projects reporting green status
Risks | Amber | Program addressing risks/issues detailed on subsequent slide
Issues | Amber | Program addressing issues/issues detailed on subsequent slide
Quality Control | Red | Status driven by number of Sev 1 and 2 defects and lengthy defect turn-around time
ERCOT Readiness | Amber | Status quo until the schedule is released
Market Participant Readiness | Amber | Status quo until the schedule is released
Note: health indicator measures are located in the appendix

## Slide 4: Highlights
Reminder: the program posts a weekly status report to the nodal website: http://nodal.ercot.com/docs/po/index.html
No tasks on the program critical path are currently behind schedule
Resource Asset Registration Form (RARF) data is now 98%
  The remaining 2% is spread across 59 RARFs
  EDS is working individually with MPS to correct remaining errors
EMS Outage Evaluation, Voltage Support, Interfaces, and Displays release completed FAT on Nov. 14th
MMS4 FAT testing for Patch5 completed on Nov. 20th (this is four workdays ahead of schedule)
Defect update – no change since last time
Utilicast, the company conducting Nodal program audits, began work onsite starting Nov. 10th

## Slide 5: Steps to Finalize Schedule and Budget
Step | Activity
1 | Present schedule to TPTF for initial review
2 | Incorporate TPTF feedback into schedule and identify budget impacts
3 | Present revised schedule to TPTF for final review
4 | Incorporate final TPTF feedback; finalize budget draft
5 | Present to TAC and incorporate feedback
6 | Present to Special Nodal Program Committee and incorporate feedback
7 | Present to Board of Directors and incorporate feedback
8 | Present to PUCT

## Slide 6: Preliminary Schedule – Key Points
Vendor product development is nearly complete (75-80%)
Business processes and protocols traceability need to be completed
System integration started in October 2008
Testing and defect resolution is ongoing for all projects
Market trials and production readiness, including go-live, will take 10.5 months and we should not shortcut this
This schedule is preliminary pending TPTF review

## Slide 7: Top Contributors to Delay
Jan 1 2009 date was overly aggressive; requirements were not complete; insufficient program controls in place to identify early schedule problems
Under-estimated the effort, time required, and complexity of several key areas:
  Common Information Model (CIM) data validation was started late and was significantly more complex than anticipated; delays in this area required an additional release of the MMS software from ABB, adding several months to the timeline for regression testing
  AREVA CIM importer to move data from the CIM into the Energy Management System was more complex than anticipated by ERCOT or AREVA
Vendor software delivery delays undermined the “early delivery systems” approach that was designed to give Market Participants early access to the systems. New delivery dates and coordination across vendors resulted in several months being added to the new schedule
Decision to skip integration testing was a bad decision, introducing unacceptable quality
Under-estimated the time required for bug fixes by several months in the original schedule
Project teams were not organized to support end-to-end program delivery

## Slide 8: Timeline – Accomplishments to Date (visual)

## Slide 9: Timeline – Accomplishments to Date
Oct 2007 | Real-time status and validation of generation and transmission data complete (EDS 1) Real-time market execution and pricing started (and continues) Real-time locational market prices (LMPs) posted
Feb 2008 | Large hardware/software/data migration complete
Mar 2008 | ERCOT held mock Congestion Revenue Rights Auction
May 2008 | ERCOT executed Day Ahead and Adjustment Period Market
Jun 2008 | Real time market and Load Frequency Control of entire ERCOT system for 2 hours
Oct 2008 | CIM schema finalized Integration Release 3 started
Nov 2008 | State Estimator standard achieved for first time with improved telemetry, reaching the quality measure of 97% convergence
Nov 2008 | System Operations Testing Environment (SOTE) available for TSP access
Nov 2008 | 75-80% of vendor software delivered to ERCOT
2008 | Numerous reports and extracts completed; electronic file formats provided to Market Participants
Notes: EDS 1: point to point check out (telemetry) Approved by TPTF
Real time market execution and pricing started – SCED (6 months of SCED)

## Slide 10: Timeline – Work Remaining (visual)

## Slide 11: Timeline – Work Remaining
Dec 2008 | Integration Release 3 completes
Jan 2009 | Synchronized version of CIM XML file for EMS, MMS, and CRR
Jan 2009 – Aug 2009 | Final version MMS software delivered and regression tested
Jan 2009 – Jul 2009 | Integration Release 4
Jul 2009 – Feb 2010 | Integration Release 5
Jul/Aug 2009 | NMMS Single Entry Model go-live
Feb 2010 | Prepare for market trials
Mar 2010 | Restart market trials
Apr 2010 | Execute Day Ahead Market (DAM) and Reliability Unit Commitments (RUC) Publish settlements for DAM Conduct Congestion Revenue Rights (CRR) auction
May 2010 | Execute DAM fives days per week Publish real-time settlement statements Conduct 2-hour and 8-hour Load Frequency Control (LFC) tests
Jun 2010 | Test full market timeline for 7 days and settle the market Conduct operational readiness testing (disaster recovery, failover testing)
Jul 2010 | Conduct 48-hour LFC test Conduct integrated CIM business process testing
Aug 2010 | Verify LMP quality Conduct DAM/RUC Security Constrained Economic Dispatch (SCED) performance test
Sep 2010 | Conduct 48-hour full market timeline test and prepare for 168-hour test
Oct 2010 | Complete the 168-hour test and begin the Go-Live Period
Dec 2010 | Nodal Go-Live
Expectations for Market Participants
Notes: <number>
<footer>
<header>
<date/time>
Apr 2010: CRR auction is a mock auction, similar to previous mock auction runs for monthly and annual auctions; uses live data but non-binding results.
Jul 2010: 48-hr LFC test is controlling grid for 2-days.
Sep 2010: 48-hour full market timeline test is exercising all systems on proper timeline for 2 days straight – but not control the grid.

## Slide 12: Preliminary Budget by Cost Element
Nodal Implementation Preliminary Budget |  |  |  |  | 
Estimate at complete (EAC) | Budget | Actuals |  |  | Forecast
 |  | Oct-08 |  |  | 
 | Approved Budget | Life to Date | Subtotal Forecast |  | Total (Actuals + Forecast)
COST SUMMARY ($) |  |  |  |  | 
Internal Labor Costs | 35,858,381 | 31,224,298 | 63,611,857 |  | 94,836,155
External Resource Costs | 175,093,797 | 182,490,058 | 113,063,658 |  | 295,553,716
Administrative & Employee Expenses | 7,614,628 | 1,624,547 | 1,524,663 |  | 3,149,210
Software & Software Maintenance | 17,053,096 | 19,138,962 | 17,099,415 |  | 36,238,377
Hardware & Hardware Maintenance | 42,103,029 | 44,722,227 | 11,694,438 |  | 56,416,665
Contingency | 15,000,000 | - | 39,888,788 |  | 39,888,788
Total Direct Project Costs | 290,722,931 | 279,200,092 | 246,882,819 |  | 526,082,911
Backfill | 1,422,626 | 2,937,759 | 4,953,421 |  | 7,891,180
Indirect Support Costs | 10,589,195 | 9,848,091 | 8,616,857 |  | 18,464,948
Facilities Support Allocation | 4,126,574 | 5,511,383 | 2,494,185 |  | 8,005,567
Finance Charge** | 10,600,000 | 11,286,700 | 88,268,693 |  | 99,555,393
Total Indirect Project Costs | 28,738,395 | 29,583,933 | 104,333,156 |  | 133,917,089
Total Project Costs | 319,461,326 | 308,784,025 | 351,215,975 |  | 660,000,000
**Finance Charge of $88.2M is inclusive of new finance charges recovered during Nodal Surcharge Recovery Period
**Finance Charge of $10.6M represents estimated finance costs through Dec 2008 only (development period), additional finance charges
of $31.6M were assumed during the debt repayment period for a total of $42.2M for the entire Program

## Slide 13: Cost Elements
Internal Labor Costs
  Labor costs of ERCOT employees who are working on the Nodal program.
External Resource Costs
  Includes both contractor and vendor expenses. Examples of the two types of expenses would be contingent labor contracted to work on the Nodal program, and also software development expenses from the software vendors (ABB, AREVA, etc…). Contractor labor is for staff augmentation where ERCOT does not have the number of employees required to perform the additional Nodal project work or where ERCOT does not have employees with the skills to perform the work.
Administrative & Employee Expenses
  Equipment, tools, office materials & supplies. Also includes ERCOT employee expenses. For example, the expenses for trips by ERCOT employees to vendor sites to supervise software development would fall into this category.
Software
  Expenses for purchased 3rd party software not being developed solely for the Nodal program. For example, this would include a wide variety of software ranging from Oracle database licenses to Microsoft Windows Server licenses. Also in this cost category are the maintenance expenses associated with the software licenses.
Hardware
  Includes all computer hardware purchased to enable the Nodal market and the future maintenance on this equipment. Examples would be servers, data storage hardware and networking equipment.

## Slide 14: Cost Elements (continued)
Backfill
  This category represents the difference between ERCOT’s labor expense for an internal employee and a contractor hired to perform that employee’s duties while that employee is working on the Nodal program. For example, if the fully loaded cost to ERCOT for an employee was $50/hr and that employee was reassigned from ERCOT base operations to the Nodal program and a contractor was hired at $70/hr to perform the base operations duties while the employee is working on the Nodal program, the cost to the Nodal program is the difference between the two expenses, in this case $20/hr.
Indirect Support Costs
  Several ERCOT administrative departments charge the Nodal program an allocation for services provided to Nodal. For example, ERCOT Procurement, Finance, Legal, and some others provide their services to the Nodal program. The amount charged to the Nodal program is based on an allocation that has been audited and approved.
Facilities Allocation
  Similar to the Indirect Support Costs category, the Facilities Allocation is a reimbursement to ERCOT base operations from the Nodal program for the facilities space and services provided by ERCOT to the Nodal program.
Finance Charge
  Interest expenses related to debt incurred to finance the Nodal program.

## Slide 15: Preliminary Budget by Project
Project | Current Approved Budget | Preliminary Revised Budget | Variance
IT Operations & Infrastructure (INF) | 65,400,015 | 132,761,230 | 103.0%
Market Management System (MMS) | 50,527,343 | 79,862,883 | 58.1%
Integration Testing (INT) | 17,907,527 | 42,229,395 | 135.8%
Early Delivery System (EDS) | 19,311,548 | 37,178,516 | 92.5%
Energy Management System (EMS) | 20,913,735 | 36,440,056 | 74.2%
Commercial Systems (COMS) | 16,022,542 | 29,717,150 | 85.5%
Enterprise Integration (EIP) | 18,963,151 | 26,832,020 | 41.5%
Program Control (PC) | 9,092,381 | 20,525,874 | 125.7%
ERCOT Readiness (ERT) | 6,767,763 | 20,100,060 | 197.0%
Network Model (NMMS) | 13,709,494 | 16,364,647 | 19.4%
MER – Training | 9,137,503 | 12,020,952 | 31.6%
Integration Design (IDA) | 8,876,607 | 10,995,342 | 23.9%
Congestion Revenue Rights (CRR) | 7,605,047 | 8,980,757 | 18.1%
Enterprise Data Warehouse (EDW) | 3,655,570 | 7,098,125 | 94.2%
Market Information System Portal (MIS) | 9,255,331 | 6,096,552 | -34.1%
Administration | 16,715,769 | 33,352,259 | 99.5%
Contingency | 15,000,000 | 39,888,788 | 165.9%
Finance Charges** | 10,600,000 | 99,555,393 | 839.2%
Total | 319,461,326 | 660,000,000 | 106.6%
**Finance Charge of $99.5M is inclusive of the previous finance charges and new finance charges recovered during Nodal Surcharge
Recovery Period
**Finance Charge of $10.6M represents estimated finance costs through Dec 2008 only (development period), additional finance charges of
$31.6M were assumed during the debt repayment period for a total of $42.2M for the entire Program

## Slide 16: Preliminary Forecast Spend by Month
$M
**Chart does not include finance charges or contingency**

## Slide 17: Top Risks / Issues
Description | Status
NEW RISK: With the delayed go-live for Nodal, there are a number of Zonal projects, PRRs, and IMM suggestions for Zonal improvements that may result in resource constraints for Nodal. | Currently in process of identifying potential resource conflicts so that ERCOT can reprioritize scheduled Nodal activities and/or identify new resources to perform the additional work.
NEW RISK: In order to keep the multiple database environments in synch (Dev, iTest, Prod), a refresh of the associated databases must be completed. This activity is estimated to take approximately one month based on prior refreshes. Actual downtime is estimated at one to two weeks and has not been incorporated into the schedule. | Tentatively scheduled for March 2009; working closely with Nodal project teams to minimize downtime impacts.
Information Lifecycle Management (ILM) strategy for ERCOT is behind schedule. Problem: Current processes do not adequately address archival and storage requirements for Nodal; Existing Data Center constraints limit new storage growth Without ILM in place and executed, the nodal program go-live date could be delayed because of insufficient storage | Assigning a PM to manage a project to develop an ILM strategy and implement the strategy Project funds have been identified Project to be managed by Business, IT and Nodal

## Slide 18
Appendix

## Slide 19: Health Indicator Measures
Metric | Green | Amber | Red
Overall | Both core indicators are green | At least one core indicator is amber, but none are red | At least one core indicator is red
Schedule | All activities on the critical path are complete, or are expected to be complete, on or ahead of the planned dates | No dates have been missed, but one or more critical path activities is forecasted to complete late | At least one critical path deliverable has missed its due date. Project implementation date is in jeopardy
Budget (hrs) | Project forecasted to complete within the baselined hours | Project forecasted to complete up to 5% over the baselined hours | Project forecasted to complete more than 5% over the baselined hours
Scope | All Requirements approved; no unplanned scope changes | Pending approvals for Requirements; no unplanned scope changes | Unapproved Requirements and/or unplanned scope changes
Resources | All key resource positions are filled and no schedule delays are expected. | One or two key positions are not staffed and the schedule may be adversely impacted. | More than two key positions are not staffed and the schedule will be impacted.
Risk | All project risks have a Risk Score =< 4 | At least one project risk has a Risk Score => 5 and =< 8 | At least one project risk has an Risk Score => 9
Issues | All issues are being resolved by the required due dates | Some issues are remaining open past the required due dates but none are of “critical” priority (Impact = 3 or 4) | At least one “critical” priority issue (Impact = 3 or 4) is open past the due date
Quality Control | Defect metrics meet all of the following: # of Severity 1 = 0 # of Severity 2 = 0 Avg. #. Days to Close Sev 1 and Sev 2 Defects < 45 % Reopen Defects < 15 | Defect metrics meet at least one of the following: # of Severity 1 = 1 to 5 # of Severity 2 = 1 to 5 Avg. # Days to Close Sev 1 and Sev 2 Defects => 45 and =< 90 % Reopen => 15 and =< 24 | Defect metrics meet at least one of the following: # of Severity 1 > 5 # of Severity 2 > 5 Avg. # Days to Close Sev 1 and Sev 2 Defects >90 % Reopen >24

## Slide 20
Questions?