|  |  | System Planning Division |
| --- | --- | --- |
|  |  | Monthly Status Report to Reliability and Operations Subcommittee for November 2008 |
|  | Report Highlights |  |
| Item |  |  |
| 1. | ERCOT is currently tracking 244 active generation interconnection requests totaling over 102,000 MW. This includes almost 48,000 MW of wind generation. 2,010 MW of new generation began commercial operation in November, of which 332 MW was gas-fired and 1,678 MW was from wind turbines, bringing the currently installed total of wind power capacity to 7,912 MW. |  |
| 2. | Regional Planning is currently reviewing proposed transmission improvements with a total cost of $471 Million Transmission Projects approved in 2008 to date total $255 Million All projects (in engineering, routing, licensing and construction) totals approximately $4.1 Billion Transmission Projects energized in 2008 total about $453 Million |  |

Table of Contents

1.	Generation Interconnection	1

1.1	New Generation Beginning Commercial Operations	1

1.2.     Summary of Active Generation Interconnection Requests	1

1.3	Potential Future Generation Interconnections	2

# 1.	Generation Interconnection

Additional information regarding detailed generation interconnection and impact studies is contained in the “Generation Project Interconnection Information” folder in the “Operations and System Planning” area on the ERCOT website:  http://planning.ercot.com/login/login.

## New Generation Beginning Commercial Operations

## Victoria Power Station (08INR0050) Combined Cycle in Victoria County for 332 MW

# Turkey Track Wind Energy (07INR0011) in Nolan County for 170 MW

# Hackberry Wind Farm (07INR0011e) in Shackelford County for 165 MW

# Pyron Wind Farm (07INR0045a) in Scurry County for 249 MW

# Bull Creek Wind Plant (07INR0037) in Borden County for 180 MW

# Elbow Creek Wind Farm (08INR0053) in Howard County for 117 MW

# Inadale Wind Farm (07INR0045b) in Scurry County for 197 MW

# Panther Creek 2 Wind Farm (08INR0037) in Scurry County for 115 MW

# Gulf Wind I (05INR0015a) in Kenedy County for 283 MW

# Penascal Wind  (06INR0022a) in Kenedy County for 202 MW

## The total installed wind capacity is now 7,912 MW, of which 7,254 (92%) is located within the Western Congestion Management Zone.

## Summary of Active Generation Interconnection Requests

| GENERATION INTERCONNECTION REQUESTS CURRENTLY BEING PROCESSED |
| --- |
| Currently tracking 244 active generation interconnection or change requests |
| As of November 30, 2008 | North | South | West | Total |
| Security Screening Study | 3 | 8 | 12 | 23 |
| SSS Completed | 4 | 16 | 23 | 43 |
| Full Interconnect Study | 36 | 30 | 80 | 146 |
| FIS Completed | 1 | 8 | 0 | 9 |
| Interconnect Agreement Completed | 6 | 7 | 10 | 23 |
| Capacity under Interconnection Agreements | 3,516 | 2,578 | 1,413 | 7,507 |
| Capacity for Grid, MW | 25,396 | 36,643 | 40,110 | 102,149 |
| Wind Capacity, MW | 2,047 | 9,910 | 35,927 | 47,884 |

| Fuel Type | Non-Public (MW) | Public (MW) | Grand Total (MW) |
| --- | --- | --- | --- |
| Gas-CC | 22,790 | 5,187 | 27,977 |
| Gas-CT | 1,353 | 505 | 1,858 |
| Nuclear | 3,200 | 9,186 | 12,386 |
| Coal | 5,375 | 4,131 | 9,506 |
| Wind | 40,691 | 7,194 | 47,884 |
| Solar | 863 | 0 | 863 |
| Biomass | 50 | 145 | 195 |
| Other | 1,480 | 0 | 1,480 |
| Grand Total | 75,802 | 26,348 | 102,149 |

## Potential Future Generation Interconnections

The table below summarizes the publicly known potential future generation projects for the ERCOT region.  (IA=Interconnect Agreement, PL=Public Letter, XX= cancelled)

| Future Generation Interconnections (Public Projects) as of November 30, 2008 |
| --- |
| INR | SiteName | Status | County | Region | COD | Fuel | MW For Grid | Change from Last Report |
| 07INR0036 | Coyote Run Windfarm | IA | Borden | West | Mar-09 | Wind | 225 |  |
| 08INR0025 | Pistol Hill Energy Center | PL | Ector | West | Mar-09 | Wind | 300 | Date |
| 08INR0046 | Bosque Expansion | IA | Bosque | North | Mar-09 | Gas-CC | 255 |  |
| 08INR0065 | Buffalo Gap 4 and 5 | PL | Nolan | West | Mar-09 | Wind | 465 |  |
| 09INR0026a | Sterling Energy Center | PL | Sterling | West | Mar-09 | Wind | 200 | Date |
| 07INR0027 | S Houston Green Power Exp Prj1 | IA | Galveston | South | Apr-09 | Gas-CC | 244 |  |
| 07INR0028b | Goat Wind - phase 2 | IA | Sterling | West | Apr-09 | Wind | 70 |  |
| 09INR0072 | Dansby3 | PL | Brazos | North | Apr-09 | Gas-CT | 48 |  |
| 08INR0012 | Papalote Creek Wind Farm | IA | San Patricio | South | May-09 | Wind | 180 |  |
| 08INR0040 | Lenorah Project | PL | Martin | West | May-09 | Wind | 350 |  |
| 09INR0060 | Stephens Wind Farm | PL | Borden | West | May-09 | Wind | 141 |  |
| 08INR0035 | Cedar Bayou 4 | IA | Chambers | South | Jun-09 | Gas-CC | 539 |  |
| 08INR0059 | Gray Wind Project | XX | Borden | West | Dec-08 | Wind | 141 | Cancelled |
| 09INR0026 | Sterling Energy Center | PL | Sterling | West | Jun-09 | Wind | 300 |  |
| 09INR0036 | McAdoo Energy Center II | PL | Dickens | West | Jun-09 | Wind | 500 |  |
| 09INR0006a | Oak Grove SES 1 | IA | Robertson | North | Jul-09 | Coal | 855 |  |
| 08INR0003 | Sandow 5 | IA | Milam | North | Jul-09 | Coal | 581 |  |
| 09INR0027 | Winchester Power Park | IA | Fayette | South | Jul-09 | Gas-CT | 178 |  |
| 05INR0015b | Gulf Wind 2 | PL | Kenedy | South | Sep-09 | Wind | 400 |  |
| 08INR0033 | Lufkin | IA | Angelina | North | Sep-09 | Biomass | 45 |  |
| 09INR0015 | Comanche Peak 1&2 Upgrade | PL | Somervell | North | Oct-09 | Nuclear | 86 |  |
| 08INR0018 | Gunsight Mountain | IA | Howard | West | Oct-09 | Wind | 120 |  |
| 09INR0028 | V H Braunig 6 | PL | Bexar | South | Oct-09 | Gas-CT | 185 |  |
| 09INR0039 | Nueces Bay 7 Repowering | IA | Nueces | South | Nov-09 | Gas-CC | 327 |  |
| 09INR0038 | Barney Davis 2 Repowering | IA | Nueces | South | Nov-09 | Gas-CC | 360 |  |
| 09INR0045 | Sand Hill Peakers | PL | Travis | South | Nov-09 | Gas-CT | 94 |  |
| 08INR0038 | M Bar Wind | PL | Andrews | West | Dec-09 | Wind | 194 |  |
| 09INR0034 | Gatesville Wind Farm | PL | Coryell | North | Dec-09 | Wind | 200 |  |
| 09INR0047 | Loraine Windpark | IA | Mitchell | West | Dec-09 | Wind | 251 | New |
| 06INR0029 | Jackson Mountain | IA | Nolan | West | Jan-10 | Wind | 90 |  |
| 09INR0006b | Oak Grove SES 2 | IA | Robertson | North | Jan-10 | Coal | 855 |  |
| 09INR0037 | Scurry County Wind III | PL | Scurry | West | Mar-10 | Wind | 350 |  |
| 06INR0006 | Cobisa-Greenville | PL | Hunt | North | May-10 | Gas-CC | 1,750 |  |
| 09INR0002 | J K Spruce 2 | IA | Bexar | South | Jun-10 | Coal | 750 |  |
| 05INR0015c | Gulf Wind 3 | PL | Kenedy | South | Sep-10 | Wind | 400 |  |
| 06INR0012b | Sherbino Mesa Wind Farm 2 | IA | Pecos | West | Oct-10 | Wind | 150 |  |
| 06INR0026 | Wild Horse Mountain | IA | Howard | West | Dec-10 | Wind | 120 |  |
| 12INR0003 | Throckmorton Wind Farm | PL | Throckmorton | West | Dec-10 | Wind | 400 |  |
| 10INR0020 | Panda Temple Power | PL | Bell | North | May-11 | Gas-CC | 1,092 |  |
| 10INR0010 | Jack County 2 | PL | Jack | North | Jun-11 | Gas-CC | 620 |  |
| 09INR0007 | Nacogdoches Project | PL | Nacogdoches | North | Apr-12 | Biomass | 100 |  |
| 07INR0004 | Pampa Energy Center | PL | Gray | West | May-12 | Coal | 165 |  |
| 09INR0001 | Sandy Creek 1 | IA | McLennan | North | Jun-12 | Coal | 925 |  |
| 09INR0024 | B&B Panhandle Wind | PL | Carson | West | Jun-12 | Wind | 1,001 |  |
| 12INR0004 | Fort Concho Wind Farm | PL | Tom Green | West | Jul-12 | Wind | 400 |  |
| 04INR0011b | Mesquite Wind Phase 4 | IA | Shackelford | West | Jun-13 | Wind | 136 |  |
| 04INR0011c | Cottonwood Wind | IA | Shackelford | West | Jun-13 | Wind | 100 |  |
| 15INR0002 | Comanche Peak 3 and 4 | PL | Somervel | North | Jan-15 | Nuclear | 3,200 |  |
| 15INR0008 | STP 3 and 4 | PL | Matagorda | South | Jan-15 | Nuclear | 2,700 |  |
| 11INR0011 | Victoria City Nuclear | PL | Victoria | South | Jan-15 | Nuclear | 3,200 |  |
|  |  |  |  |  |  |  | 26,348 |  |

# Regional Planning Group Project Reviews

# American Electric Power Service Corporation submitted a project to construct 2 new 138 kV substations, rebuild a 138 kV circuit, build  2 new 138 kV circuits, and install a new 138/69 kV autotransformer in the Abilene/San Angelo area.  The estimated cost of this project is $105.9 M.  This project is in ERCOT Independent Review.

# Luminant submitted a set of projects to reduce North to South Congestion.  It consists of several 138 kV line upgrades and series reactor installations.  The total cost for all projects is approximately $31 M. This project is in ERCOT Independent Review.

# AEPSC submitted a project to add a 345 kV Transmission Substation at the point in Haskell County where the Oklaunion to Mulberry Creek and Tonkawa to Graham 345 kV lines cross called Clear Crossing and construct a new 345 kV transmission circuit from the existing Oklaunion Substation to the Bowman Substation.  This project was a result of the 2007 Five-Year Plan.  Clear Crossing is projected to be in service by peak 2010 with a cost of $14 M.  The Oklaunion to Bowman 345 kV line is estimated to be in service by the end of 2011 with a cost of $ 71 M.  The need for the Oklaunion to Bowman part of the project has been established by the PUC Docket 33672.  Determination of the builder of this project will be decided in PUC Docket 35665.  RPG Review of this part of the project can not continue.  RPG review of the Clear Crossing part of this project is in ERCOT Independent Review.

# Oncor submitted a project to install an additional 300 MVar of dynamic reactive at Renner station.  The estimated cost of this project is $ 35 M with an in-service of 2010.  This project is in ERCOT Independent Review.

# Oncor submitted a project to relieve congestion related to new wind units in the Lamesa area.  The project will upgrade the Lamesa to Bluff Creek 138 kV line, rebuild the Bluff Creek to China Grove 138 kV line, rebuild the Lamesa to Ackerly Vealmoor 69 kV line to 138/69 kV double circuit, rebuild the Lamesa 138 kV switching station, build a new 138 kV Ackerly Vealmoor station, add second circuits to all rebuilt lines and include station upgrades at China Grove and Big Spring.  The cost of this project is $ 80.8 M.  This project will be reviewed to ensure that the improvements fit into the likely CREZ transmission solution for the area.  This project is in ERCOT Independent Review.

# Oncor submitted a project to add several 345 kV circuits to support the addition of Comanche Peak units 3 and 4 in 2015 at an estimated cost of $ 133 M.    These upgrades include a new 345 kV double circuit line with one circuit in place from Comanche to Whitney, a new 345 kV line from Comanche to Johnson Switch, a new circuit on existing structures from Johnson Switch to Everman, a new 345 kV double circuit with one circuit in place from Comanche to DeCordova, and a new 345 kV line on existing structures from Comanche to Parker Switch.  This project is in ERCOT Independent Review.

# Austin Energy submitted a project to establish a 138 kV circuit from Hicross to Slaughter Lane by building 2.2 miles of new transmission line to an unenergized 1.2 mile circuit segment.  This project will cost $5.774 M with an estimated completion date of October 2010.  This project is in the comment period.

# Other Notable Activities

All postings referred to below can be found at http://planning.ercot.com/login/login unless otherwise indicated.

- ERCOT Regional Planning is continuing work on the 2013 case to be used for reliability analysis and RPG analysis.  The purpose of this effort was to extend the 2007 Five-Year plan from 2012 to 2013.  The report of this study is being written as an addendum to the 2007 Five-Year plan and will be posted upon completion in late 2008 or early 2009.

- ERCOT TPIT report for 11/01/08 (4th Quarter) completed and posted on 11/26/08.