## Slide 1: MO Projects Financial Overview Commercial Operations Subcommittee December 8, 2008 Hope Parrish Market Operations Division Projects Organization

## Slide 2: 2008 MO PPL
Projects ABOVE the
current Capability Line
(Orange Shaded Area)
Projects BELOW the
current Capability Line
(Yellow Shaded Area)

## Slide 3: 2008 Project Health
Project # | Description | Go-Live | Within Schedule | Within Budget | Comments
40066_04 | Lodestar 4.7 Upgrade | 09/27/08 | No | Yes | Project was put on hold to avoid impacts from IO projects and release of L*4.7
50024_02 | Enhancements to SCR727-Market Enhancements | 11/01/07 | No | Yes | Delays due to resource constraints with Nodal and extended stabilization requests
50137_02 | Maestro Replacement - Phase 2 | 12/14/07 | Yes | Yes | 
60077_01 | ERCOT COM Registered Access | 06/20/08 | No | Yes | Delays due to cross dependency on for Google search tools under Nodal development
70038_01 | Collage Infrastructure Redesign | 03/14/08 | Yes | Yes | 
70048_01 | MV90xi System Upgrade | 05/09/08 | Yes | Yes | 
70057_01 | AMIT Study for Long-Term Settlement Solution | 11/21/08 | Yes | Yes | Move to Closing 12/15/2008
All projects committed to deliver in 2008 were achieved

## Slide 4: Financial Overview as of 12/21/2007
MO PPL Budget Activity | Amount | Notes/comments
Approved MO Capability Line Budget Funding | $1.32M | Current approved MO funding allocation Designates where the capability line falls $190K transferred from RO to MO to cover the AMIT Study
Current Forecast Spend of projects above the Capability Line | $1.27M | Based on current expectations for remaining accruals and closing activities
Budget Variance | ~$52k | Budget Variance is difference between MO Capability Line Budget Funding and Current Forecast Spend of projects above the Capability Line

## Slide 5: MO 2009 PPL approved by PRS

## Slide 6: Questions / Contact
Hope Parrish
Project Manager, MODPO
Market Operations Divisional Projects Organization
ERCOT
(512) 248-6522
hparrish@ercot.com
Notes: <number>