## Slide 1: Nodal COMS Update Commercial Operations Subcommittee December 8, 2008 Hope Parrish ERCOT - Market Operations Division Projects Organization

## Slide 2: Agenda
http://nodal.ercot.com <number>
Settlements & Billing, and Data Aggregation update
Registration and Disputes update
Credit monitoring and mgmt update
COMS Remaining Software Release Schedule
Commercial Systems Extracts update
Readiness Center Posting Location(s)
Questions

## Slide 3: COMS Project: S&B and Data Aggregation
http://nodal.ercot.com <number>
S&B and Data Aggregation
  Development
    S&B/Data Agg: Completed 100% of core nodal coding and functionally verified by business (Bundle migrated to iTEST)
      Outstanding code (to date): S&B/Data Aggregation source reports (not extracts), Memory workaround, additional error handling and performance tuning
    CSI: Completed over 210 of 222 of Lodestar Bill Determinants and verified by business
      Outstanding code (to date): Long Day/Short Day, remaining BDs, MMS4P6 and MMS5 refactoring
  Testing
    Migrated CORE Lodestar and CSI 5.4 and 6.1 releases to iTEST on 11/11/2008
    Completed smoke test of DAM event data from MMS to Lodestar core via Commercial System Integration Layer
  Major issues
    None at this point. We continue to manage the need for a synchronized dataset and have identified a workaround for the Lodestar product memory issue.

## Slide 4: COMS Project: Registration and Disputes
http://nodal.ercot.com <number>
Registration and Disputes
  Development:
    Registration Phase 5 - Siebel Refactoring Changes (MMS, MPIM, Dispute API and Other Integration Interfaces).
  Testing
    Registration 4 Release I-Test complete
    Migration scheduled 12/13/08; Verification 12/14/08
      Registration 4 Release includes:
        Calendar for Dispute Timeliness Calculations
        Bulk Upload process for RE/JOU creation
        Invoice Disputes
        Siebel Development of Dispute API Integration
        Siebel To Lodestar (REG  SNB) interface replacement.
  Discussion for COPS
    Discuss lead time for API certification testing
      Certification procedures posted for COPS review:
        COMS Disputes API Certificaton Process DRAFT.doc

## Slide 5: COMS Project: Credit Monitoring and Mgmt
http://nodal.ercot.com <number>
Development
  CMM 4.1
    Includes External Reports as part of NPRR138
    Custom Management of the internal Interface and application (screens, workflows, parameter adjustments)
      Outstanding code to date – Internal reports (4.2) and upgrade to latest software version of ROME5.0 (4.3)
Testing
  CMM 3.1 FAT complete
    Core Functionality (Calculations, ACL, and ACL file posting)
  CMM3.1 Integration Testing in progress
    All interface testing with CMM will be completed with CSI 6.1 and 6.3 test cycles
Major Issues
  Vendor and ERCOT Turnover resulted in delays to finalization of detailed analysis and designs of the internal custom management functions – scheduled for completion by 12/19/2008.

## Slide 6: Schedule Information for COMS Only Work Remaining – COMS 1
Project | Release | Description | FAT Complete
COMS | REG/DISP | REG4/DISP2: Migration to Production – Stage in current production environment | Dec 06 08
 | REG/DISP | COMS REG5/DISP3: Refactoring and Disputes API – iTEST Complete | Feb 17 09
 | Data Agg Core | Lodestar Bundle for Data Aggregation Re-Write (Initial) | Dec 19 08
 | CSI5.5 | Commercial Systems Integration with S&B | Jan 23 08
 | CSI6.3 | Commercial Systems Integration with CMM | Jan 23 08
 | S&B and Data Agg | Source Systems Reports - Internal | Feb 17 08
 | S&B and Data Agg | Source Systems Reports - External | Mar 04 09
 | CSI7.0 | Commercial Systems Integration Refactoring - MMS 5 S&B/CMM Long Day-Short Day | Apr 17 09
http://nodal.ercot.com <number>

## Slide 7: Schedule Information Work Remaining – COMS – 2
Project | Release | Description | FAT Complete
COMS | CMM4.1 | External Reports / Custom Management | Mar 31 09
 | CMM4.2 | Internal Reports / Bug Fix | Apr 24 09
 | CMM4.3 | Upgrade 5.0 / Bug Fix | May 22 09
 | FTGUI | Internal Financial Transfer GUI | May 19 09
**Nodal Program Schedule Review will be conducted at the 12/10/2008 TPTF Webex and the 12/15/2008 TPTF Meeting
http://nodal.ercot.com <number>

## Slide 8: COMS Project: Extracts & Reports Status
http://nodal.ercot.com <number>
COMS shadow settlements extracts have completed integration testing with limited stubbed data sets. Extracts will be retested when full functionality of all business process components are available.
  DAM Code and Mode Extracts
  RTM Code and Mode Extracts
  Public Reference Data Extract
  Settlement Input Data Extract
ERCOT is currently integration testing the following COMS extracts with limited datasets provided by internal business teams
  Market Participant Dispute Extract
  Settlement Calendar Extract
  Settlements Late Fee Extract
  ESIID Service History & Usage Extract
  ESIID Web Services – Provide Public Data Extract
Extract code will be regression tested with any future updates to metadata

## Slide 9: Readiness Center Reports, DDLs, and XSDs
http://nodal.ercot.com <number>
Nodal Reports Readiness Center
  The Nodal Data Services Master List (NDSML) is updated each Friday with the latest information. It is located at: http://nodal.ercot.com/about/news/2008/0118a.html
  The site will be updated each Friday with the latest extract & report specifications and DDLs and XSDs. http://nodal.ercot.com/readiness/reports/index.html

## Slide 10: Readiness Center Standard & Mock Statements and Invoices
http://nodal.ercot.com <number>
Mock CARD Invoice and Extracts | http://nodal.ercot.com/readiness/reports/si/kd/card_invoices_and_extracts.zip
Mock CRR Balancing Account Invoice | http://nodal.ercot.com/readiness/reports/si/kd/mock_crr_balancing_account_invoice_examples.zip
Mock DAM Late Fee Invoices | http://nodal.ercot.com/readiness/reports/si/kd/dam_late_fee_invoices.zip
Draft Invoices | http://nodal.ercot.com/readiness/reports/si/kd/Draft%20Invoices.zip
Draft Settlement Statements | http://nodal.ercot.com/readiness/reports/si/kd/draft_settlement_statements.zip
Mock DAM Settlement Examples | http://nodal.ercot.com/readiness/reports/si/kd/mock_dam_settlement_examples.zip
Release 8 Settlement Postings (Statements, Invoices, Extracts, Reports, Notices) | (http://nodal.ercot.com/readiness/eds4/documents/index.html)

## Slide 11
http://nodal.ercot.com <number>
Questions?