## Slide 1: Nodal Status Report: Program Update
Ron Hinsley

## Slide 2: Agenda
Highlights
Staffing
Top Risks / Issues
Schedule – Milestones
Budget
Notes: <number>
<footer>
<header>
<date/time>
<number>

## Slide 3: Highlights – 1
No tasks on the program critical path are currently behind schedule
Core Project Highlights
  NMMS delivered a synchronized model (v1.21 schema and data set) on Dec. 10th – a major milestone delivered on time
  Resource Asset Registration Form (RARF) data is now 98%
    The remaining 2% is spread across 59 RARFs
    EDS is working individually with MPS to correct remaining errors
  EMS Outage Evaluation, Voltage Support, Interfaces, and Displays release completed FAT on Nov. 14th. The team recently also completed FAT testing on the Habitat 5.6 Security Patch
  MMS4 FAT testing for Patch5 completed on Nov. 20th (this was four workdays ahead of schedule). MMS4 FAT testing for Patch6 is currently underway

## Slide 4: Highlights – 2
Core Project Highlights (continued)
  CRR completed FAT testing on their patch release last week. This completes FAT for their CRR4 release
  COMS completed FAT on their Registration/Disputes release (REG4/DISP2) on Dec. 10th and conducted a migration to production this past weekend
Defect update – no change since last time
Oversight and Audits
  Utilicast continues work to assess the Nodal program schedule and budget
  Detailed nodal program controls review held on Dec. 2nd with the Board’s Special Nodal Committee

## Slide 5: Staffing

## Slide 6: Top Risks / Issues
Description | Status
Existing integration testing strategy (i.e., planning approach, team structure, methodology), as well as the tactical implementation (i.e., execution plan, resource plan, testing schedules) may not be adequate to successfully perform integration. | A second ‘deep-dive’ review of the Integration methodology and staffing is being scheduled with Utilicast for the week of 12/15. The Integration Team is working to provide more specific task-level scheduling details for the utilization of Functional SMEs from the projects to support Functional Integration Test (FIT) and Business Scenarios (E2E) test execution activities. Meetings with core product PMs are underway. A new Integration Lab (iLab) environment is underway to support more integration component testing in parallel with FAT. The objective is to identify and resolve integration adaptor issues prior to migrating the applications and associated integration adaptors to iTest.
With the delayed go-live for Nodal, there are a number of Zonal projects, PRRs, and IMM suggestions for Zonal improvements that may result in resource constraints for Nodal. | Currently in process of identifying potential resource conflicts so that ERCOT can reprioritize scheduled Nodal activities and/or identify new resources to perform the additional work.
In order to keep the multiple database environments in synch (Dev, iTest, Prod), a refresh of the associated databases must be completed. This activity is estimated to take approximately one month based on prior refreshes. Actual downtime is estimated at one to two weeks and has not been incorporated into the schedule. | Tentatively scheduled for March 2009; working closely with Nodal project teams to minimize downtime impacts. Will also need to plan for another refresh in 2010.
Information Lifecycle Management (ILM) strategy for ERCOT is behind schedule. Current processes do not adequately address archival and storage requirements for Nodal; Existing Data Center constraints limit new storage growth. Without ILM in place and executed, the nodal program go-live date could be delayed because of insufficient storage. | SAIC has been engaged to complete the Road Map for an ILM strategy at ERCOT. Estimated 6 week effort, then the ILM Project will proceed

## Slide 7
Preliminary Schedule – Milestones – 1
Notes: There are printed copies of the milsetone charts available for TPTF members today.
A few things to point out:
The up and down arrows on the charts do not represent start and end dates. All milestones are end dates.
All critical path milestones have been achieved

## Slide 8
Preliminary Schedule – Milestones – 2

## Slide 9: Preliminary Budget by Cost Element
Nodal Implementation Preliminary Budget |  |  |  |  | 
Estimate at complete (EAC) | Budget | Actuals |  |  | Forecast
 |  | Oct-08 |  |  | 
 | Approved Budget | Life to Date | Subtotal Forecast |  | Total (Actuals + Forecast)
COST SUMMARY ($) |  |  |  |  | 
Internal Labor Costs | 35,858,381 | 31,224,298 | 63,611,857 |  | 94,836,155
External Resource Costs | 175,093,797 | 182,490,058 | 113,063,658 |  | 295,553,716
Administrative & Employee Expenses | 7,614,628 | 1,624,547 | 1,524,663 |  | 3,149,210
Software & Software Maintenance | 17,053,096 | 19,138,962 | 17,099,415 |  | 36,238,377
Hardware & Hardware Maintenance | 42,103,029 | 44,722,227 | 11,694,438 |  | 56,416,665
Contingency | 15,000,000 | - | 39,888,788 |  | 39,888,788
Total Direct Project Costs | 292,722,931 | 279,200,092 | 246,882,819 |  | 526,082,911
Backfill | 1,422,626 | 2,937,759 | 4,953,421 |  | 7,891,180
Indirect Support Costs | 10,589,195 | 9,848,091 | 8,616,857 |  | 18,464,948
Facilities Support Allocation | 4,126,574 | 5,511,383 | 2,494,185 |  | 8,005,567
Finance Charge** | 10,600,000 | 11,286,700 | 88,268,693 |  | 99,555,393
Total Indirect Project Costs | 26,738,395 | 29,583,933 | 104,333,156 |  | 133,917,089
Total Project Costs | 319,461,326 | 308,784,025 | 351,215,975 |  | 660,000,000
**Finance Charge of $88.2M is inclusive new finance charges recovered during Nodal Surcharge Recovery Period
**Finance Charge of $10.6M is inclusive only of finance charges through Dec 2008

## Slide 10
Cost: Element Summary
Variance
(over)/under
Cost Element
Budget
Actual
Budget
Internal Labor
$ 45.2
$ 46.5
$ (1.3)
External Labor
177.4
191.3
(13.9)
Hardware / Software
61.6
64.8
Travel and Other
11.5
7.2
4.3
Subtotal
$ 295.7
$ 309.8
$ (14.1)
Finance Charge
10.3
12.3
(2.0)
Total
$ 306.0
$ 322.1
$ (16.1)
Nodal Program
Cost Element Summary
($ Millions)
Through November 2008
When the integrated schedule has been finalized and the financial impact determined we will incorporate this into an updated forecast

## Slide 11
Questions?