## Sheet1
Category | Comment | From | Assigned to | Response
PMO | Luminant is concerned about the ongoing communication of FAT and Integration test results to Market Participants (MP) during 2009. In part, these communications are needed to provide information to the market regarding the functionality of the market systems under the various test market scenarios. We believe it is important that the market be provided an ongoing opportunity to understand the response of ERCOT systems to help in the design of internal market participant applications and confirm the continued accuracy of existing internal and MP-to-ERCOT interface applications. Additionally, Luminant is concerned that Market Participant involvement is assured when ERCOT is considering the resolution of FAT or Integration Test deficiencies that impact system functionality or existing Market Participant – to – ERCOT interface designs. Consequently, we would like to understand how ERCOT proposes to report the deficiencies, proposed resolutions and final resolutions to Market Participants. To the extent there is a role to be played by TPTF and the various market participant committees and subcommittees in this process, the responsibilities and response times for all need to be explicitly described. | Luminant | Murray
PMO | Assuming the proposed Nodal Integrated Schedule will be approved and implemented, how will it impact the responsibilities of Market Participants and associated timelines with those responsibilities? In particular, I am interested to know more details on the possible postponement of current participation in market trials and testing of software and required communication. This is a concern that I have heard from various Market Participants, specially the smaller ones who are financially in no position to maintain certain activities which are not urgent in the near future. | APX | Murray
PMO | Need to have a list of all project tasks that have less than 10 days of schedule float. | Reliant | Murray
Requirements | The work to be done for each project should include updating the Requirements documents and getting them reviewed and approved by TPTF? | Reliant | Betty
Requirements | Need to have a milestone of TPTF approving all final requirements documents and some assurances that no new functionality will be implemented without TPTF review and approval. | Reliant | Betty
Requirements | Where is the list of “go-live” requirements? | AEP | Betty
NPRRs | It should be noted that there are several NPRR in process that may impact the Nodal schedule. However, most all will probably not affect the critical path and can be done as part of the correction process to minimize costs. Later NPRR’s will need consideration as well. This may be difficult to hold for the next 2 years | AEP | Troy
NPRRs | The presentation under "Scope" states that "Nodal program scope included in the integrated schedule -- All NPRRs approved through Nov 22, 2008". It is our understanding that certain NPRRs in the "approval process," but not yet approved by the Board have been included in the Integrated Schedule - as stated in Troy Anderson's presentation to TPTF on Aug 25,08 (see lines 15 and 35 of the attached presentation "06-Post Baseline 2 NPRRs.") Of specific interest is NPRR091 and NPRR102 | Power and Gas Consulting | Troy
NPRRs | On the EMS report, NPR 102 implementation referenced Load Resources. How does all the remaining tasks of NPRR 102 being done? | Reliant | Troy
NPRRs | Where is the current “grey boxed” list? | AEP | Troy
Network Model, SEM | Network Model should be in a PSSE and base model CIM format for TSP’s efforts to validate the network model. This will keep the validation effort on schedule. Formats other than PSSE and base model CIM may require a longer validation due to each of the TSP’s converting data plus the risk of data loss in the conversion | AEP | Linda, Matt
Network Model, SEM | It does not appear there are parallel operations on the TSP for SEM. However, we would encourage additional time (not on the critical path) for SEM business process testing and additional training by ERCOT as needed | AEP | Linda, Matt
Network Model, SEM | Before the TSP’s conduct our validation, all up to date system changes and all relevant information needs to be in NMMS for a good validation. Additionally, as identified by the TPTF, the TSP’s need to look on ERCOT’s systems to validate the model. As we are aware, this is a long process and a ERCOT review assuring all the relevant is in NMMS needs a sign off point by the Project Management Office. We only want to do this validation once | AEP | Linda, Matt
Network Model, SEM | ERCOT was to provide a document to the TPTF that documents the testing and validation requirements for NMMS that the TSP would use as a check off list as part of the TSP validation. We have not seen the delivery of this document at this time | AEP | Linda, Matt
Network Model, SEM | Need to address Training on NMMS and SEM. Is the training that has been given to date obsolete? Are there portions that are still usable | AEP | Linda, Matt
Network Model, SEM | MP training on NMMS, SEM, etc… has not been identified in the schedule and is a critical component for MP’s | AEP | Linda, Matt
MMS | MMS5 is critical path from Jan. 9, 2009 – Aug. 24, 2009; QSEs testing prior to this adds little value. Time should be spend on test case development. | AEP | Jeff, Matt
MMS | MMS MM UI interface with MP have not been approved by TPTF. How can the system be in FAT in Feb if the requirements have just been brought to TPTF for approval sometime in Jan 2009? | Reliant | Jeff, Kate
OS | In OS, what is the status of the SCR to fix the problems with QSEs being able to enter their outages of all owned transmission elements? Where is this in the schedule? | Reliant | Krish, Jeff
Integration | In the Integration slide 25, how can you perform any meaningful performance testing without MP driving the applications? | Reliant | Mike
Integration | Luminant is concerned about the ongoing communication of FAT and Integration test results to Market Participants (MP) during 2009. In part, these communications are needed to provide information to the market regarding the functionality of the market systems under the various test market scenarios. We believe it is important that the market be provided an ongoing opportunity to understand the response of ERCOT systems to help in the design of internal market participant applications and confirm the continued accuracy of existing internal and MP-to-ERCOT interface applications. Additionally, Luminant is concerned that Market Participant involvement is assured when ERCOT is considering the resolution of FAT or Integration Test deficiencies that impact system functionality or existing Market Participant – to – ERCOT interface designs.Consequently, we would like to understand how ERCOT proposes to report the deficiencies, proposed resolutions and final resolutions to Market Participants. To the extent there is a role to be played by TPTF and the various market participant committees and subcommittees in this process, the responsibilities and response times for all need to be explicitly described. | Luminant | Mike
Reports and Extracts | Verbal comment from LCRA – want to know schedule for availability of reports and extracts. She said her Settlements team was there and they’re used to being “left out”. They were pleased that the COMS presentation addressed their needs with respect to invoices and statements. They’re going to submit a request that we lay out dates for extracts as well | LCRA | Jackie
EDS | The Go live sequence identified in the schedule needs to be reviewed by ROS and should be a control point that the Go live meet the reliability requirements of ERCOT | AEP | Matt
EDS | The EDS restart schedule is too late to assure delivery even in Dec 2010. It took 8 months to get EDS with MPs working. Restarting EDS after this much delay, will need to have at least 4 months to get all MPs back to where they were this past April. | Reliant | Matt
EDS | The 6 months of posting of reasonable LMPs to begin in 2010. Need this earlier in 2009 to find if there are modeling problems | Reliant | Matt
EDS | The handbooks do not reflect current durations and have not been updated since 3/2008. The expectations for the MPs is unclear | AEP | Matt
EDS | Preliminary EDS project timeline starts at January 2010, does that mean that testing for 2009 will not be required? | AEP | Matt
EDS | Relates to EDS slide that said ERCOT is behind schedule in delivering a validated model with final RARF data Mar. 9: Validated Model with Final RARF data (v1.21 schema and data set) - Why would MPs start testing again if we don’t have the final RARF? | AEP | Matt
EDS | Testing results reports need to be developed to a level of detail that MP’s can take corrective action and modify internal business processes. Current test results are fairly generic and vague if a MP has a flaw in the data, (without naming names) a description of the flaw and corrective action would be more aid to MP’s than “issue resolved” for major issues. A Quality Assurance Review of the Results and the adequacy of the controls used during the test plan is warranted but not identified in this high level schedule. It should be addressed in the detail schedule with input from the sub-groups. | AEP | Matt
EDS | Why wouldn’t we spend time on Test data required and test cases before testing? The current tests are using resources time for something that adds little value. Currently the MPs are doing more testing then originally required per the handbooks | AEP | Matt
EDS | All [EDS] dates are 2010. Why is ERCOT talking about 2009 testing if the schedule is for 2010? | AEP | Matt
EDS | “Execute SCED with the objective of publishing LMPs for 6 months” This is where testing ended, so are we going to stop testing till Feb 2010? | AEP | Matt
EDS | System Reliability testing is not identified on the schedule. We strongly encourage ERCOT to allow for business process and TSP interface testing on issues such as congestion relief process/procedures, scenario testing and evaluation of coordination efforts • System Reliability Business Process and TSP interface stress testing : This testing would involve testing congestion relief processes and procedures. Several scenario’s would be tested on the system to assure TSP’s coordination and congestion relief actions are adequate for system reliability. • System Reliability Testing (During the 48-hour & 168-hour tests were congestion relief and outage events handled according to established business process and integration with TSP coordinators. i.e. was the system more or less reliable) | AEP | Matt
EDS | The handbooks do not reflect the new dates and it is unclear what is expected for testing in 2009. The schedules reflects the testing that was remaining and it is all in 2010 | AEP | Matt
EDS | In general, test result reports (for ICCP telemetry for example) frequently need additional detail that MP go dig for at ERCOT. If there were more detail in the reports without naming name, we could learn more from the reporting and check our systems for the types of data errors identified in the testing | AEP | Matt
EDS | Aug 21 09 - This is the logical start data for MPs to begin testing again. As stated above “Market participant activities that were placed on hold are not restarted until the NMMS/EMS/MMS5 systems are on a synchronized model (schema and data set) | AEP | Matt
EDS | Begin functional integration testing and operational readiness (Apr. - July 2009) This is another logical start data for MPs to begin testing again. As stated above “Market participant activities that were placed on hold are not restarted until the NMMS/EMS/MMS5 systems are on a synchronized model (schema and data set) | AEP | Matt
EDS | Outage Scheduler sandbox testing for business processes and interface issues does not appear to be on the critical path. Therefore, we would request that additional sandbox testing time be allowed for business processes and interface issues so that we may test our interfaces to the Outage Scheduler system | AEP | Matt
EDS | No reference to Outage Scheduler training, How much training time is in the detail schedule? Can we have more time for training and testing since the OS is not on the critical path it appears? | AEP | Matt
EDS | One thing I would like to see going forward is a way to ensure our comments are followed up after making requests in market calls. For example, I had asked several questions (can I submit trades for multiple days via web service) in the last EDS and never heard back | Shell | Matt